## PMCCalls
S.No | Date received | Job No. | Contractor/ Main Supplier | Supplier | Handled By | Item | Ordered Quantity | Offered Qty | Inspection Date (From) | Inspection Date(Upto) | Inspection Attended (From) | Inspection Attended(Upto) | Review dates | IRN Endorsement Date | Order Status | QAP rev. request | QAP appl. | Remarks | No. of Days
1 | 2021-11-03 | B016 | L&T | KSBMIL | BT | Control Valves |  | 70 |  |  |  |  | 7,8-11-2021 | 2021-11-08
2 | 2021-11-10 | B224 | L&T ECC(Water Blk) | Flowserve | US | Pumps | 21 | 11 | 2021-11-10 | 2021-11-25 | 2021-11-10 | 2021-11-25
3 | 2021-11-11 | B224 | Linde | Micon | BT | Valves |  | 37 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12
4 | 2021-11-12 | B224 | TPL/Sulzer | Tmeic | SV | Motors | 16 | 8 |  |  |  |  | 9,12-11-2021 | 2021-11-12
5 | 2021-11-16 | B224 | Toyo | Godrej | YVT | Busducts |  | 13 |  |  |  |  | 2021-11-12 | 2021-11-16
6 | 2021-11-18 | B224 | Toyo/Hamon | ABB | YVT | Motors | 12 | 12 | [5 empty] | 2021-11-22
7 | 2021-11-19 | B287 | Toyo | Tyco | NV | FA system | [6 empty] | 2021-11-24
8 | 2021-11-21 | B224 | L&T ECC(Water Blk) | Godrej | YVT | Busducts |  | 6 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-22 |  | P
9 | 2021-11-21 | B224 | L&T ECC(Water Blk) | Godrej | YVT | Busducts | 10 | 10 | 2021-11-25 | 2021-11-26 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-06 | C |  |  | After confirmation of readiness & rect. Of Int. test repts
10 | 2021-11-22 | A538 | B&R |  | BT | LR Bends | [9 empty] | 2021-11-22 | 2021-11-22
11 | 2021-11-23 | B224 | Toyo(DHDT) | Flowserve | US | Pumps |  | 2 | 2021-11-30 | 2021-12-02
12 | 2021-11-23 | B224 | Toyo(DHDT) | ABB | YVT | Drives | [6 empty] | 2021-11-23 | 2022-02-17 |  |  |  | JNK Heater - IRN endors after review of compliance
13 | 2021-11-17 | B016 | L&T | KSBMIL | BT | Control Valves |  | 83 |  |  |  |  | 16,17-Nov-21 | 2021-11-17
14 | 2021-11-23 | B016 | L&T | YIL | VR | Magnetic Flowmeters | 19 | 19 |  |  |  |  | 9,22,29-Nov-21,03-Feb-22 | 29-11-2021,03-Feb-22 | C |  |  | 17 nos clrd; 2nos- recal. At FCR involved-clrd on 3/2/22
15 | 2021-11-23 | B016 | L&T | YIL | VR | VA Flowmeters |  | 18 |  |  |  |  | 9,11,22-Nov-21 | 2021-11-23 | C
16 | 2021-11-24 | A538 | B&R |  | AG | TCP | [9 empty] | 2021-11-24 |  | reviewd by SV on 8/12, after appl of BOM
17 | 2021-11-24 | B224 | TPL/Sulzer | ABB | SV | Motors | 6 | 6 | 2021-12-06 | 2021-12-08 |  |  | 2022-02-21 | 2022-02-21 | C |  |  | LV DOL Motors - Doc rev.
18 | 2021-11-25 | B240 | BHEL,Hyd | E&H | SV | Field Insts | [9 empty] | 2021-11-25 | 2021-11-29 | Inst Pkg QAP appls.
19 | 2021-12-03 | B248 | BLK Ahmedabad | Climaveneta | AG | Chiller | 5 | 2 | 2021-12-09 | 2021-12-10 | 2021-12-09 | 2021-12-10 | 2022-01-05 |  |  |  |  | Client:NHSRCL
20 | 2021-12-04 | B016 | L&T | KSBMIL | BT | Control Valves |  | 44 | [9 empty] | Doc.rev
21 | 2021-12-09 | B224 | L&T ECC(Water Blk) | Flowserve | US | Pumps | 21 | 16 | 2021-12-15 | 2021-12-17 | [7 empty] | Fin.Insp
22 | 2021-12-10 | B224 | Hamon | YIL | VR | Magnetic Flowmeters | 5 | 5 |  |  |  |  | 13-12-2021,23/7/22;02-sep-23 | 2023-09-02 |  |  |  | Doc.rev as per agreed ITP
23 | 2021-12-23 | B224 | L&T ECC(Water Blk) | Hitachi Energy | YVT | APFC | 5 | 5 | 2021-12-28 | 2021-12-29 | 2022-01-06 | 2022-01-07 | 1,9,21/3/22 | 2022-03-21 | C |  |  | queries sent on 24/12;rev on 2,11,14/2
24 | 2022-01-04 | B287 | Afcons | Emerson | NV | Vortex FM | 2 | 2 | 2022-01-06 | 2022-01-07 |  |  | 2022-08-04 | 2022-08-04 | C |  |  | items not reached FCRI as on 5/1/22; recal done & 0.65% accr recd- client/pjts accepted & TPI IRN endorsed on 4/8/22
25 | 2021-12-30 | B016 | L&T | Schneider | SV | Switch Bds | 4 | 4 |  |  |  |  | 06,7-Jan-22 | 2022-01-07
26 | 2022-01-07 | B224 | Linde | Belgaum Aqua | BT | Ball Valves | 47 | 47 | 2022-01-11
27 | 2022-01-27 | B215 | Thermax | KSBMIL | BT | Valves | 21 | 17 | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-09
28 | 2022-02-01 | B215 | Thermax | ABB | NV | Motors | 6 | 6 | 2022-02-03 | 2022-02-04 | 2022-02-03 | 2022-02-04 | 2022-02-26 | 2022-02-26 |  |  |  | IRN to be endorsed after resolution of combined testing related comments
29 | 2022-02-01 | B016 | L&T | YIL | VR | Magnetic Flowmeters | 19 | 19 |  |  |  |  | 9,22,29-Nov-21,03-Feb-22 | 29-11-2021,03-Feb-22 | C |  |  | 17 nos clrd; 2nos- recal. At FCR involved-clrd on 3/2/22
30 | 2022-02-02 | B016 | L&T/Incosoft | YIL | VR | Magnetic Flowmeters |  | 12 |  |  |  |  | 2022-02-03
31 | 2022-02-09 | B224 | L&T/Sulzer | Tmeic | SV | Motors | 8 | 8 | 2022-02-22 | 2022-02-26 | 2022-02-22 | 2022-02-26 | 11,14-feb-22 |  |  |  |  | HT motors
32 | 2022-02-10 | B224 | YIL (L&T-DHDT) | YIL | NV | DCS |  |  | 2022-02-14 | 2022-02-19 | 2022-02-14 | 2022-02-19 | 11-02-2022,4/3/22 | 2022-03-04
33 | 2022-02-11 | B224 | Tata Pjts(DCU) | Hitachi Energy | YVT | APFC & Capacitor Panel | 2 | 2 | 2022-02-21 | 2022-02-22 | 2022-02-21 | 2022-02-22 | 2022-03-04 | 2022-04-06 | C |  |  | Insp Aft.Code1 appl; TPI IRN/Compliance recd on 4/4/22
34 | 2022-02-13 | B224 | YIL (CT1,U&O) | YIL | NV | DCS |  |  | 2022-02-22 | 2022-02-24 | 2022-02-22 | 2022-02-24 | 2022-03-04 | 2022-03-04 |  |  |  | EIL/Hammon
35 | 2022-02-15 | B224 | Toyo | YIL | NV | WirelessTx |  |  | 2022-02-21 | 2022-02-22 | 2022-03-04 | 2022-03-05 | 2022-03-07 | 2022-10-23 | P |  |  | 160-180 txers;2panels - Code 1 drgs fwded on 2/3/22 by Toyo & sought fresh insp dates -Rel. of HHC & Laptop pending compliance issue
36 | 2022-02-16 | B224 | Tata Pjts(CDU)/Patel Airtemp | ABB | SV | Drives | 18 | 18 | 2022-02-21 | 2022-02-22 | 2022-03-08 | 2022-03-11 | 22-03-2022;14-jul-22 | 2022-07-14 | C |  |  | upon readiness of drives & conf. of Test bed facility recd on 2/3/22, insp firmed up; Combined testing compliance recd,reviewed & IRN endorsed on 14/7/22
37 | 2022-02-21 | B215 | Themax/BHEL | IL | US | Control Valves | 3 | 1 | 2022-02-28 |  |  |  |  | 2022-03-01 |  |  |  | queried if it can be reviewed by us.
38 | 2022-02-22 | B240 | BHEL,Hyd/Blr | Schneider | SV | MCC/DCDB | 3 | [8 empty] | 2022-02-22 |  | B240/16 S/o - no QAP appl - only Std ITP to be followed.
39 | 2022-02-22 | B224 | Tata Pjts (CDU) | YIL | NV | Magnetic Flowmeters | 3 | 3 | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-15 | 2022-07-13 | 2023-07-20 |  |  |  | call for wet.cal witness @ FCRI of 2 nos-meters failed in calib.
40 | 2022-03-01 | B016 | L&T/Heurty Petrochem | ABB | SV | Drives | 6 | 6 | [9 empty] | Doc Rev.- goahead for TPI given on 1/3/22
41 | 2022-03-02 | B224 | Toyo(HGU) | YIL | NV | DCS | 1 | 1 | 2022-03-07 | 2022-03-11 | 2022-03-07 | 2022-03-11 |  |  | C
42 | 2022-03-04 | B224 | Tata Pjts (DCU) | YIL | NV | Magnetic Flowmeters | 11 | 1 | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-15 | 18,21/3/22,13/7/22 | 2022-03-21 |  |  |  | FCRI cal witness - meter failed in calib.
43 | 2022-03-07 | B224 | L&T(DFCU) | Tmeic | SV | Motors | 6 | 4 | 2022-03-21 | 2022-03-23 | 2022-04-28 | 2022-04-29 | 2022-05-19 | 19-05-2022(TPI IRN stamped on 26/5) |  |  |  | RCA for failures of prev. lot as well as int. repts for this lot not recd;4 motors reoffered for insp on 28/29/4 & clrd on 19/5- TPI IRN endorsed on 26/5/22
44 | 2022-03-09 | B224 | Tata Pjts (CDU) | Hitachi Energy | NV | APFC | 2 | 2 | 2022-03-24 | 2022-03-25 | 2022-04-26 | 2022-04-27 | 2022-05-09 |  |  |  |  | Item not ready; TPL postponed to 26/27 vide rev call dtd 19/4/22;Obs given on 9/5
45 | 2022-03-11 | B287 | Toyo | Tyco | NV | Fire Alarm | 1 | 1 | 2022-03-17 | [8 empty] | Doc. Rev of bal. items
46 | 2022-03-11 | B224 | L&T(DFCU) | Flowserve | US | Pumps |  | 2 | 2022-03-21 | 2022-03-22 | [7 empty] | Postponed by FS as items not ready
47 | 2022-03-11 | B016 | L&T | KSBMIL | BT | Control Valves | 6 | 6 |  |  |  |  | 2022-03-16 | 16-mar-22
48 | 2022-03-15 | B224 | Toyo | YIL | NV | WirelessTx |  |  | 2022-03-17 | 2022-03-21 | 2022-03-21 |  | 12,14 & 23/4,28/11/22 | 2022-10-23 | C |  |  | Pump seal insts -IRN-28/11
49 | 2022-03-15 | B224 | Tata Pjts (DCU) | Schneider | SV | Switch Bds |  | 8 | 2022-03-21 |  | 2022-03-25 |  | 2022-04-20 | 2022-04-25 | P |  |  | w/o Num.Rel-Client acc. Sought
50 | 2022-03-21 | B224 | Tata Pjts (DCU) | Flowserve | US | Pumps | 2 | 2 | 2022-03-23 |  | 2022-03-24 | 2022-03-25 | [5 empty] | Final Insp.
51 | 2022-03-21 | B016 | L&T | Flowserve | US | Pumps | 2 | 2 | 2022-03-21 |  |  |  | 2022-03-21 | 2022-03-22 |  |  |  | Doc.Rev.
52 | 2022-03-24 | 4866 | Dubas |  | SV | Batt.Charger | 7 | 7 | 2022-03-28 | 2022-03-30 | 2022-03-28 | 2022-03-30 | [5 empty] | payment deposited on 24/3/22;(4+4 sets of Batt Ch/DCDB/Cell Boos/Batt Isol Box/BMS against A538/40 & 41)
53 | 2022-03-24 | B359 | Corrtech | KEC Intl | NV | FO Cable | 284 |  | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-29
54 | 2022-03-25 | B215 | Thermax | IL | BT | Control Valves | 3 | 3 |  |  |  |  | 2022-03-28 | 2022-03-28 | C |  |  | Only doc rev.
55 | 2022-03-28 | B016 | L&T | KSBMIL | BT | Control Valves | 8 | 8 |  |  |  |  | 2022-03-28 | 2022-03-29 | C |  |  | Only doc rev.
56 | 2022-03-31 | A538 | Emerson |  | NV | Mass Flow Meters | 2 | 2 | 2022-04-05 | 2022-04-06 | 2022-04-05 | 2022-04-07 | [5 empty] | calibration witness at FCRI-fresh meters-xtnded to 7/4 becos of failure & retesting
57 | 2022-04-02 | B224 | Toyo/BHEL | FS Sanmar/RSA Turbotech | BT | Dry Gas Seal | 3 | 3 | 2022-04-07 | 2022-04-11 | [7 empty] | Toyo to revert on RSA acceptance & also items not ready
58 | 2022-04-07 | B016 | L&T | KSBMIL | BT | Control Valves | 4 | 4 |  |  |  |  | 2022-05-04 | 2022-05-04 | P |  |  | Insp for 11,12/4- our role only review;TCs fwded on 26/4 & endorsed on 4/5
59 | 2022-04-07 | B287 | Toyo | Schneider | SV | Switch Bds | 3 | 3 | 2022-04-18 | 2022-04-19 | 2022-04-18 | 2022-04-19 | 2022-05-11 | 2022-05-11 | C |  |  | 12/13 resch by Toyo to 18,19/4;int TC provided on 12/4;IRN endorsed on 11/5/22
60 | 2022-04-08 | B224 | Tata Pjts (DCU) | Schneider | SV | Switch Bds |  | 6 | 2022-04-18 | 2022-04-21 | 2022-04-20 | 2022-04-22 | 2022-04-29 | 2022-04-29 | P |  |  | after rect. Of Code1 drgs & Int. TCs-provided on 13/4
61 | 2022-04-12 | B224 | L&T (DFCU) | Flowserve | US | Pumps | 8 | 8 |  | 2022-04-26 | 2022-04-26 | 2022-04-29 | [5 empty] | perf./MRT/strip(EIL insp. Visit- 26 to 29/4/22)
62 | 2022-04-13 | B224 | L&T ECC(Water Blk) | KEC Intl | NV | FO Cable | 20.25 | 20.25 | 2022-05-04 | 2022-05-05 | 2022-05-04 | 2022-05-05 | 2022-05-10 | 2022-05-12 | C |  |  | item not ready;fresh call issued on 27/4
63 | 2022-04-14 | B215 | Thermax | ABB | SV | Drives | 10 | 10 | 2022-05-17 | 2022-05-19 | 2022-05-17 | 2022-05-19 | [5 empty] | After readiness,firm insp. Call given for 17-19/5/22
64 | 2022-04-14 | B215 | Thermax | ABB | SV | Drive+Motor | 1 | 1 | 2022-05-16 | 2022-05-17 | 2022-06-09 | 2022-06-10 | [5 empty] | combined testing
65 | 2022-04-18 | B224 | L&T/Sulzer | Tmeic | SV | Motors | 2 | 2 | 2022-05-25 | 2022-05-26 | 2022-05-25 | 2022-05-26 | 2022-07-26 | 2022-08-09 | C |  |  | PFCCU-HT motors-860KW-call to be confirmed 3 days before;Firm call given on 18/5/22 for insp on 25,26/5
66 | 2022-04-25 | B224 | L&T (DFCU) | Flowserve | US | Pumps | 3 | 3 | 2022-04-27 | 2022-04-29 | 2022-04-26 | 2022-04-29 | [5 empty] | perf./MRT/strip - chk actual inspns - call is confusing
67 | 2022-05-05 | B224 | L&T(PFCCU) | Phils Engg. | BT | Reflux Drum | 1 | 1 | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-05-10 | [5 empty] | Fin.dim & Hardness chk
68 | 2022-05-07 | B224 | L&T(PFCCU) | Phils Engg. | BT | Reflux Drum | 1 | 1 | 2022-05-10 | 2022-05-13 | 2022-05-13 | 2022-05-13 | [5 empty] | Hyd.test
69 | 2022-05-14 | B224 |  | YIL | NV | DCS | 11 | 1 | 2022-05-31 | 2022-06-02 | 2022-05-31 | 2022-06-02 |  |  | C |  |  | Air & N2 section FAT
70 | 2022-05-18 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 3 | 3 | 2022-06-06 | 2022-06-10 | 2022-05-23 | 2022-05-27 | [5 empty] | Perf/NPSH
71 | 2022-05-18 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 15 | 15 | 2022-06-06 | 2022-06-10 | 2022-05-23 | 2022-05-27 | [5 empty] | Perf/NPSH/doc rev
72 | 2022-05-18 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 3 | 3 | 2022-06-06 | 2022-06-10 | [7 empty] | Perf/NPSH/doc rev
73 | 2022-05-20 | B224 | L&T(DFCU) | Tmeic | SV | Motors | 2 | 2 | 2022-06-03 | 2022-06-04 |  |  | 2022-08-03 | 2022-08-03 | C |  |  | a/c - Sulzer-650Kw,6.6KV Motors
74 | 2022-05-27 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-06-01 | 2022-06-02 | 2022-06-01 | 2022-06-01 | [5 empty] | Dim.chk
75 | 2022-06-03 | B224 | L&T(PFCCU) | Godrej | SV | Busducts | 24 | 24 | 2022-06-20 | 2022-06-21 | 2022-06-20 | 2022-06-21 | 2022-06-29 | 2022-06-29 |  |  |  | HV BD-Cat B (vide mail dt 14/6, earlier insp call of 13/6 changed to 20/6)
76 | 2022-06-03 | B240 | BHEL | Sandvik | SV | Heater Panel | 1 | 1 |  |  |  |  | 2022-07-05 | 2022-07-05 | C | 2022-06-03 | 2022-06-07 | QAP rev.appd on 15/6;Doc rev & IRN endorsement on 5/7/22
77 | 2022-06-06 | B224 | Hitachi Energy(220KV SwYard) | Hitachi Energy | SV | ECS Panel | 4 | 4 | 2022-06-10 | 2022-06-10 | 2022-06-10 |  | 2022-06-28 | 2022-06-28 | C |  |  | 6th insp call for 8th - docs sought & insp firmed up on 10thPeenya unit;compliance sent on 28/6
78 | 2022-06-13 | B224 | L&T(DFCU) | BelloSeal | BT | Bellow Seal Valves | 98 | 98 | [9 empty] | Cat B*(Doc rev &IRN endorse)
79 | 2022-06-14 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-06-21 | 2022-06-21 | 2022-06-22 | [6 empty] | Dim.chk of 1 vessel + Hyd test of 1 Vessel
80 | 2022-06-15 | B240 | BHEL | BHEL | SV | GTC | 1 | 1 | [7 empty] | 2022-06-15 |  | ICP appl.for SwBds & acc.
81 | 2022-06-21 | B215 | Thermax | ABB | SV | Drive+Motor | 1 | 1 | 2022-06-23 |  | 2022-06-23 |  | 2022-07-14 | 2022-07-14 | C |  |  | combined testing-repetition- issues resolved during a mtg of all stake holders on 14/7/22
82 | 2022-06-27 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-07-07 |  | 2022-07-07 | [6 empty] | Dim.chk of 1 vessel + of another Hydro vessel (orig call for 30/6 for dim of 1)
83 | 2022-06-28 | B224 | L&T (DFCU) | Tmeic | SV | Motors | 4 | 4 | 2022-07-18 | 2022-07-19 | 2022-07-18 | 2022-07-19 | 2022-08-17 | 2022-08-17 | C |  |  | 180KW-4 nos-SV mail dt14/7
84 | 2022-07-05 | B224 | L&T (DFCU) | Tmeic | SV | Motors | 2 | 2 | 2022-07-21 | 2022-07-22 | 2022-07-25 | 2022-07-26 | 2022-08-12 | 2022-08-12 | C |  |  | 2nos 250Kw motor routine & type a/c Sulzer
85 | 2022-07-07 | B302 | Corrtech | KEC Intl | NV | FO Cable | 230 | 230 | 2022-07-11 | 2022-07-12 | 2022-07-12 | 2022-07-14 | 2022-07-16 | 2022-07-16 | C
86 | 2022-07-07 | B359 | Corrtech | KEC Intl | NV | FO Cable | 20 | 20 | 2022-07-11 | 2022-07-12 | 2022-07-12 | 2022-07-14
87 | 2022-07-07 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-07-12 |  | 2022-08-03 | [6 empty] | Hyd. For 1 vessel - combined & another call given for 2/8 - attended on 3/8
88 | 2022-07-17 | B224 |  | YIL | NV | DCS | 11 | 1 | 2022-07-18 | 2022-07-29 | 2022-07-18 | 2022-07-29 | 17,19-Aug-22 | 2022-08-19 | C |  |  | CDU/VDU section
89 | 2022-07-20 | B240 | BHEL | Schneider | SV | Switch Bds | 1 | 1 | 2022-07-22 |  | 2022-07-22
90 | 2022-08-02 | B224 | Toyo | Tyco | NV | Fire Alarm | 1 | 1 | [9 empty] | Rev.of TPI repts & docs
91 | 2022-08-02 | B215 | Thermax | ABB | SV | Drives | 2 | 2 | 2022-08-08 | 2022-08-09 | 2022-08-08 | 2022-08-09
92 | 2022-08-06 | B224 | L&T(PFCCU) | Flowserve India | US | Control Valves | 17 | 17 | 2022-08-19 | 2022-08-24 | 2022-08-22 | 2022-08-25 | 2022-08-29 | 2022-08-30
93 | 2022-08-09 | B224 | L&T(DFCU) | Godrej | SV | Busducts | 8 | 3 | 2022-08-23 | 2022-08-25 | 2022-08-23 | 2022-08-25 | [5 empty] | Client witness involved
94 | 2022-08-17 | B016 | L&T | ABB | SV | Drives | 3 | 3 | 2022-08-19 | 2022-08-20 |  |  | 2022-09-30 | 2022-09-30 | C |  |  | Clarification sought - EIL scope limited to review.
95 | 2022-08-18 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-08-22 | 2022-08-22 | [7 empty] | Fin Dim Insp
96 | 2022-08-25 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-08-29 | 2022-08-30 | 2022-08-30 | [6 empty] | Hyd.test
97 | 2022-08-25 | B240 | Sopan | Schneider | SV | Switch Bds | 2 | 2 | 2022-08-29 | 2022-08-30 | 2022-09-05 | 2022-09-06 | [5 empty] | readiness conf. frm Sch. Recd. On 2/9
98 | 2022-08-26 | B224 | L&T (PFCCU) | Schneider | SV | Switch Bds | 5 | 5 | 2022-09-05 | 2022-09-08 | 2022-09-05 | 2022-09-09
99 | 2022-08-26 | B224 | Tata Pjts(CDU/VDU) | YIL | NV | Magnetic Flowmeters | 2 | 2 | 2022-09-12 | 2022-09-16 | 2022-09-12 | 2022-09-13 | [5 empty] | FCRI cal.
100 | 2022-08-26 | B224 | Tata Pjts(DCU) | YIL | NV | Magnetic Flowmeters | 2 | 2 | 2022-09-12 | 2022-09-16 | 2022-09-12 | 2022-09-13 | [5 empty] | -do-
101 | 2022-09-01 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 4 | 4 | 2022-09-12 | 2022-09-14 | 2022-09-19 | 2022-09-23
102 | 2022-09-01 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 7 | 7 | 2022-09-19 | 2022-09-23 | 2022-09-19 | 2022-09-23
103 | 2022-09-03 | B224 | DCU section | YIL | NV | DCS | 1 | 1 | 2022-09-19 | 2022-09-29 | 2022-09-19 | 2022-09-29 | 2022-09-30 | 2022-10-22 | C
104 | 2022-09-05 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-09-12 |  | 2022-09-12 | [6 empty] | Fin. Dim Insp
105 | 2022-09-05 | B224 | L&T(PFCCU) | Flowserve India | US | Control Valves | 17 | 4 | 2022-09-15 | 2022-09-17 | 2022-09-19 | 2022-09-20
106 | 2022-09-07 | B224 | L&T ECC(Water Blk) | Flowserve | US | Pumps | 21 | 3 | 2022-09-13 | 2022-09-16 | 2022-09-13 | 2022-09-16
107 | 2022-09-08 | B224 | L&T(DFCU) | Godrej | SV | Busducts | 8 | 8 | 2022-09-16 | 2022-09-17 | 2022-09-14 | 2022-09-15
108 | 2022-09-10 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 16 | 16 | 2022-09-13 | 2022-09-15 | 2022-09-13 | 2022-09-15
109 | 2022-09-15 | B224 | L&T(EPCC03) | Phils Engg. | AG | Vessel | 1 | 1 | 2022-09-20 | 2022-09-21 | 2022-09-21 | [6 empty] | 1Hyd & 1Fin Dim
110 | 2022-09-17 | B224 | L&T(DFCU) | Flowserve India | US | Pumps | 25 | 25 | 2022-10-05 | 2022-10-21
111 | 2022-09-22 | B035 | Ace Pipeline | Westcoast Optilinks | NV | FO Cable | 68 | 68 |  |  |  |  | 2022-10-15 | 2022-10-15
112 | 2022-09-22 | B240 | Sopan | Belgaum Aqua | BT | Ball Valves | 8 | 8 | 2022-09-26
113 | 2022-09-23 | B224 | L&T(PFCCU) | Flowserve India | US | Control Valves | 17 | 1 | 2022-09-23 |  | 2022-09-23
114 | 2022-09-23 | B016 | L&T | ABB | SV | Drives | 3 | 3 |  |  |  |  | 2022-09-23
115 | 2022-09-29 | B224 | L&T(PFCCU) | Tmeic | SV | Motors | 3 | 3 | 2022-10-06 | 2022-10-07 | 2022-10-06 | 2022-10-07 | 2022-11-16 | 2022-11-16 | C |  |  | A/c WPIL-180kw-IRN endors on 16/11
116 | 2022-10-03 | 8590 | EIL | AmaraRaja Batteries | SV | Batteries | 2 | 2 |  |  |  |  | 2022-09-12 | 2022-10-14 | C |  |  | rev/cl-17/10
117 | 2022-10-07 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 5 | 5 | 2022-10-11 | 2022-10-14 | 2022-10-11 | 2022-10-14 | 2022-10-31 | 2022-10-31
118 | 2022-10-11 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 17 | 17 | 2022-10-11 | 2022-10-14 | 2022-10-11 | 2022-10-14
119 | 2022-10-14 | B224 | Hamon | Hach DHR | NV | Analyser | 2 | 2 | 2022-10-19 |  | 2022-10-19 | [6 empty] | Unitisation/Perf/MRT/NPSH/doc rev of various pumps
120 | 2022-10-14 | B224 | Tata Pjts | Schneider | SV | Switch Bds | 2 | 2 | 2022-10-19 | [8 empty] | Short supplies for MV swbds
121 | 2022-10-15 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 2 | 2 | 2022-10-26 | 2022-10-27
122 | 2022-10-27 | B224 | L&T(DFCU) | ABB | SV | Drives | 2 | 2 | 2022-11-03 | 2022-11-04 | 2022-11-02 | 2022-11-03 | [5 empty] | Boldrocchi s/o
123 | 2022-10-28 | B224 | VGO/HDT section | YIL | NV | DCS | 1 | 1 | 2022-11-10 | 2022-11-19 | 2022-11-14 | 2022-11-19 | [5 empty] | FAT resch fm 14Nov
124 | 2022-10-29 | B224 | L&T(DFCU) | Godrej | SV | Busducts | 4 | 4 | 2022-11-07 |  | 2022-11-07
125 | 2022-10-31 | B224 | L&T ECC(Water Blk) | Flowserve | US | Control Valves | 52 | 43 | 2022-11-15 | 2022-11-21 |  |  | 2022-12-01 | 2022-12-01 | P
126 | 2022-11-04 | B302 | Oswal | Auma | AG | Actuators | 104 | 30 |  |  | 2022-11-16 |  | 2022-11-22 | 2022-11-22 | P |  |  | Multiple lots in Nov & early dec
127 | 2022-11-03 | B224 | L&T(DFCU) | Flowserve | USAG | Pumps | 2 | 2 | 2022-11-16 | 2022-11-18 | 2022-11-23 | 2022-11-25
128 | 2022-11-04 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 7 | 7 | 2022-11-16 | 2022-11-18 | 2022-11-15 | 2022-11-18 | 2022-11-29 | 2022-11-29
129 | 2022-11-10 | B224 | L&T (PFCCU) | Schneider | SV | Switch Bds | 5 | 5 | 2022-11-14 | 2022-11-16 | 2022-11-14 | 2022-11-16 | 2022-11-25 | 2022-11-25
130 | 2022-11-07 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 6 | 6 | 2022-11-24 | 2022-11-25 | 2022-11-23 | 2022-11-25 | [5 empty] | call rech. Frm 7 to 9/11/22
131 | 2022-11-07 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 8 | 8 | 2022-11-24 | 2022-11-25 | 2022-11-23 | 2022-11-25
132 | 2022-11-08 | B224 | L&T(DFCU) | Flowserve | BT | Control Valves | 6 | 6 | 2022-11-16 | 2022-11-18 | 2022-11-18 | 2022-11-23
133 | 2022-11-08 | B224 | L&T(PFCCU) | Flowserve | BT | Control Valves | 2 | 2 | 2022-11-17 | 2022-11-21 | 2022-11-18 |  | 2022-11-28 | 2022-11-28 |  |  |  | subject to reconfirmation on 14/11
134 | 2022-11-08 | B224 | L&T(DFCU) | Flowserve | BT | Control Valves | 6 | 6 | 2022-11-18 | 2022-11-21 | 2022-11-23 | 2022-11-24 | [5 empty] | based on prov. Of intl tcs
135 | 2022-11-09 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 5 | 5 | 2022-11-28 | 2022-11-29 | 2022-11-23 | 2022-11-25
136 | 2022-11-10 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 2 | 2 | 2022-11-24 | 2022-11-25 | 2022-11-23 | 2022-11-25 | 2022-12-19 | 15,19-12-2022 |  |  |  | 2 pumps CEIL IRN 68 rev & cl. On 15/1213 pumps rev & cl on 19/12- CEIL IRN 67 dt 30/11/22
137 | 2022-11-12 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 2 | 2 | 2022-11-29 | 2022-12-02 | 2022-11-23 | 2022-11-25 | [5 empty] | Perf-2 pumps
138 | 2022-11-11 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 6 | 6 | 2022-11-29 | 2022-11-30 | 2022-11-23 | 2022-11-25 | 2022-11-28 | 2022-11-28 |  |  |  | 8 nos IRN on 28/11
139 | 2022-11-15 | B224 | Tata Pjts(DCU) | Enginemates | BT | Tube Bundle | 2 | 2 | 2022-11-21 |  | 2022-11-21 | [6 empty] | Earlier call of 17 & 29 clubbed to 21/11-rev.call on 15/11
140 | 2022-11-11 | B224 | Tata Pjts(DCU) | Enginemates | US | Tube Bundle | 1 | 1 | 2022-11-29 | [8 empty] | Hyd.Test
141 | 2022-11-14 | B016 | BGR | Swims | US | Butterfly Valves | 3 | 3 |  |  |  |  | 2022-11-14 |  |  |  |  | Doc rev & Endorsement
142 | 2022-11-14 | B224 | Tata Pjts(DCU) | Hach DHR | NV | Analyser | 2 | 2 | 2022-11-18 |  |  |  | 2022-12-21 | 2022-12-22 | C |  |  | call cancelled
143 | 2022-11-17 | B224 | L&T ECC(Water Blk) | Schneider | SV | Switch Bds | 2 | 2 | 2022-12-05 | 2022-12-06 | 2022-12-05 | 2022-12-06 | 2022-12-16 | 2022-12-19 | C
144 | 2022-11-17 | B224 | Tata Pjts(DCU) | Schneider | SV | Switch Bds | 1 | 1 | [9 empty] | Rev of short supply items-Relays
145 | 2022-11-17 | B224 | L&T(DFCU) | Belgaum Aqua | BT | Valves | 412 | 412 | 2022-11-17 |  |  |  | 2022-11-17 | 2022-11-17 |  |  |  | Only doc rev.
146 | 2022-11-19 | B224 | Hamon(CWTP) | YIL | NV | Magnetic Flowmeters | 1 | 1 | 2022-11-21 | 2022-11-23 | 2022-11-21 | 2022-11-23 | [5 empty] | failed again
147 | 2022-11-25 | B224 | L&T(DFCU) | Emerson | NV | Mass Flow Meters | 14 | 14 | 2022-12-07 | 2022-12-09 | 2022-12-07 | 2022-12-09 | 2022-12-26 | 2022-12-26 | C
148 | 2022-11-25 | B224 | Tata Pjts(DCU) | Enginemates | BT | Tube Bundle | 2 | 2 | 2022-11-30 |  | 2022-12-02 | [6 empty] | MRT-resch -1/12
149 | 2022-11-25 | B224 | L&T(DFCU) | Emerson | NV | Mass Flow Meters | 14 | 14 | 2022-12-12 | 2022-12-15
150 | 2022-11-28 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | Switch Bds | 7 | 7 | 2022-12-06 | 2022-12-09 | 2022-12-06 | 2022-12-09
151 | 2022-11-30 | A538 | Kalpataru | Microfinish | BT | Valves | 5 | 5 | 2022-12-02 |  | 2022-12-02
152 | 2022-11-30 | B224 | Megha(LLDP) |  | SV | GIS | [11 empty] | QAP appl
153 | 2022-11-30 | B224 | Megha(LLDP) |  | SV | GIS | [11 empty] | QAP appl
154 | 2022-12-01 | B302 | Oswal | Auma | AG | Actuators | 74 | 74 | 2022-12-05 | 2022-12-06
155 | 2022-12-02 | B224 | L&T ECC(Water Blk) | Flowserve | US | Control Valves | 52 | 22 | 2022-12-12 | 2022-12-16 | 2022-12-12 | 2022-12-16
156 | 2022-12-06 | B378 | Flowserve | Tmeic | SV | Motors | 2 | 2 | 2022-12-15 | 2022-12-16 | 2022-12-15 | 2022-12-16 | [5 empty] | 250KW Motors
157 | 2022-12-07 | B224 | Tata Pjts (DCU) | ABB | NV | Drives | 2 | 2 | 2022-12-13 | 2022-12-14 | 2022-12-13 | 2022-12-14
158 | 2022-12-08 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 3 | 3 | 2022-12-19 | 2022-12-21 | 2022-12-19 | 2022-12-21 | 2022-12-29 | 2022-12-29 | P |  |  | MOM dt 20/12
159 | 2022-12-09 | B224 | L&T(DFCU) | Emerson | NV | Vortex FM | 4 | 4 | 2022-12-20 | 2022-12-23 | 2022-12-20 | 2022-12-23 | [5 empty] | sch. to be confirmed on 13/12
160 | 2022-12-09 | B224 | L&T(PFCCU) | Schneider | SV | Switch Bds | 4 | 4 | 2022-12-20 | 2022-12-23 | 2022-12-20 | 2022-12-23 | 2022-12-29 | 2022-12-29 | P |  |  | 4Swbd+Accessories/spares
161 | 2022-12-12 | B224 | L&T(DFCU) | Hitachi Energy | SV | Capacitors | 5 | 5 | 2022-12-19 | 2022-12-20 | 2022-12-27 | 2022-12-28 | 18-01-2023,30-mar-23 | 2023-03-30 | C |  |  | aft.sorting out Peenya/Dbpur loc. Issue; ITCs not yet given as on 23/12
162 | 2022-12-12 | B302 | Oswal | Auma | AG | Actuators | 74 | 74 | 2022-12-15
163 | 2022-12-12 | B224 | L&T(DFCU) | YIL | NV | Analyser | 23 | 23 | 2022-12-22 | 2022-12-23 | [7 empty] | FAT proc. Not appd - postponed
164 | 2022-12-12 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 5 | 5 | 2022-12-27 | 2022-12-30 |  |  | 06,09-Jan-23 |  |  |  |  | Head rise issue
165 | 2022-12-14 | B224 | Megha(LLDP) | Voltamp | SV | Transformer | [9 empty] | 2022-12-14 | 2022-12-14
166 | 2022-12-14 | B016 | L&T | KSBMIL | US | Control Valves | 2 | 2
167 | 2022-12-15 | B224 | L&T(PFCCU) | Flowserve | US | Control Valves | 1 | 1 | 2022-12-29 | 2022-12-29 | 2022-12-22 | 2022-12-23 | 2022-12-26 | 2022-12-29
168 | 2022-12-16 | B224 | L&T(DFCU) | Flowserve | US | Control Valves | 58 | 54 | 2022-12-23 | 2022-12-29 | 2022-12-22 | 2022-12-23 | 2022-12-30 | 2022-12-30 |  |  |  | visit made on 30/12 also
169 | 2022-12-19 | B224 | L&T(DFCU) | Belgaum Aqua | BT | Valves | 171 | 171 |  |  |  |  | 2022-12-23 | 2022-12-23 |  |  |  | only doc rev.
170 | 2022-12-19 | B224 | L&T(DFCU) | BelloSeal | US | Valves | 28 | 28 |  |  |  |  | 2022-12-20 | 2022-12-20 |  |  |  | only doc rev.
171 | 2022-12-21 | B224 | L&T(DFCU) | BelloSeal | US | Valves | 34 | 34 |  |  |  |  | ?? |  |  |  |  | only doc rev.
172 | 2022-12-23 | B224 | Tata Pjts(DCU) | Enginemates | US | At.Vent Cond. | 1 | 1 | 2022-12-27 |  | 2022-12-27
173 | 2022-12-27 | B224 | L&T(DFCU) | Hitachi Energy | SV | Capacitors | 2 | 2 | 2023-01-06 |  | 2023-01-06
174 | 2023-01-02 | B224 | L&T(DFCU) | Flowserve | AG | Control Valves | 58 | 26 | 2023-01-12 | 2023-01-17 | 2023-01-11 | 2023-01-13 | 2023-01-27
175 | 2023-01-03 | B224 | YIL (U&O) | YIL | NV | DCS | [9 empty] | 2023-01-05 |  | Sig cab.QAP rev
176 | 2023-01-05 | B224 | L&T(DFCU) | YIL | NV | Analyser | [9 empty] | 2023-01-05 | 2023-01-05 | FAT proc. Rev.
177 | 2023-01-07 | B224 | Tata Pjts(DCU) | Enginemates | BT | Tag no- 114-A-1042 | 1 | 1 | 2023-01-16 |  | 20-jan-23 | [6 empty] | MRT
178 | 2023-01-09 | B224 | L&T(DFCU) | Belgaum Aqua | BT | Valves | 279 | 279 |  |  |  |  | 2023-01-13 | 2023-01-13 |  |  |  | Only Doc rev
179 | 2023-01-11 | B224 | L&T(ECC) | Flowserve | US | Control Valves | 6 | 6 | 2023-01-20 | 2023-01-23 | 2023-01-23 | 2023-01-24 | 2023-01-29 | 2023-01-29 |  |  |  | fin. Conf to be provided by 19/1
180 | 2023-01-12 | B224 | L&T(DFCU) | Hitachi Energy | SV | Capacitors | 2 | 2 | 2023-01-23 | 2023-01-24 | 2023-01-23 | 2023-01-24 | 20-02-2023 & 7 Mar23 | 2023-03-07
181 | 2023-01-17 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | Switch Bds |  |  | 2023-01-23 | 2023-01-25 | 2023-01-23 | 2023-01-25
182 |  | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 2 | 2 | 2023-01-23 | 2023-01-25 | 2023-01-23 | 2023-01-25 | 2023-01-31 | 2023-01-31
183 | 2023-01-18 | B224 | L&T(PFCCU) | Hitachi Energy | SV | Capacitors | 2 | 2 | 2023-02-08 | 2023-02-09 | 2023-02-08 | 2023-02-09 | 2023-03-14 | 2023-03-16
184 | 2023-01-19 | B224 | Linde | Flowserve | US | Control Valves | 2 | 2 | 2023-01-19 |  | 2023-01-19 |  | 2023-01-23 | 2023-02-03
185 | 2023-01-21 | B224 | MEIL(LLDPE) | Bruckhardt | NV | E&I QAP | [9 empty] | 2023-01-21 | 2023-01-25 | QAP not in order- comments given
186 | 2023-01-25 | B224 | EIL-PFCCU | YIL | NV | DCS | 1 | 1 | 2023-02-13 | 2023-02-18 | 2023-02-14 | 2023-02-21 | [5 empty] | Resc & extended
187 | 2023-01-25 | B224 | Tata Pjts(DCU) | Enginemates | AG | Tag no- 114-A-1004 | 1 | 1 | 2023-01-30 | 2023-02-01 | 2023-01-30 | 2023-02-02 | 2023-02-09 |  |  |  |  | Hyd & MRT; doc rev on 9/2
188 | 2023-01-27 | B224 | L&T(DFCU) | ABB | SV | Drive | 1 | 1 | 2023-03-10 | [8 empty] | Boldrochi -125-PM-1110 - Int. TCs given on 28/2 & call revised to 10/3 on 2/3/23; not ready on 10/3 - fresh call not recd
189 | 2023-02-03 | B224 | L&T(DFCU) | YIL | NV | Analyser | 23 | 23 | 2023-02-13 | 2023-02-15 | 2023-02-14 | 2023-02-16 | 2023-03-14 |  |  |  |  | based on finalisation of FAT proc.(10/2 msil fm L&T)
190 | 2023-02-03 | B224 | L&T(DCU) | Hach DHR | NV | Analyser | 2 | 2 | 2023-02-13 |  | 2023-03-03 |  |  | 2023-10-13 |  |  |  | resch to 3/3(L&T mail 27/2)
191 | 2023-02-07 | B224 | L&T(ECC) | ABB | SV | SAS | 1 | 1 | 2023-02-22 | 2023-02-23 | 2023-02-23 |  | 2023-03-14 | 2023-03-14
192 | 2023-02-09 | A538 | B&R | Dubas | SV | Batt Charger | 1 | 1 | 2023-02-15 | 2023-02-17 | 2023-02-15 | 2023-02-17
193 | 2023-02-03 | B016 | L&T | FS Sanmar/RSA Turbotech | BT | Dry Gas Seal | 1 | 1 |  |  |  |  | 2023-02-17 | 2023-02-17 |  |  |  | only doc. Rev
194 | 2023-02-13 | B224 | L&T(DFCU) | Flowserve | BT | Pumps | 2 | 2 | 2023-02-27 | 2023-03-01 | 2023-02-28 | 2023-03-01 | [5 empty] | perf & MRT
195 | 2023-02-13 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 3 | 3 | 2023-02-20 | 2023-02-22 | 2023-02-20 | 2023-02-22 | 2023-02-27 | 2023-02-28
196 | 2023-02-14 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 1 | 1 | 2023-02-23 |  | 2023-02-22 |  | 2023-03-14 | 2023-03-14 |  |  |  | Short supplied Num. Relays
197 | 2023-02-09 | B378 | GreenPower | TDPS | SV | Alternator | 1 | 1 | 2023-02-28 | 2023-03-01 | 2023-02-28 | 2023-03-01
198 | 2023-02-15 | B224 | L&T(PFCCU) | Schneider | SV | Switch Bds | 1 | 1 | 2023-02-24 |  |  |  | 2023-03-10 | 2023-03-10 |  |  |  | Short supplied Num. Relays
199 | 2023-02-16 | B224 | L&T(DFCU) | Microprecision | NV | Wedge Flowmeter | 3 | 3 | 2023-02-24 | 2023-02-28 | 2023-02-28 | 2023-03-02 | [5 empty] | FCRI wet. Cal.- insp postponed by L&T vide their mail dt. 22/2/23
200 | 2023-02-15 | B224 | Megha(LLDP) | Voltamp | SV | Transformer | [9 empty] | 2023-02-15 | 2023-02-20 | QAP Rev1
201 | 2023-02-15 | B224 | TPL(CDU/VDU) | Tmeic | SV | Motors | 6 | 6 | 2023-03-01 | 2023-03-06 | 2023-03-03 | 2023-03-08 | 2023-06-26 |  |  |  |  | Tech.Reunidas;6 motors(200,280&270Kw) + 1combined testing
202 | 2023-02-02 | B224 | L&T(PFCCU) | Flowserve | BT | Control Valves | 12 | 12 | 2023-02-16 | 2023-02-18 | 2023-02-16 | 2023-02-18 | 2023-03-07 | 2023-03-07 |  |  |  | IRN given on 3/3 for endorsement
203 | 2023-02-20 | B215 | Thermax | KSBMIL | NV | Control Valves | 13 | 7 | 2023-02-21 |  | 2023-02-27 |  | 2023-03-14 | 2023-03-14 |  |  |  | CatC converted to CatB by Client.Vlvs TCs provided on 24/2
204 | 2023-02-20 | A538 | ECIL | Adarsha | NV | Control Desk | 1 | [5 empty] | 2023-02-25 |  |  |  |  | Doc sub for rev.
205 | 2023-02-21 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 2 | 2 | 2023-02-21 | 2023-02-23 | 2023-02-21 | 2023-02-23 | [5 empty] | MRT 129P2104A,Doc rev 128P1832A/B/C during AG's visit
206 | 2023-02-23 | B215 | Thermax | Microfinish | US | Valves | 4 | 4 | 2023-02-24 |  | 2023-03-07 |  | 2023-03-28 | 2023-03-28
207 | 2023-02-24 | B224 | MEIL(LLDPE) | Voltamp | SV | Transformer | [9 empty] | 2023-02-23 | 2023-02-24 | Rev2 for appl.
208 | 2023-02-02 | B224 | Toyo | Tyco | NV | Fire Alarm | 1 | 1 |  |  |  |  | 17,25Feb23 |  |  |  |  | Rev of FA docs
209 | 2023-02-20 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | Switch Bds | 2 | 2 | 2023-02-21 | 2023-02-22 | 2023-02-21 | 2023-02-22 | 2023-02-27 | 2023-02-28
210 | 2023-02-28 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 50 | 50 | 2023-03-06 | 2023-03-10 | 2023-03-13 | 2023-03-15
211 | 2023-03-02 | B378 | BHEL | Triveni | US | Gear Box | 2 | 2 | 2023-03-15 | 2023-03-17 | 2023-03-15 | 2023-03-17
212 | 2023-03-02 | B297 | Coperion | Micon | US | Ball Valves | 55 | 55 | 2023-03-02 | 2023-03-03 | 2023-03-07 | 2023-03-08
213 | 2023-03-02 | B224 | L&T(DFCU) | YIL | NV | Analyser | 5 | 5 | 2023-03-10 |  | 2023-03-10 |  | 2023-03-14 | 2023-03-14 |  |  |  | was not ready- reinsp involved
214 | 2023-03-03 | B224 | L&T(DFCU) | Flowserve | US | Control Valves | 10 | 10 | 2023-03-10 | 2023-03-13 | 2023-03-11 |  | 2023-03-14 | 2023-03-14 |  |  |  | 2 nos clrd on 14/3/22
215 | 2023-03-08 | B224 | TPL(CDU/VDU) | ABB | SV | Motors | 1 | 1 | 2023-03-10 |  | 2023-03-10 | [6 empty] | Technicas Reunidas- Combined testing - 110KW motor
216 | 2023-03-08 | B224 | TPL(CDU/VDU) | ABB | SV | Motors | 2 | 2 | 2023-03-15 | 2023-03-16 | 2023-03-15 | [6 empty] | Technicas Reunidas- Combined testing - 132KW& 90KW motor+Schneider drive
217 | 2023-03-13 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 2 | 2 | 2023-03-30 | 2023-04-03 | 2023-03-30 | 2023-03-31 | [5 empty] | 128P1830 MRT,strip,CUT
218 | 2023-03-13 | B224 | MEIL(PPU) | Nidec | SV | Motors | [9 empty] | 2023-03-13 |  | sought ref. docs for review
219 | 2023-03-07 | B224 | L&T(DFCU) | Godrej | SV | Busducts | 5 | 5 | 2023-03-16 | 2023-03-17 | 2023-03-20 | 2023-03-21 | 2023-03-30 | 2023-03-30 | P |  |  | 2nos 3200A BD clrd on 30/3/23; 5000A BDs temp rise to be re-offered as Engg. Has not accepted margin of rise
220 | 2023-03-14 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 23 | 23 | 2023-03-20 | 2023-04-13 | 2023-03-28 | 2023-03-31
221 | 2023-03-14 | B224 | TPL(CDU/VDU) | ABB | SV | Drives | 2 | 2 | 2023-03-15 | 2023-03-17 | 2023-03-15 |  | 2023-07-15 | 2023-07-15 |  |  |  | 132 &90Kw Comb.testing with Hitachi Drives:90Kw cancelled
222 | 2023-03-14 | B224 | TPL(DCU) | ABB | SV | Drives | 27 | 27 | 2023-03-21 | 2023-03-24 | 2023-03-21 | 2023-03-24 | 2023-10-16 | 2023-10-16 |  |  |  | A/c -Enginemates-Combined testing
223 | 2023-03-14 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 4 | 4 | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-29 | 2023-04-01 | 2023-04-01
224 | 2023-03-14 | B224 | Megha(LLDP) | [12 empty] | 2023-03-14 | 2023-03-22 | CT Fan Motors - Marathon Motors a/c PCTL
225 | 2023-03-14 | B224 | L&T(PFCCU) | Emerson | NV | Vortex FM | 8 | 8 | 2023-03-23 | 2023-04-06 | [7 empty] | sch to be conf. on 20/3;our queries on RCA yet to be answered
226 | 2023-03-15 | B224 | L&T(DFCU) | Hitachi Energy | SV | APFC | 1 | 1 | 2023-03-22 | 2023-03-24 | [7 empty] | to be taken up after closure of issues pert. To Lot 1 & its rels.
227 | 2023-03-15 | B224 | L&T(DFCU) | Flowserve | US | Control Valves | 3 | 3 | 2023-03-22 | 2023-03-24 | 2023-03-23 | 2023-03-24 | 2023-03-28 | 2023-03-28 |  |  |  | 22 postponed by FS on a/c of Ugadi holiday
228 | 2023-03-16 | B224 | Megha(LLDP) |  | SV | TR unit Cathodic Protection | [9 empty] | 2023-03-16 | 2023-03-22 | SARK EPC Pjts
229 | 2023-03-21 | B224 | Technip Energies(MS Block/PFCC) | Alleima | BT | Electric Heater | 2 | 2 | 2023-03-23 | 2023-03-27 | 2023-03-24 | 2023-03-27 | 2023-07-29 | 2023-07-29
230 | 2023-03-23 | B224 | TPL(CDU/VDU) | Tmeic | NV | Motors | 6 | 2 | 2023-03-25 | 2023-03-27 | 2023-04-03 | 2023-04-04 | 2023-05-23 | 2023-05-23 |  |  |  | Tech.Reunidas;6 motors(200 &280Kw)- combined testing -resch. By TPL to 3/4 Apr
231 | 2023-03-21 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valvestachi | 99 |  | 2023-03-22 | 2023-03-24 |  | 2023-03-22 | 2023-03-24 | 2023-03-28
232 | 2023-03-21 | B224 | Tata Pjts(DCU) | Enginemates | US | Tag no- 114-A-1001 | 1 | 1 | 2023-03-30 | 2023-04-03 | 2023-03-30 | 2023-04-04 | [5 empty] | Hyd on 30/3 & MRT on 3/4
233 | 2023-03-21 | B224 | L&T(DFCU) | YIL | NV | Analyser | 23 | 23 | 2023-03-27 | 2023-03-28 | 2023-03-27 | 2023-03-28 | 2023-05-04
234 | 2023-03-21 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 2 | 2 | 2023-04-04 | 2023-04-05 | [7 empty] | Tags:129P2104A/B
235 | 2023-03-15 | B215 | Thermax | KSBMIL | NV | Control Valves | 7 | 7 | 2023-03-24 |  | 2023-03-24 |  | 2023-03-30 | 2023-03-30
236 | 2023-03-23 | B224 | TPL(CDU/VDU) | Tmeic | NV | Motors | 1 | 1 | 2023-04-04 |  | 2023-04-04 |  | 2023-05-04 | 2023-05-23 |  |  |  | Tech Reunidas:280Kw Routine test
237 | 2023-04-03 | B224 | Technip Energies(MS Block/PFCC) | Alleima | US,NV | Electric Heater | 2 | 2 | 2023-04-05 |  | 2023-04-05 |  | 2023-08-07 | 2023-07-29 |  |  |  | US-Mech & NV- Control Panel Insp - BT IRN on 29/7; NV query on 7/8/23
238 | 2023-04-06 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 8 | 8 | 2023-04-11 | 2023-04-13 | 2023-04-11 | 2023-04-13 | 2023-04-24
239 | 2023-04-07 | B224 | L&T | Godrej | SV | Busducts | 2 | 2 | 2023-04-17 |  | 2023-04-21 |  | 2023-04-25 | 2023-04-25 |  |  |  | 5000A- reinsp of Temp Rise- call revised to 21/4/23
240 | 2023-04-08 | B224 | TPL(DCU) | Hydac | AG | Boom Luff Hydraulic Cylinder | 1 | 1 | 2023-04-13 |  | 2023-04-18 | [6 empty] | Thysssen Krupp S/o-details recd. On 17/4-insp taken up on 18/4
241 | 2023-04-07 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 83 | 83 | 2023-04-17 | 2023-04-20 | 2023-04-17 | 2023-04-20 | 2023-04-21
242 | 2023-04-06 | B240 | Sopan | Shridhan | BT | SS Chamber | [9 empty] | 2023-04-06 | 2023-04-10 | response given
243 | 2023-04-10 | B215 | Thermax | KSBMIL | NV | Control Valves | 1 | 1 | 2023-04-12 |  | 2023-04-20
244 | 2023-04-10 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 2 | 2 | 2023-04-27 | 2023-04-28 | 2023-04-26 | 2023-04-28 | [5 empty] | 128P1832A/B-final
245 | 2023-04-12 | B224 | L&T(DFCU) | Hitachi Energy | SV | APFC Panel | 2 | 2 | 2023-04-18 | 2023-04-19 | 2023-04-18 | 2023-04-19 | 2023-05-12 | 2023-05-12 | C |  |  | 4500KVAR
246 | 2023-04-14 | B224 | Megha(PPU) | Voltamp | SV | Power T/f | [9 empty] | 2023-04-14 | 2023-04-17
247 | 2023-04-13 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 3 | 3 | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27
248 | 2023-04-17 | B224 | L&T(DFCU) | YIL | NV | Analyser | 13 | 13 | 2023-04-24 | 2023-04-27 | [7 empty] | cancelled by L&T due to non availability of EIL appd docs
249 | 2023-04-17 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | Switch Bds | 1 | 1 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-28 | 2023-05-18 | 2023-05-18 | C
250 | 2023-04-10 | B224 | EIL | YIL | NV | FO Cable | 118 | 118 |  |  |  |  | 2023-04-18 | 2023-04-20
251 | 2023-04-18 | B224 | L&T(DFCU) | Flowserve | BT | Pumps | 2 | 2 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-09 | [5 empty] | 129P2104A/B-2hr run test
252 | 2023-04-18 | B224 | Megha(PPU)/Kirl.Pneu | Severn Glocon | VR | Control Valves | [9 empty] | 2023-04-18 |  | query sent on 19/4/23
253 | 2023-04-20 | B224 | L&T(PFCCU) | Godrej | NV | Busducts | 1 | 1 | 2023-05-27 |  |  | 2023-05-02 | [5 empty] | 11KV, 2500A Busduct (BD-111-KM-1101)
254 | 2023-04-20 | B224 | Technip Energies(MS Block/PFCC) | Godrej | SV | Busducts | 11 | 11 | 2023-05-05 | 2023-05-12 | 2023-05-04 | 05,11,12-05-2023 | [5 empty] | Insp attended on 4,5,11,12th may (2500 & 4000A)
256 | 2023-04-25 | B297 | Coperion | Ultrafilter | US | Filters |  |  | 2023-04-29 | [8 empty] | Matl Identification
257 | 2023-04-22 | B224 | Megha/LLDPE | EIA | VR | Control Panel | [9 empty] | 2023-04-22 | 2023-04-24
258 | 2023-04-24 | B224 | MEIL(LLDPE) | Bruckhardt | NV | E&I QAP | [9 empty] | 2023-04-24 | 2023-05-01 | QAP resubmission
259 | 2023-04-24 | B224 | Megha(LLDP) | Voltamp | SV | Transformer | [9 empty] | 2023-04-24 | 2023-05-19 | QAP Rev2
260 | 2023-04-29 | B224 | L&T(DFCU) | YIL | NV | Analyser | 6 | 6 | 2023-05-15 | 2023-05-19 | 2023-05-15 | 2023-05-19 | 31/7,14-Aug-23 | 2023-08-14 |  |  |  | Rev. Call on 10/5/23; 13cab +1ShelterAS-007
261 | 2023-05-01 | B398 | Corrtech | KEC Intl | NV | FO Cable | [9 empty] | 2023-05-01
262 | 2023-05-04 | B224 | TPL(DCU) | ABB | SV | Drives | 1 | 1 | 2023-05-22 | 2023-05-23 | 2023-05-25 | 2023-05-26 | [5 empty] | 55Kw motor/vfd combined testing- Rev. to 26/5 on 22/5
263 | 2023-05-03 | B224 | TPL(DCU) | Flowserve | US | Pumps | 2 | 2 | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-05-17 | [5 empty] | Filtrex S/o-114-A-1038 A/B - perf/mrt
264 | 2023-05-03 | B224 | Megha/PPU | Voltamp | SV | Transformer | [9 empty] | 2023-05-03 | 2023-05-09
265 | 2023-05-07 | B240 | Sopan | Belgaum Aqua | BT | Valves | 23 | 23 | 2023-05-08
266 | 2023-05-06 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valvestachi | 100 | 100 | 2023-05-23 | 2023-05-26 | 2023-05-23 | 2023-05-26 | 05,09-06-2023 | 2023-06-09 |  |  |  | insp revised to 23-26 on 16/5
267 | 2023-05-08 | B302 | PLN Constn | KEC Intl | NV | FO Cable | 6 | 6 | 2023-05-08 | 2023-05-09 | 2023-05-11 | 2023-05-12
268 | 2023-05-06 | B224 | TPL | YIL | NV | Magnetic Flowmeters | 1 | 1 | 2023-05-15 |  | 2023-05-15
269 |  | B224 | TPL | ABB | SV | Motors | 1 | 1 | 2023-05-15 | 2023-05-16 | 2023-05-15 | 2023-05-16 | [5 empty] | 90Kw combined testing with Hitachi Drive-retest a/c Tecnicas Reunidas
270 | 2023-05-10 | B224 | Tata Pjts(DCU) | Enginemates | BT | Tag no- 114-A-1002 | 1 | 1 | 2023-05-15 | 2023-05-17 | 2023-05-15 | 2023-05-17 | [5 empty] | Hydro & MRT
271 | 2023-05-10 | B224 | Megha(LLDP) | [12 empty] | 2023-05-10 | 2023-05-19 | CT Fan Motors Rev2 - Marathon Motors a/c PCTL
272 | 2023-05-15 | B224 | Tata Pjts(CDU/VDU) | YIL | NV | Mass Flow Meters | 4 | 4 | 2023-06-05 | 2023-06-08 | 2023-06-05 | 2023-06-08 | [5 empty] | 4MFM Cal@FCRI
273 | 2023-05-15 | B224 | EIL- U&O | ABB | NV | SCADA | 1 | 1 | 2023-05-29 | 2023-05-31 | 2023-05-29 | 2023-05-31 | [5 empty] | HRRL job
274 | 2023-05-17 | B224 | Technip Energies(MS Block/PFCC) | Godrej | SV | Busducts | 1 | 1 | 2023-05-23 |  | 2023-05-23 | [6 empty] | 4000A Temp Rise - Failed
275 | 2023-05-18 | B239 | HAL Offshore | Schneider | SV | Switch Bds | 2 | 2 | 2023-05-15 |  | 2023-05-22 |  |  | 2023-05-26 | C |  |  | Extn Panels
276 | 2023-05-18 | B224 | Megha/PPU | BHEL | SV | Motors | [9 empty] | 2023-05-18 | 2023-05-19 | Bruckhardt Compr - submitted in BHEL format
277 | 2023-05-19 | B224 | Megha(PPU)/Kirl.Pneu | Severn Glocon | VR | Control Valves | [9 empty] | 2023-05-19 | 2023-05-22
278 | 2023-05-19 | B224 | Megha(LLDPE)/Kirl.Pneu | Severn Glocon | VR | Control Valves | [9 empty] | 2023-05-19 | 2023-05-22
279 | 2023-05-19 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 8 | 8 | 2023-05-24 | 2023-05-26 | 2023-05-24 | 2023-05-26
280 | 2023-05-19 | B224 | L&T(DFCU) | Flowserve | BT | Pumps | 2 | 2 | 2023-05-24 | 2023-05-26 | 2023-05-24 | 2023-05-26
281 | 2023-05-19 | B224 | Megha/LLDPE | BHEL | SV | Motors | [9 empty] | 19/5 & 24-6-2023 | 2023-05-19 | Bruckhardt Compr - submitted in BHEL format;Rev 3 app on 24/6
282 | 2023-05-24 | B224 | L&T(DFCU) | YIL | NV | Analyser | 4 | 4 | 2023-06-05 | 2023-06-05 |  |  | 2023-06-27 | 2023-06-27 |  |  |  | TOC anal.
283 | 2023-05-25 | B224 | Tata Pjts(DCU) | Enginemates | US | Tag no- 114-A-1002 | 1 | 1 | 2023-06-02 |  | 2023-06-02 | [6 empty] | Vis/Dim/Hyd
284 | 2023-05-25 | B016 | L&T | Flowserve | US | Pumps | 4 | 4 | 2023-06-13 | 2023-06-14 | 2023-06-13 | 2023-06-14
285 | 2023-05-25 | B224 | Megha(PPU) | Positronics | VR | Local Control Panel | [9 empty] | 2023-05-25 | 2023-05-26
286 | 2023-05-26 | B224 | L&T(DFCU) | YIL | NV | Analyser | 13 | 13 | 2023-06-05 | 2023-06-05 |  |  | 05-07,25/8-2023 | 2023-08-25 |  |  |  | Para O2 Anal;rev of shelter docs on 5/7
287 | 2023-05-29 | B224 | L&T(DFCU) | Emerson | NV | Mass Flow Meters | 1 | 1 | 2023-06-08 | 2023-06-09 | 2023-06-08 | 2023-06-09 | [5 empty] | FCRI Cal of Coriolis MFM
288 | 2023-05-29 | B224 | L&T(DFCU) | Flowserve | BT | Pumps | 3 | 3 | 2023-06-08 | 2023-06-15 |  |  | 2023-06-26 | 2023-06-26 |  |  |  | MRT,Perf
289 | 2023-05-31 | B224 | L&T(DFCU) | ABB | SV | Drives | 2 | 2 | 2023-06-07 |  | 2023-06-07 | [6 empty] | Boldrocchi - VFD testing - 125-K-1110 to 125-K-1150-earlier calls postponed because of doc appl/T/f availability etc. 490Kw/690V VFD
290 | 2023-06-03 | B224 | Megha(LLDPE)/Kirl.Pneu |  | NV | [10 empty] | 2023-06-03 | 2023-06-13 | Rev3 E&I ICP
291 | 2023-05-30 | B224 | L&T(DFCU) | Schneider | SV | Switch Bds | 1 | 1 |  |  |  |  | 2023-06-03 | 2023-06-03 |  |  |  | Rev of lot 2 of Sht Supplied Num Relays
292 | 2023-06-05 | B224 | Megha(SRU) | Siemens | SV | GIS | [9 empty] | 2023-06-05 | 2023-06-12
293 | 2023-06-06 | B224 | L&T(DFCU) | Flowserve | US | Control Valves | 1 | 1 | 2023-06-15 | 2023-06-19 | 2023-06-19 | 2023-06-26
294 | 2023-06-05 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 4 | 4 | 2023-06-08 | 2023-06-09 | 2023-06-13 | 2023-06-14 | [5 empty] | 105-P-0006 A/B -4HPX13A -2# - Fin. Insp
295 | 2023-05-23 | B224 | EIL | YIL | NV | Cables | [6 empty] | 2023-06-09 | 2023-06-09
296 | 2023-06-07 | B224 | TPL(DCU) | Hydac | AG | Boom Luff Hydraulic Cylinder | 1 | 1 | 2023-06-13 | 2023-06-14 | 2023-06-13 | 2023-06-14 | 12-09,3,25/10-2023 | 2023-10-25 |  |  |  | Thyssen Krupp order- Fin Insp@Ctore
297 | 2023-06-14 | B224 | Megha(PPU) | Sundyne | SV | Motors | [9 empty] | 2023-06-14
298 | 2023-06-21 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 12 | 12 | 2023-06-26 | 2023-06-29 | 2023-06-26 | 2023-06-29
299 | 2023-06-19 | B224 | Megha(LLDP) | Voltamp | SV | Transformer | [9 empty] | 2023-06-19 | 2023-07-09 | Rev3 QAP
300 | 2023-06-22 | B224 | Technip Energies(MS Block/PFCC) | Godrej | SV | Busducts | 1 | 1 | 2023-06-23 |  | 2023-06-23 | [6 empty] | 4000A Temp Rise test
301 | 2023-06-27 | B224 | Megha(STG Pk9) |  | SV | GIS | [9 empty] | 2023-06-27 |  | GIS ITP Rev0
302 | 2023-06-27 | B224 | L&T(DFCU) | Emerson | NV | Vortex FM | 11 | 11 | 2023-07-10 | 2023-07-21 | 2023-07-10 | 2023-07-21 | [5 empty] | Wet cal +Hyd test @FCRI-reoffer
303 | 2023-06-27 | B224 | Tata Pjts(DCU) | Enginemates | BT | Tag no- 114-A-1001 | 1 | 1 | 2023-07-07 |  | 2023-07-10 | [6 empty] | Vis/Dim/hydro - postponed by Enginemates
304 | 2023-06-27 | B224 | Megha(STG Pk9) |  | SV | GIS | [9 empty] | 2023-06-27 |  | GIS ITP Rev0
305 | 2023-07-03 | B182 | Sopan | Belgaum Aqua | US | Valves | 40 | 40 | 2023-07-07 |  | 2023-07-07 |  | 2023-07-13 | 2023-07-13
306 | 2023-07-03 | B224 | Megha(STG Pk9) |  | SV | GIS | [9 empty] | 2023-07-03 | 2023-07-04 | GIS ITP Rev0
307 | 2023-07-06 | B224 | Megha(SRU) |  | SV | MOV | [9 empty] | 2023-07-06 |  | not QAP - proc.related queries
308 | 2023-07-10 | B224 | Megha(PPU) | Positronics | VR | Local Control Panel | [9 empty] | 2023-07-10 | 2023-07-11 | QAP Rev2
309 | 2023-07-11 | B224 | Megha(PPU) | KPC/ABB | SV | Motors | [9 empty] | 2023-07-11
310 | 2023-07-12 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 8 | 8 | 2023-07-20 | 2023-07-25 |  |  | 2023-08-08
311 | 2023-07-12 | B224 | Tata Pjts(DCU) | Enginemates | BT | 114-A-1002 | 1 | 1 | 2023-07-18 |  | 2023-07-24 | [6 empty] | Vis/Hyd.
312 | 2023-07-12 | B224 | Technip Energies(MS Block/PFCC) | KSBMIL | NV | Control Valves | 90 | 90 | 2023-07-17 | 2023-07-18 | 2023-07-17 | 2023-07-18 | 26-07-2023 & 6-aug-23 | 2023-08-07
313 | 2023-07-17 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | Switch Bds | 1 | 1 | 2023-07-25 |  | 2023-07-25 |  | 2023-08-02 | 2023-08-02
314 | 2023-07-20 | B224 | Megha(SRU) | Voltamp | SV | Transformer | [9 empty] | 2023-07-20 |  | Rev4 QAP
315 | 2023-07-22 | B224 | Megha(STG Pk9) |  | SV | GIS | [6 empty] | 2023-08-07 |  |  | 2023-07-22 | 2023-07-27 | Rev1 QAP
316 | 2022-07-21 | B224 | L&T(DFCU) | YIL | NV | Analyser | 1 | 1 | 2023-07-24 | 2023-07-25 | 2023-07-24 | 2023-07-25 | 2023-08-01 |  |  |  |  | An.Shelter AS09
317 | 2023-07-19 | B224 | Tata Pjts(DCU) | Schneider | SV | Switch Bds | 1 | 1 | 2023-07-24 | 2023-07-25 | 2023-07-24 | 2023-07-25 | 2023-08-04 | 2023-08-04 |  |  |  | replacement for transit damage
318 | 2023-07-18 | B378 | BHEL | BHEL | NV | ASC | [9 empty] | 2023-07-18 | 2023-07-25 | ASC of BHEL EDN
319 | 2023-07-26 | A922 | Exide |  | SV | Batteries |  |  | 2023-07-28 |  | 2023-07-28 | [6 empty] | Insp @ Exide Hosur
320 | 2023-07-18 | B378 | BHEL | Gov Panel | NV | [10 empty] | 2023-07-18 | 2023-07-26 | Gov.Cont.Panel
321 | 2023-07-26 | B239 | HAL Offshore | Microfinish | US | Valves |  |  | 2023-08-01 | 2023-08-02 | 2023-08-01 | 2023-08-02
322 | 2023-07-27 | B224 | Tata Pjts(DCU) | Enginemates | BT | 114-A-1002 | 1 | 1 | 2023-08-07 |  | 2023-08-07 | [6 empty] | Vis/Hyd.
323 | 2023-07-28 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 2 | 2 | 2023-08-10 | 2023-08-11 | 2023-08-10 | 2023-08-11 | [5 empty] | 126-P-2225 A/B perf/MRT - Client part. Inv.
324 | 2023-07-28 | B224 | Megha(PPU) | Bruckhardt/CGL | SV | Motors | [9 empty] | 2023-07-28
325 | 2023-07-28 | B224 | Tata Pjts(CDU/VDU) | Tmeic | SV | Motors | 4 | 4 | 2023-08-07 | 2023-08-08 | 2023-08-07 | 2023-08-08 | [5 empty] | 210KW-2nos a/c FS
326 | 2023-08-02 | B302 | Likita | Birla Cable | NV | FO Cable | [9 empty] | 2023-08-02 | 2023-08-08
327 | 2023-08-02 | B224 | L&T(DFCU) | ABB | SV | VFD | 2 | 2 |  |  |  |  | 2023-08-02 |  |  |  |  | Combined test results of Bold.VFD at ABB Vad compltd & IRN endors of VFD sought
328 | 2023-08-01 | B224 | L&T(DFCU) | Schneider | SV | Sw.Bds | [6 empty] | 2023-08-01 | 2023-08-01 |  |  |  | Rev&IRN end. For Sh.supplied Relays
329 | 2023-08-03 | B297 | Coperion | ABB | SV | Drives | 7 | 7 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11
330 | 2023-08-01 | B224 | Megha(LLDP) | Voltamp | SV | Transformer | [9 empty] | 2023-08-01 | 2023-09-14 | Rev2 QAP
331 | 2023-08-01 | B224 | Hamon | YIL | NV | Magnetic Flowmeters | [6 empty] | 2023-08-01 |  |  |  |  | Compl. Rev for 1 MFM
332 | 2023-08-01 | B224 | Megha(STG Pk9) | Gutor | SV | UPS | [6 empty] | 2023-10-18 |  |  | 2023-08-01 | 2023-08-19 | disc on 10/8, 18/10
333 | 2023-08-04 | B224 | Megha(PPU) | Voltamp | SV | Power T/f | [9 empty] | 2023-08-04 | 2023-08-10 | Rev2 QAP
334 | 2023-08-04 | B224 | Megha(PPU) | Voltamp | SV | Power T/f | [9 empty] | 2023-08-04 | 2023-08-10 | Rev3 QAP
335 | 2023-08-05 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 34 | 34 | 2023-08-10 | 2023-08-11 | 2023-08-09 | 2023-08-10 | 2023-08-26
336 | 2023-08-04 | B224 | Technip Energies(MS Block/PFCC) | KSBMIL | NV | Control Valves | 70 | 70 | 2023-08-08 | 2023-08-09 | 2023-08-09 | 2023-08-10 | 26/8,26-Sep-23,27-Oct-23,15-Dec-23 | 2023-12-15
337 | 2023-08-07 | B224 | Megha(SRU) | Siemens | SV | GIS | [9 empty] | 2023-08-07 | 2023-09-14 | Rev2
338 | 2023-08-04 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | AG | Pumps | 2 | 2 | 2023-08-11 | 2023-08-14 | 2023-08-10 | 2023-08-11
339 | 2023-08-03 | B224 | Megha(PPU) | ABB | SV | Motors | [9 empty] | 1923-08-03 | 2023-08-11 | Kir.Pneu-Coolant Compr sys - QAP R1
340 | 2023-08-07 | B297 | Coperion | Ultrafilter | US | Filters | 1 | 1 | 2023-08-09 |  | 2023-08-10
341 | 2023-08-08 | B224 | Tata Pjts (DCU) | Enginemates | BT | 114-A-1002 V | 1 | 1 | 2023-08-14 |  | 2023-08-17 | 2023-08-18 | [5 empty] | Vis/Dim/Hyd-Bay5
342 | 2023-08-08 | B378 | Summit Technodyne | Schneider | SV | Sw. Bds | 7 | 7 | 2023-08-28 |  | 2023-08-28 | [6 empty] | resch frm 24/8 to 28/8 on 16/8
343 | 2023-08-02 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | BT | Pumps | 11 | 11 |  |  |  |  | 04,08-Aug-23 | 2023-08-08 |  |  |  | Rev/IRN4&5
344 | 2023-08-08 | B224 | Megha(LLDPE) | Siemens | SV | GIS | [9 empty] | 2023-08-08 | 2023-08-19 | R0 SS-18 & SS-19
345 | 2023-08-09 | B378 | BHEL | BHEL | NV | ASC | [9 empty] | 2023-08-09 | 2023-08-18 | ASC of BHEL EDN-Rev1
346 | 2023-08-09 | B224 | YIL (U&O) |  | NV | DCS | 1 | 1 | 2023-09-12 | 2023-09-14 | 2023-09-22 | 2023-09-29 | 2023-09-27 |  |  |  |  | resch. To 20-22/9/23
347 | 2023-08-12 | B224 | Megha(LLDPE)/Kirl.Pneu | Microfinish | US | On-Off Valves | [9 empty] | 2023-08-12 | 2023-08-19
348 | 2023-08-16 | B224 | Monte Carlo | Schneider | SV | Sw. Bds | 11 | 11 | 2023-08-28 | 2023-08-31 | 2023-08-28 | 2023-08-31 | 2023-09-25 | 2023-09-25 |  |  |  | Pkg 14
349 | 2023-08-17 | B224 | Tata Pjts (DCU) | Enginemates | BT | Tag no- 114-A-1002 V | 1 | 1 | 2023-08-24 | 2023-08-28 | 2023-08-24 | 2023-08-28 | [5 empty] | Tag no- 114-A-1002 Visual, dimension & Hydro test for Bay no-6 (F1 & F2) & Bay no-7 (G1 & G2)
350 | 2023-08-18 | B398 | Likita | Birla Cable | NV | FO Cable | [9 empty] | 2023-08-18
351 | 2023-08-21 | B224 | Tata Pjts(CDU/VDU) | Tmeic | SV | Motors | 4 | 4 | 2023-08-25 |  | 2023-08-25 | [6 empty] | 210KW-2nos a/c FS- Reinsp of failed TR test
352 | 2023-08-21 | B224 | Megha(SRU) | Voltamp | SV | Transformer | [9 empty] | 2023-08-21 | 2023-09-15 | EPCC06-2.5MVA & 1.6MVA R4 QAP
353 | 2023-08-21 | B297 | Daniel | Micon | BT | Valves | 41 | 41 | 2023-08-25 |  | 2023-08-28 | 2023-08-29
354 | 2023-08-21 | B224 | Tata Pjts (DCU) | Thyssen Krupp / Sam Turbo | AG | Pumps | 1 | 1 | 2023-08-23 | 2023-08-24 | 2023-08-28 | 2023-08-29 | 2023-10-26 |  |  |  |  | Sump pump & coke settling pit
355 | 2023-08-21 | B224 | L&T(DFCU) | ABB | SV | Drives | 4 | 4 | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-13 | [5 empty] | Boldrochi - routine testing-call for 28/8; resch on 7/9 by L&T to 12,13/9
356 | 2023-08-23 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | AG | Pumps | 2 | 2 | 2023-08-28 | 2023-08-29 | 2023-08-28 | 2023-08-29
357 | 2023-08-23 | B398 | KEC Spur Infra | KEC Intl | NV | FO Cable | 156 | 156 | 2023-08-25 | 2023-08-26 | 2023-08-29 | 2023-08-30
358 | 2023-08-23 | B224 | L&T(PFCCU) | Emerson | NV | Magnetic Flowmeters | 2 | 2 | 2023-09-14 | 2023-09-15 | 2023-09-14 | 2023-09-15 | 2023-12-21 | 2023-12-21 |  |  |  | Wet Cal/Hyd/Vis
359 | 2023-08-24 | B224 | Megha (LLDPE) | Microfinish | US | Valves | 14 | 14 | 2023-08-28 | 2023-08-29 | 2023-08-28 | 2023-08-29 | 20,21-09-2023 | 2023-09-22
360 | 2023-08-24 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | AG | Pumps | 2 | 2 | 2023-08-28 | 2023-08-29 | 2023-08-28 | 2023-08-29 | [5 empty] | 106P0001A/B -Fin.
361 | 2023-08-24 | B224 | Megha(LLDPE) | Microfinish | US | Valves | [9 empty] | 2023-08-24 | 2023-08-24 | ITP Rev3
362 | 2023-08-25 | B224 | L&T(DFCU) | YIL | NV | Analysers | 13 | 13 | 2023-09-04 | 2023-09-06 | 2023-09-04 | 2023-09-06 | [5 empty] | AS01 &02-13 analysers
363 | 2023-08-30 | B224 | Tata Pjts (DCU) | Enginemates | BT | 114-A-1002 V | 1 | 1 | 2023-09-07 |  | 2023-09-07 | [6 empty] | Vis/Dim/Hyd-Bay8
364 | 2023-08-29 | B378 | Siemens | PTSS Global | BT/NV | Online T/F Drying system |  |  | 2023-09-25
365 | 2023-09-04 | B224 | L&T(DFCU) | YIL | NV | Analysers | 14 | 14 | 2023-09-07 | 2023-09-08 | 2023-09-07 | 2023-09-08 | 2023-12-26 | 2023-12-26 |  |  |  | CEMS
366 | 2023-09-02 | B224 | Megha(PPU) | Sundyne/BHEL | SV | Motors | [9 empty] | 2023-09-02 | 2023-09-07 | R0
367 | 2023-08-29 | B224 | Megha(PPU) | [12 empty] | 2023-08-29 | 2023-09-02 | Buckhardt Comp Inst ICPRev3
368 | 2023-09-05 | B224 | Megha(PPU) | Tmeic | SV | Motors | [9 empty] | 2023-09-05 | 2023-09-07 | Tmeic Rev1
369 | 2023-09-07 | B224 | L&T(DFCU) | Flowserve | BT | Control Valves | 1 | 1 | 2023-09-25 |  |  |  | 2023-09-27 | 2023-09-27 |  |  |  | Angle CV
370 | 2023-09-08 | B398 | Likita | Birla Cable | NV | OFC | [9 empty] | 2023-09-08 | 2023-09-08
371 | 2023-09-07 | B224 | Megha(LLDPE) | [12 empty] | 2023-09-07 |  | Buckhardt Comp Inst ICPRev1
372 | 1923-09-11 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 36 | 36 | 2023-09-25 | 2023-09-26 | 2023-09-29 | 2023-09-30 | 2023-10-26 | 2023-10-26
373 | 2023-09-21 | B224 | Megha(STG Pk9) | TDPS | SV | Generator | [9 empty] | 2023-09-21
374 | 2023-09-21 | B224 | L&T(DFCU) | YIL | NV | Analysers | 2 | 2 | 2023-09-27 | 2023-09-29 | [7 empty] | AS04 & Wobbe Analyser
375 | 2023-08-24 | B224 | Megha (LLDPE) | Microfinish | US | V
376 | 2023-09-14 | B224 | L&T(DFCU) | YIL | NV | Analysers | 7 | 7 | 2023-09-21 | 2023-09-22 | [7 empty] | 7CEMs tags+2 Racks
377 | 2023-09-15 | B224 | Megha(STG Pk9) | Gutor | SV | UPS | [6 empty] | 2023-10-18 |  |  | 2023-09-15 | 2023-09-15 | Rev1; Mtg on 18/10
378 | 2023-09-16 | B224 | L&T(DFCU) | YIL | NV | WirelessTx |  |  | 2023-09-25 | 2023-09-26
379 | 2023-09-18 | B224 | Technip Energies(MS Block/PFCC) | Circor | US | DSH | 8 | 8 | 2023-09-14 | [8 empty] | IBR
380 | 2023-09-15 | B224 | Tata Pjts (DCU) | Enginemates | BT | Tag no- 114-A-1006 | 1 | 1 | 2023-09-26 | 2023-09-28 | [7 empty] | Visual, dimension & Hydro test & MRT for Bay no-1 (A1 & A2)
381 | 2023-09-22 | B224 | Tata Pjts (DCU) | Flowserve | BT | Pumps | 2 | 2 | 2023-09-25 | 2023-09-26 | [7 empty] | 114-P-1038 A/B;Filtrex S/o
382 | 2023-09-21 | B224 | Megha(STG Pk9) |  | SV | Generator | [9 empty] | 2023-09-21 |  | sought ref. docs
383 | 2023-09-20 | B224 | Megha(PPU) | CGL | SV | Motors | [9 empty] | 2023-09-20 | 2023-09-25 | Buckhardt Comp- Rev1
384 | 2023-09-21 | B224 | Tata Pjts (DCU) | Schneider | SV | Sw.Bds | [11 empty] | Request for rev. of Fin.Doc.Completeness Cert.(MRB-Mfg. Rec. Book)
385 | 2023-09-27 | B224 | Technip Energies(MS Block/PFCC) | KSBMIL | NV | Control Valves | 30 | 30 | 2023-09-29 | 2023-09-30 | 2023-09-29 | 2023-09-30 | [5 empty] | 3rd Lot Withdrawn by Tecnip
386 | 2023-09-28 | B224 | L&T(DFCU) | ABB | SV | Drives | 7 | 7 | 2023-10-04 | 2023-10-06 | 2023-10-10 | 2023-10-12 | [5 empty] | resch to 10-12 by ABB based on test bed availability;10 by SV, 11&12 by NV
387 | 2023-09-28 | B224 | Tata Pjts (DCU) | Hach DHR | NV | Analysers | 2 | 2 | 2023-10-03 | 2023-10-03 | 2023-10-03 |  | 2023-10-13 | 2023-10-13
388 | 2023-09-30 | B224 | L&T(PFCCU) | Microfinish | US | Valves | 17 | 17 |  |  |  |  | 04,05-10-2023 | 2023-10-05 |  |  |  | TPI IRN rev req. on 30/9
389 | 2023-09-29 | B378 | BHEL | BHEL | NV | ASC | [9 empty] | 2023-09-29 |  | ASC of BHEL EDN- Rev1 QAP & TP
390 | 2023-09-22 | B224 | YIL (DFCU) |  | NV | DCS | 1 | 1 | 2023-10-04 | 2023-10-12 | 2023-10-04 | 2023-10-12
391 | 2023-10-04 | B224 | Tata Pjts (DCU) | Enginemates | BT | Tag no- 114-A-1006 | 1 | 1 | 2023-10-11 | [8 empty] | Bay2 (B1/B2)Vis/Hyd
392 | 2023-10-04 | B297 | Coperion | Ultrafilter | US | Filters |  |  | 2023-10-06 |  |  |  | 2023-10-06 | 2023-10-06 |  |  |  | Fin. Insp.(cont. of prev insp)
393 | 2023-10-05 | B224 | Megha(PPU) | Iris Automation | NV | Control Panel | [9 empty] | 2023-10-05 | 2023-10-16 | Bruckhardt Compr. Pkg ITP Rev 2
394 | 2023-10-06 | B224 | Tata Pjts/Filtrex (DCU) | Flowserve | US | Pumps | 2 | 2 | 2023-10-10 | 2023-10-12 | 2023-10-10 | 2023-10-12 | [5 empty] | fin insp.
395 | 2023-10-06 | B224 | Tata Pjts (DCU) | Flowserve | US | Pumps | 1 | 1 | 2023-10-10 | 2023-10-12 | 2023-10-10 | 2023-10-12
396 | 2023-10-06 | B224 | Tata Pjts (DCU) | Flowserve | US | Pumps | 1 | 1 | 2023-10-10 | 2023-10-12 | 2023-10-10 | 2023-10-12
397 | 2023-10-06 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 1 | 1 | 2023-10-10 | 2023-10-12 | 2023-10-10 | 2023-10-12
398 | 2023-10-06 | B224 | L&T(DFCU) | Flowserve | US | Pumps | 1 | 1 | 2023-10-10 | 2023-10-12 | 2023-10-10 | 2023-10-12
399 | 2023-10-06 | B224 | L&T(DFCU) | Schneider | SV | Sw Bds | [6 empty] | 04,06-Oct-23 | 2023-10-06 |  |  |  | Short supplied Relays site testing rev & endorsement
400 | 2023-10-06 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 2 | 2 | 2023-10-10 | 2023-10-12 | 2023-10-10 | 2023-10-12
401 | 2023-10-07 | B224 | Thermax | Triveni | AG | Gear Box |  |  | 2023-10-16 | 2023-10-18 | 2023-10-17 | 2023-10-19 | [5 empty] | pkg9A -UB
402 | 2023-10-06 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 2 | 2 | 2023-10-10 | 2023-10-12 | 2023-10-10 | 2023-10-12
403 | 2023-10-06 | B378 | Coperion | Tmeic | SV | Motors | 7 | 7 | 2023-10-18 | 2023-10-20 | 2023-10-17 | 2023-10-19
404 | 2023-10-09 | B224 | L&T(DFCU) | YIL | NV | WirelessTx |  |  | 2023-10-17 | 2023-10-18 | 2023-10-17 | 2023-10-18
405 | 2023-10-09 | B224 | Mahati Infra | SARK EPC | SV | TR unit Cathodic Protection | [9 empty] | 2023-10-09 |  | mfrs QAP requested on 16/10
406 | 2023-10-10 | B224 | Mahati Infra | Bharat Bijlee | SV | Motors | [9 empty] | 2023-10-10 |  | mfrs QAP requested on 16/10
407 | 2023-10-10 | B224 | L&T(DFCU) | YIL | NV | Analysers | 16 | 16 | 2023-10-18 | 19,31-10-2023 |  |  | 28-10-2023,15-dec-23 | 28-10-2023,15-dec-23 |  |  |  | 1Shelter+15 Analysers - Clrd 1 shelter+7 anal on 28/10
408 | 2023-10-11 | B224 | L&T(DFCU) | Flowserve India | US | Control Valves | 2 | 2 | 2023-11-03 | [8 empty] | 14"2500# last vlv
409 | 2023-10-11 | B224 | Megha(LLDPE)/Kirl.Pneu | Rockwell Automation | NV | PLC | [9 empty] | 2023-10-11 | 2023-10-25 | ITP Rev2 for PLC Panel
410 | 2023-10-13 | B215 | Thermax | Siemens | NV | Ultrasonic FM | 2 | 2 | 2023-10-18 |  |  |  | 2023-10-19 |  |  |  |  | wet cal @FCRI
411 | 2023-10-13 | B224 | Megha(PPU) | FCG | NV | Control Stn | [9 empty] | 2023-10-13 | 2023-11-02 | CatB - 2 QAPs- a/cBurkhardt Compression
412 | 2023-10-12 | B378 |  | Thermo Cables | VR | FF Cables | [9 empty] | 2023-10-12 | 2023-10-16
413 | 2023-10-11 | B378 | BHEL | BHEL | NV | ASC | [9 empty] | 2023-10-11 | 2023-10-16 | Rev1
414 | 2023-10-12 | B224 | L&T(DFCU) | Schneider | SV | [10 empty] | 2023-10-12 | 2023-10-16 | endorsement of MRB
415 | 2023-10-16 | B378 | Coperion | Micon | US | Valves | 132 | 132 | 2023-10-19 | 2023-10-30 | 2023-10-31
416 | 2023-10-18 | B224 | AICPL | Westcoast Optilinks | NV | FO Cable | 22 | 22 | 2023-10-30 | 2023-10-31 | 2023-10-30 | 2023-10-31 | 2023-12-20 | 2023-12-20
417 | 2023-10-18 | B224 | Megha(PPU) | Japan Steel Works | SV | Underwater Cutter Motor | [9 empty] | 2023-10-18 |  | ITP rev1- sought ref docs on 31/10
418 | 2023-10-19 | B378 | BHEL | BHEL | NV | Turbine Control Panel | [9 empty] | 2023-10-19 | 2023-11-03 | ITP & TP Rev 1
419 | 2023-10-23 | B297 | Coperion | ABB | SV | Drives |  |  | 2023-11-07 |  | 2023-11-17 |  | 2024-02-28 | 2024-02-28
420 | 2023-10-23 | B224 | Tata Pjts (DCU) | Enginemates | BT | Tag no- 114-A-1006 | 1 | 1 | 2023-10-23 | 2023-10-30 | 2023-10-31 | [6 empty] | Visual, dimension & Hydro test of Steam Coil for Bay no-4 (D1 & D2)
421 | 2023-10-15 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | US | Pumps | 2 | 2 |  |  |  |  | 2023-10-25 | 2023-10-25
422 | 2023-10-15 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | BT | Pumps | 14 | 14 |  |  |  |  | 25,26-10-2023 | 2023-10-26
423 | 2023-10-30 | B224 | Technip Energies(MS Block/PFCC) | Micon | US | Valves |  |  | 2023-10-31 | 2023-10-31
424 | 2023-10-31 | B378 | BHEL | BHEL | NV | ASC | [9 empty] | 2023-10-31 | 2023-11-07 | B378/487-ASC -CatB
425 | 2023-11-03 | B224 | L&T(DFCU) | Flowserve | US | Control Valve | 1 | 1 | 2023-11-07 | 2023-11-10 | 2023-11-07 |  | 2023-11-22 | 2023-11-22
426 | 2023-11-01 | B224 | Megha(Pkg9) | Schneider | SV | UPS | [9 empty] | 2023-11-01 | 2023-11-02 | comments provided to Pjts & they hv comm. to Megha on 3/11
427 | 2023-11-02 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | Sw Bds |  |  | 2023-11-08 | 2023-11-10 | 2023-11-08 | 2023-11-10 | 20,24-11-2023 |  |  |  |  | with HRRL participation - rev/resoln of SAS config. Issues
428 | 2023-11-01 | B224 | Megha(Pkg9) | Siemens | SV | AVR Panel | [9 empty] | 2023-11-01
429 | 2023-11-01 | B224 | L&T(DFCU) | YIL | NV | Analysers |  |  | 2023-11-07 | 2023-11-09 | 2023-11-07 | 2023-11-09 | 2023-12-27 | 2023-12-27 |  |  |  | 9 Anal+1SHelter
430 | 2023-11-02 | B215 | Thermax | Siemens | NV | Ultrasonic FM | 2 | 2 | 2023-11-21 | [8 empty] | wet cal @FCRI
431 | 2023-11-06 | B224 | Tata Pjts(DCU) | Flowserve | US | Pumps | 2 | 2 | 2023-11-22 | 2023-11-23 | 2023-11-22 | 2023-11-23 | [5 empty] | perf testing 103P113A,B
432 | 2023-11-09 | B224 | L&T(DFCU) | YIL | NV | WirelessTx | 1 | 1 | 2023-11-23 | 2023-11-24
433 | 2023-11-10 | B378 | BHEL | EIC | NV | LCP | [9 empty] | 2023-11-10 |  | B378/421-LCP of PSA Feed Compr.
434 | 2023-11-17 | B224 | Tata Pjts (DCU) | Enginemates | BT | Tag no- 114-A-1006 | 1 | 1 | 2023-11-23 | 2023-11-27 | 2023-11-22 | 2023-11-24 | [5 empty] | 4 bundles(C1,C2,D1,D2) Hyd & dim.- Total 8 bundles
435 | 2023-11-16 | B224 | Tata Pjts (DCU) | Westcoast Optilinks | NV | FO Cable |  |  | 2023-11-21 | 2023-11-22 | 2023-11-21 | 2023-11-22
436 | 2023-11-17 | B378 | BHEL | BHEL | NV | ASC |  |  | 2023-11-29 | 2023-12-01 | 2023-11-29 | 2023-12-01 | [5 empty] | ASC +Spares
437 | 2023-11-20 | B016 | BHEL | BHEL | SV | Solar Modules | [6 empty] | 2023-12-22 | 2023-12-22 |  |  |  | TPI repts to be endorsed
438 | 2023-11-17 | B224 | L&T(DFCU) | YIL | NV | Analyser | 11 | 11 | 2023-11-23 | 2023-11-24 |  |  | 2023-12-06 |  |  |  |  | AS-06+11Analysers
439 | 2023-11-20 | B224 | Megha(LLDPE) | BHEL | SV | Motors | [9 empty] | 2023-11-20 | 2023-11-20 | Rev1 QAP
440 | 2023-11-16 | B224 | L&T (DFCU) | Flowserve | BT | Pumps | 2 | 2 | 2023-11-22 | 2023-11-23 | 2023-11-22 | 2023-11-23 | [5 empty] | Impeller Rework/perf retest
441 | 2023-11-20 | B224 | Technip Energies(MS Block/PFCC) | Micon | US | Valves | 634 | 634 |  |  |  |  | 21,22-Nov-23 |  |  |  |  | TPI repts to be endorsed
442 | 2023-11-20 | B329 | Mahati Infra | ABB | SV | DCS | 1 | 1 | 2023-11-21 | 2023-11-22 | 2023-11-21 | 2023-11-23
443 | 2023-11-22 | B224 | L&T(DFCU) | YIL | NV | WirelessTx |  |  | 2023-11-23 | 2023-11-24 | 2023-11-23 | 2023-11-24 | 01,20-12-2023 | 2023-12-20 |  |  |  | pre-occupied
444 | 2023-11-22 | B224 | L&T(DFCU) | YIL | NV | DCS | 1 | 1 |  |  | 2023-11-23 |  | 24-11-2023,08-dec-23 | 2023-12-08 |  |  |  | DFCU DCS insp,doc rev & IRN endors.
445 | 2023-11-27 | B224 | Megha(PPU) | Burckhardt/FCG | NV | Control Panel | [9 empty] | 2023-11-27 | 2023-12-19 | Rev1
446 | 2023-11-27 | B224 | Thermax-EPCC9B | Schneider | SV | Sw Bds |  |  | 2023-11-29 | 2023-11-30 | 2023-11-29 | 2023-11-30 | 2023-12-21 | 2023-12-21
447 | 2023-11-27 | B224 | Technip Energies(MS Block/PFCC) | Micon | US | Valves | 195 | 195 | 2023-11-28 | 2023-11-30
448 | 2023-11-22 | B224 | L&T(DFCU) | YIL | NV | WirelessTx |  |  | 2023-12-07 |  | 2023-12-07 |  | 2023-12-27 | 2023-12-27
449 | 2023-12-08 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 16 | 16 | 2023-12-15 | 2023-12-16
450 | 2023-12-08 | B224 | Megha(LLDPE) | Kirloskar Pneu/Rockwell | NV | PLC Panel | [9 empty] | 2023-12-08 | 2023-12-19 | Rev3
451 | 2023-12-04 | B224 | Megha(Pkg9) | Vee Vee Controls | SV | NGTR | [9 empty] | 2023-12-04 | 2023-12-07 | Rev1
452 | 2023-12-04 | B224 | Megha(Pkg9) | Vee Vee Controls | SV | LA-SC-PT Panel | [9 empty] | 2023-12-04 | 2023-12-07 | Rev1
453 | 2023-12-04 | B224 | Megha(Pkg9) | ABB | SV | AVR Panel | [9 empty] | 2023-12-04 | 2023-12-07 | Rev0
454 | 2023-12-05 | B224 | Megha(Pkg9) | CGL | SV | LV Motors | [9 empty] | 2023-12-06 | 2023-12-07 | Rev0
455 | 2023-12-06 | B224 | Megha(LLDPE) | Schenck Process Solns | NV | Solid Additive Pkg System | [9 empty] | 2023-12-06 |  | Rev2 - 2 sets of QAPs
456 | 2023-12-11 | B378 | BHEL | Triveni | BT | Gear Box |  |  | 2023-12-21 | 2023-12-22 | 2023-12-21 | 2023-12-22
457 | 2023-12-07 | B224 | Megha(PPU) | KPC/Microfinish | US | On-Off Valves | [9 empty] | 2023-12-08 | 2023-12-15 | Rev3
458 | 2023-12-06 | B224 | Tata Pjts | Enginemates | US | Tag: 114-A-1006 |  |  | 2023-12-08 |  | 2023-12-20 | 2023-12-21 | [5 empty] | Tag: 114-A-1006, 7th bay. Coil G1 & G2 Hyd/dim - 2more exch. Added - total 6 exch. Dim/Hyd
459 | 2023-12-12 | B224 | Thermax-EPCC9B | Schneider | SV | Sw Bds |  |  | 2023-12-19 | 2023-12-20 | 2023-12-19 | 2023-12-20
460 | 2023-12-11 | B378 | Siemens | PTSS Global | SV | Online T/F Drying system |  |  | 2023-12-18 |  | 2023-12-18 |  |  | 2024-01-04 |  |  |  | Online Drying System
461 | 2023-12-12 | B224 | Megha(Pkg9) |  | SV | Cont Panel | [9 empty] | 2023-12-12 | 2023-12-14 | ITP R0 Add. To Pjts
462 | 2023-12-12 | B224 | Megha(Pkg9) | TDPS | SV | Generator | [9 empty] | 2023-12-12 | 2023-12-12 | ITP R0
463 | 2023-12-14 | B378 | BHEL | Triveni | BT | Gear Box |  |  | 2023-12-21 | 2023-12-22 | 2023-12-21 | 2023-12-22 | 2024-11-05 | 2024-11-05
464 | 2023-12-15 | B224 | L&T(DFCU) | Flowserve | BT | Pumps | 3 | 3 | 2023-12-18 | 2023-12-19 | 2023-12-28 | 2023-12-29 | [5 empty] | A/c GE Oil&Gas/Chem process -125-K-1300 ,125-K-1600 & 125-K-1650; Docs reqd for firming up insp call - offered on 28,29/12 aft. Doc appl
465 | 2023-12-12 | B224 | Megha(Pkg9) |  | SV | SAS Panel | [9 empty] | 2023-12-12 | 2023-12-14 | FAT proc. To Pjts
466 | 2023-12-16 | B224 | Megha(Pkg9) |  | SV | SAS Panel | [9 empty] | 2023-12-16 | 2023-12-29 | R1Fat proc
467 | 2023-12-16 | B224 | Megha(Pkg9) |  | SV | Cont Panel | [9 empty] | 2023-12-16 | 2023-12-29 | R1 ITP
468 | 2023-12-14 | B224 | L&T(DFCU) | YIL | NV | Analysers |  |  | 2023-12-21 | 2023-12-22 |  |  | 2024-02-17 |  |  |  |  | AS08+13 Analysers | 0.5
469 | 2023-12-16 | B224 | Megha(Pkg9) |  | SV | SAS Panel | [9 empty] | 2023-12-16 | 2023-12-21 | Rev1
470 | 2023-12-12 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | BT | Pumps | 2 | 2 | 2023-12-28 | 2023-12-29 | 2023-12-28 | 2023-12-29 | [5 empty] | Multistage pumps-Perf/MRT
471 | 2023-12-20 | B224 | Megha(Pkg9) | Siemens/TDPS | SV | STG | [9 empty] | 2023-12-20 | 2023-12-22 | Rev1 ITP
472 | 2023-12-25 | B224 | L&T(PFCCU) | RSA Turbotech | US | Dry Gas Seal | 1 | 1 | 2024-01-03 | 2024-01-05 | [7 empty] | Elliot Ebara/John Crane
473 | 2023-12-25 | B224 | Megha(PPU) | Siemens | SV | GIS | [9 empty] | 2023-12-25
474 | 2023-12-22 | B224 | Thermax(UB-Pkg9A) | Triveni | US | Gear Box | 2 | 2 | 2023-12-27 | 2023-12-29 | 2023-12-27 | 2023-12-29
475 | 2023-12-28 | B224 | Thermax-EPCC9B | Schneider | SV | Sw Bds | 1 | 1 | 2023-12-29 |  | 2023-12-29 |  |  | 2023-12-30 |  |  |  | TR - virtual
476 | 2023-12-13 | B378 | BHEL | EIC | NV | Control Panel | [9 empty] | 2023-12-13 | 2023-12-28 | B378/487; R)
477 | 2023-12-29 | B224 | Tata Pjts (DCU) | Flowserve | BT | Pumps | 2 | 2 | 2024-01-02 | 2024-01-06 | 2024-01-02 | 2024-01-06 | [5 empty] | Pump Tag : 103-P-113 A/B; INSPECTION DATE : 2nd Jan and 6th Jan 2024
478 | 2023-12-30 | B224 | Megha(PPU) | Burckhardt(FCG) | NV | Control Panel | [9 empty] | 2023-12-30 | 2024-01-12 | ITP R1
| 2024-01-04 | B224 | EIL | YIL | NV | DCS | [6 empty] | 2024-01-12 | 2024-01-12 |  |  |  | FFJB rev & IRN endors.
479 | 2024-01-05 | B224 | L&T(DFCU) | YIL | NV | Analysers | 19 | 19 | 2024-01-09 | 2024-01-10 | 2024-01-09 | 2024-01-10 | 2023-03-05 | 2023-03-05 |  |  |  | AS08-19 analysers
480 | 2024-01-05 | B224 | L&T(DFCU) | Flowserve | AG | Pumps | 1 | 1 | 2024-01-08 | 2024-01-08 | [7 empty] | retest of pump after SQT & seal failure RCA
481 | 2024-01-09 | B224 | Thermax(UB-Pkg9A) | Tmeic | SV | Motors | 3 | 3 | 2024-01-16 | 2024-01-17 | 2024-01-16 | 2024-01-17 | 25-01-2024 & 26-feb-24 | 2024-02-26 | C |  |  | 2x200KW 2P 6.6KV 3x260KW 2P 6.6KV Spares as per PO | 0.5
482 | 2024-01-15 | B224 | L&T(DFCU) | YIL | NV | Analysers | 11 | 11 | 2024-01-22 | 2024-01-23 | [7 empty] | AS-03 FAT
483 | 2024-01-08 | B224 | Tata Pjts (DCU) | Enginemates | US | 114-A-1041 | 1 | 1 | 2024-01-17 | 2024-01-19 | 2024-01-17 | 2024-01-19 | [5 empty] | Tag: 114-A-1041 Main Bundle & Steam Coil MRT
484 | 2024-01-12 | B224 | Technip Energies(MS Block/PFCC) | Godrej | SV | Busducts | 11 | 11 |  |  |  |  | 2024-01-12 | 2024-01-12
485 | 2024-01-09 | B224 | YIL | YIL | NV | DCS(O&U) | 1 | 1 |  |  |  |  | 2024-01-12 |  |  |  |  | Re- inspection of U&O - PDB & Network Cabinets (4 No.s)
486 | 2024-01-08 | B398 | Likita | Birla Cable | NV | OFC | [6 empty] | 2024-01-12 |  |  |  |  | QAP R2
487 | 2023-12-28 | B378 | Coperion | Micon | BT | Valves | 205 | 205 |  |  |  |  | 2024-01-18 | 2024-01-18 |  |  |  | B378/481:TPI Doc.rev.
488 | 2024-01-15 | B224 | L&T(DFCU) | YIL | NV | Analysers | 11 | 11 | 2024-01-17 | 2024-01-19 | 2024-01-17 | 2024-01-19 | 2024-03-14 | 2024-03-14 |  |  |  | pH & Conductivity Analysers
489 | 2024-01-24 | B224 | Megha(Pkg9) | ABB | SV | CRP |  |  | 2024-02-08 | 2024-02-09 | 2024-02-12 | 2024-02-15 | [5 empty] | 66kV CRP FAT | 2
490 | 2024-01-24 | B224 | Megha(Pkg9) | ABB | SV | CRP |  |  | 2024-02-12 | 2024-02-13 | 2024-02-12 | 2024-02-15 | [5 empty] | 66kV CRP & SAS Networking panels (95 nos. of panels ) for both Refinery Block and DFCU Block | 2
491 | 2024-01-24 | B378 | Coperion | ABB | SV | Drives | 7 | 7 | 2024-02-08 | 2024-02-09 | 2024-02-08 | 2024-02-09 | 2024-02-28 | 2024-02-28 |  |  |  | B378/481 s/o | 2
492 | 2024-01-24 | B224 | Technip Energies(MS Block/PFCC) | Micon | US | Valves | 85 | 85 | 2024-01-30 |  | 2024-01-30 | [7 empty] | 1.5
493 | 2024-01-19 | B224 | Mahati Infra | Bharat Bijlee | SV | Motors | [9 empty] | 2024-01-19 | 2024-02-01 | Prop.mixer motor-QAP rev. on 25/1- but mh to take into a/c in Feb'24 | 0.5
494 | 2024-01-25 | B224 | Tata Pjts (DCU) | Flowserve | BT | Pumps | 2 | 2 |  |  |  |  | 2024-02-01 | 2024-02-01 |  |  |  | 101-P-113 A/B- rev/IRN endors sought | 0.5
495 | 2024-02-02 | B224 | L&T(PFCCU) | RSA Turbotech | US | Dry Gas Seal | 1 | 1 | 2024-02-13 | 2024-02-15 | [7 empty] | Elliot Ebara/John Crane-resch to 20,21 & 23
496 | 2024-01-29 | B224 | L&T | KSBMIL | NV | Control Valves | 16 | 16 | 2024-02-07 | 2024-02-07 | 2024-02-07 |  | 2024-02-20 | 2024-02-21 |  |  |  |  | 1.5
497 | 2024-01-31 | B224 | Technip Energies(MS Block/PFCC) | KSBMIL | NV | Control Valves | 50 | 50 | 2024-02-08 | 2024-02-08 | 2024-02-08 |  | 2024-02-21 | 2024-02-21 |  |  |  |  | 1.5
498 | 2024-02-03 | B224 | Megha(Pkg9) | DMW/Tmeic | SV | Motors | [9 empty] | 2024-02-03 | 2024-02-06 | ITP R2 460Kw/6.6kV | 0.5
499 | 2024-01-31 | B378 | BHEL | Triveni | BT | Gear Box | [6 empty] | 2024-02-01 |  |  |  |  | Rev of Run out insp rept as per QAP sl 2.9of GB insptd on 22/23Dec | 0.5
500 | 2024-02-01 | B224 | Megha(LLDPE)/Kirl.Pneu | Rockwell Automation | NV | PLC | [9 empty] | 2024-02-01 | 2024-02-19 | Rev4 for review | 0.5
501 | 2024-01-31 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | Sw Bds | [6 empty] | 2024-01-31 | 2024-01-31 |  |  |  | Rev /End of TPI IRN-3 IRNs -(earlier TPI of Tecnip- TUV Rheinland not accepted) - not considered in Jan'TS | 0.5
502 | 2024-02-05 | B224 | YIL | YIL | NV | DCS | 2 | 2 | 2024-02-12 |  | 2024-02-12 |  | 2024-02-14 | 2024-02-14 |  |  |  | EWS & non DCS PDB | 0.5
503 | 2024-02-02 | B224 | Technip Energies(MS Block/PFCC) | Schneider | SV | SAS Panel | [6 empty] | 2024-02-02 | 2024-02-07 |  |  |  | Rev /End of TPI IRN-3 IRNs -(earlier TPI of Tecnip- TUV Rheinland not accepted) - not considered in Jan'TS | 0.5
504 | 2024-02-07 | B224 | L&T(DFCU) | YIL | NV | Analysers |  |  | 2024-02-15 | 2024-02-16 | 2024-03-25 | 2024-03-26 | [5 empty] | AS-03 Shelter-postponed to wk beginning 26/2 - earlier lot clearance not done | 2
505 | 2024-02-06 | B378 | BHEL | Woodward | NV | ASC | [9 empty] | 2024-02-06 | 2024-02-19 | B378/427:Anti Surge Control System- Woodward India MQP | 0.5
506 | 2024-02-06 | B378 | BHEL | Woodward | NV | ASC | [9 empty] | 2024-02-06 | 2024-02-19 | B378/421:Anti Surge Control System- Woodward India MQP | 0.5
507 | 2024-02-08 | B378 | Coperion | Micon | US | Valves | 10 | 10 | 2024-02-13 |  | 2024-02-13 | [6 empty] | B378/481 | 1
508 | 2024-02-08 | B224 | L&T(PFCCU) | Earth Tekniks P Ltd | NV | Analyser | 4 | 4 | 2024-02-12 | [8 empty] | Water in Lube Analyser
509 | 2024-02-09 | B224 | L&T(PFCCU) | RSA Turbotech | US | Dry Gas Seal | 1 | 1 | 2024-02-20 | 2024-02-23 |  |  | 2024-04-16 | 2024-04-16 |  |  |  | Elliot Ebara/John Crane - visit on 20/2 | 3
510 | 2024-02-14 | B224 | Tata Pjts (DCU) | Enginemates | US | 114-A-1041 | 1 | 1 | 2024-02-16 |  | 2024-02-26 | [6 empty] | Main Bundle (B1, B2) & Steam Coil- Hydro & VDI & call changed to 26/2 | 1
511 | 2024-02-12 | B224 | Megha(Pkg9) | KSB/BHEL | SV | Motors | [9 empty] | 2024-02-12 | 2024-02-12 | ITP Rev3 310Kw/6.6kV | 0.5
512 | 2024-02-12 | B224 | Megha(Pkg9)/KPC | Microfinish | US | Valves | 2 | 2 | 2024-02-19 | 2024-02-20 | 2024-02-26 | 2024-02-27 | 2023-03-21 | 2023-03-21 |  |  |  | postponed to 26,27/2 | 1.5
513 | 2024-02-13 | B224 | L&T(DFCU) | Flowserve | US | Valves | 1 | 1 | 2024-02-21 | 2024-02-24 | 2024-02-21 | [6 empty] | Rpt ord frm L&T | 2
514 | 2024-02-14 | B224 | Megha(PPU) |  | SV | Motors | [9 empty] | 2024-02-14 | 2024-02-19 | from Japan Steel - responded to Megha on 19/2 on the deficiencies observed | 0.5
515 | 2024-02-17 | B224 | Tata Pjts (DCU) | Westcoast Optilinks | NV | FO Cable | [6 empty] | 2024-02-21 | 2024-02-21 |  |  |  | Insptd on 30/31Oct23-based on insp obs, cable re-manufactured & with TPI done on 14/2- EIL reviewed on 21/2 & clrd | 0.5
516 | 2024-02-22 | B378 | BHEL | Forbes Marshall | NV | MMS | [9 empty] | 2024-02-22 | 2024-03-21 | B378/487 s/o | 0.5
517 | 2024-02-22 | B224 | YIL | KEI | NV | Cables | [11 empty] | Rev/IRN of cables
518 | 2024-02-21 | B297 | YIL |  | NV | Analysers | [9 empty] | 2024-02-21 |  | FAT proc comment req frm Instn
519 | 2024-02-24 | B411 | Likita | Birla Cable | NV | OFC | [9 empty] | 2024-02-24 | 2024-03-04
520 | 2024-02-08 | B224 | Megha(PPU) | Tmeic | SV | Motors | 4 | 4 | 2024-02-26 | 2024-02-29 | 2024-02-26 | 2024-02-29 | 2024-03-05 | 2024-03-14 |  |  |  | 460kW,6.6kV HT motors a/c DMW | 5
521 | 2024-02-26 | B224 | L&T(DFCU) | Emerson | NV | Mass Flow Meters | 1 | 1 | 04-mar-24 | 2024-03-05 | 2024-03-05 | [6 empty] | Cal witness@FCRI | 1
522 | 2024-02-26 | B224 | L&T(PFCCU) | YIL | NV | WirelessTx | [6 empty] | 2024-03-02 | 2024-03-21 |  |  |  | TPI Compliance & IRN rev/endors for bal. Wireless supplies | 1
523 | 2024-02-28 | B224 | L&T(PFCCU) | YIL | NV | Analysers | 8 | 8 | 2024-03-14 | 2024-03-15 | 2024-03-27 | 2024-03-28 | [5 empty] | 1TOC+7GCs -after ascertaining readiness of insp | 2
524 | 2024-02-28 | B224 | Thermax | YIL | NV | DCS |  |  | 2024-03-04 | 2024-03-09 | 2024-03-11 | 2024-03-15 |  | 2024-03-29 |  |  |  | After sorting out QAP appl. Issues, FAT called fm 11 to 15 | 4
525 | 2024-02-29 | B224 | YIL |  | NV | DCS |  |  | 2024-03-11 | 2024-03-15 | 2024-03-11 | 2024-03-15 | [5 empty] | MS Block FAT | 4
526 | 2024-02-29 | B224 | Technip Energies(MS Block/PFCC) | Flowserve | BT | Pumps | 2 | 2 | 2024-03-04 |  | 2024-03-04 |  | 2024-03-04 | 2024-03-04 |  |  |  |  | 1
527 | 2024-03-01 | b224 | Thermax | KSBMIL | NV | Control Valves | 7 | 7 | 2024-03-07 | 2024-03-08 | [7 empty] | No of vlvs/int. TCs etc. reqd.;req postponed by Thermax to 11/3 (2 ord - 5 nos in one & 2 nos in other)
528 | 2024-03-02 | B224 | Megha(SRU) | Enginemates/ | SV | Drives | [9 empty] | 2024-03-02 |  | VFDITP Rev3
529 | 2024-03-04 | B297 | YIL |  | NV | Analysers | [6 empty] | 2024-03-04 |  |  |  |  | FAT proc appl | 0.5
530 | 2024-03-04 | B244 | Megha(Pkg9) | Siemens/Triveni | US | Gear Box |  |  | 2024-03-11 | 2024-03-15 | [7 empty] | 3 nos Hi speed Gear Box
531 | 2024-03-06 | B224 | Thermax | Triveni | US | Gear Box | 2 | 2 |  |  |  |  | 2024-03-06 | 2024-03-06 |  |  |  | MRT wit on 27,29/12-now compl.+doc rev & IRN end. | 0.5
532 | 2024-03-05 | B378 | BHEL | Woodward | NV | ASC | [9 empty] | 2024-03-05 | 2024-03-12 | B378/421&427:Anti Surge Control System- Woodward India Revised MQP - 2 QAPs | 1
533 | 2024-03-04 | B224 | Mahati Infra | Bharat Bijlee | SV | Motors | [9 empty] | 2024-03-04 | 2024-03-04 | Prop.mixer motor-QAP rev. on 25/1- but mh to take into a/c in Feb'24 - revised - earlier comments not incorporated | 0.5
534 | 2024-03-05 | B224 | Megha(Pkg9) | ABB | SV | CRP | 95 | 95 |  |  |  |  | 2024-03-05 | 2024-03-05 |  |  |  |  | 0.5
535 | 2024-03-05 | B224 | Megha(Pkg9) | ABB | SV | CRP | 95 | 95 |  |  |  |  | 2024-03-05 | 2024-03-05 |  |  |  |  | 0.5
536 | 2024-03-06 | B224 | Megha(Pkg9) | Siemens/Triveni | BT | Gear Box | 3 | 3 | 2024-03-07 | 2024-03-12 | 2024-03-07 | 2024-03-13 | [5 empty] | 4 days | 4
537 | 2024-03-09 | B224 | YIL |  | NV | Blending Automation | [9 empty] | 2024-02-26 | 2024-03-09 | MFM QAP review | 0.5
538 | 2024-03-08 | B378 | BHEL |  | SV | Motor & VFD | [9 empty] | 2024-03-08 |  | Imported Motor & Drive
539 | 2024-03-08 | B378 | BHEL |  | SV | Motor & VFD | [9 empty] | 2024-03-08 | 2024-03-12 | ONAN T/f, Online T/f Moisture removal system,Num.Relay Panel,LCS & NIFPS for t/f - VFD & LCS QAP appd on 12/3/24 | 1
540 | 2024-03-06 | B224 | Airoil | E&H | NV | Vortex FM | 3 | 3 | 2024-03-18 | 2024-03-20 | 2024-03-18 | 2024-03-20 | [5 empty] | wet cal @ FCRI - failed during testing | 3
541 | 2024-03-13 | B224 | Thermax | Schneider | SV | Sw Bds | 3 | 3 | 2024-03-21 | 2024-03-22 | 2024-03-21 | 2024-03-22 |  | 2024-03-29 |  |  |  |  | 2
542 | 2024-03-13 | B224 | LTHE | Microfinish | US | Valves | 10 | 10 | [9 empty] | LTCS valves-EIL rev/end.on TPI IRN reqd
543 | 2024-03-13 | B378 | BHEL | Danfoss | SV | Drives | [6 empty] | 2024-10-27 | 2024-10-27 |  | 2024-03-13 | 2024-03-15 | BHPV Heater pkg - Motor (ABB) & Drives(Danfoss) QAP | 1
544 | 2024-03-11 | B378 | BHEL | Schneider | NV | [10 empty] | 2024-03-11 | 2024-03-19 | BHPV Soot Blower pkg B378/487- PLC-Schneider - clarifications sought | 0.5
545 | 2024-03-13 | B224 | Tata Pjts (DCU) | Enginemates | US | 114-A-1005(SC+MB) A1 & A2 | 1 | 1 | 2024-03-21 | 2024-03-22 | 2024-03-21 | 2024-03-22 | [5 empty] | Hyd,Dim & Vis
546 | 2024-03-13 | B224 | Tata Pjts (DCU) | Enginemates | US | 114-A-1005(SC) B1,B2,C1,C2,D1&D2 | 1 | 1 | 2024-03-26 | 2024-03-27 | 2024-03-27 | 2024-03-28 | [5 empty] | Hyd,Dim & Vis
547 | 2024-03-14 | B378 | BHEL | ABB | SV | ATS & NumRel Panel | 1 | 1 | 2024-03-28 | 2024-03-28 | 2024-03-28 |  |  | 2024-03-29 |  |  |  |  | 1
548 | 2024-03-14 | B224 | Megha(Pkg10) | Thyssen Krupp / Tmeic |  | Motor | [9 empty] | 2024-03-14 | 2024-03-14 | 400,1450,1750kW (8 nos each) | 0.5
549 | 2024-03-15 | B224 | L&T(DFCU) | YIL | NV | WirelessTx | 1 | 1 | 2024-03-21 | 2024-03-22 | 2024-03-21 | 2024-03-22 | 2024-04-05 | 2024-04-05 |  |  |  |  | 2
550 | 2024-03-13 | B224 | ABB |  | SV | SCADA | 1 | 1 | 2024-03-25 | 2024-03-26 | 2024-03-25 | 2024-03-26 |  | 2024-03-30 |  |  |  | Lot-2 SCADA | 2
551 | 2024-03-19 | B224 | Thermax | Tmeic | SV | Drives | 3 | 3 | 2024-04-01 | 2024-04-03 | 2024-04-01 | 2024-04-03 | [5 empty] | 3000kVA(1);1200kVA(2nos) routine & type | 3
552 | 2024-03-21 | B224 | Thermax | KSBMIL | BT | Control Valves | 20 | 20 | 2024-03-26 | 2024-03-27 | 2024-03-26 | 2024-03-27 | [5 empty] | 19nos in one PO and 44 nos in another
553 | 2024-03-19 | B224 | Thermax | Tmeic | SV | Drives | 3 | 3 | 2024-04-15 | 2024-04-17 | 2024-04-15 | 2024-04-17 | [5 empty] | 3000kVA(1);1200kVA(2nos) routine & type | 3
554 | 2024-03-11 | B224 | Mahati Infra | Bharat Bijlee | SV | Motors | [9 empty] | 2024-03-11 | 2024-03-21 | Rev1 rev. | 0.5
555 | 2024-03-26 | B224 | L&T(DFCU) | E&H | NV | Vortex FM | 3 | 3 | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-09
556 | 2024-03-28 | B224 | Megha(Pkg9) | Siemens/ABB | SV | AVR Panel | [9 empty] | 2024-03-28 |  | Rev1 ITP
557 | 2024-03-31 | B571 | HPE | Nidec | NV | Alternator | 4 | 4 | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2024-04-04
558 | 2024-04-01 | B378 | Coperion | Micon | BT | Valves |  |  | 2024-04-04 | 2024-04-07 | [7 empty] | B378/481
559 | 2024-03-30 | B224 | Megha(Pkg 9) | Sundyne/BHEL | SV | Motor | [9 empty] | 2024-03-30 |  | Rev1
560 | 2024-04-02 | B378 | BHEL | Schneider | NV | [10 empty] | 2024-04-02 | 2024-04-07 | BHPV Soot Blower pkg B378/487- PLC-Schneider - clarifications sought - revised sub
561 | 2024-03-20 | B224 | Megha(Pkg9) | Vee Vee Controls | SV | LA-SC-PT Panel | [9 empty] | 2024-03-20 | 2024-03-20 | Rev2 | 0.5
562 | 2024-04-03 | B224 | Mahati Infra | Bharat Bijlee | SV | Motors | [9 empty] | 2024-04-03 |  | TCs for review as per appd ITP - rev byRPO P?
563 | 2024-04-05 | B224 | Tata Pjts (DCU) | Enginemates | US | 114-A-1006(MB) H1 & H2 | 1 | 1 | 2024-04-10 |  | 2024-04-17 | 2024-04-18 | [5 empty] | Hyd/Vis/Dim (clubbed with earlier calls) | 2
564 | 2024-04-11 | B224 | Thermax | YIL | NV | Analyser | 27 | 27 | 2024-04-18 | 2024-04-19 | 2024-05-06 | 2024-05-07 | 2024-06-26 | 2024-06-26 |  |  |  | SWAS system-insp taken up after resolution of Code R/Code1 comments w.r.t inspn.
565 | 2024-04-10 | B378 | BHEL | ABB | SV | Motor | [9 empty] | 2024-04-10 |  | Heater Pkg
566 | 2024-04-10 | B378 | BHEL | FCG | SV | Local Control Panel | [9 empty] | 2024-04-10 | 2024-04-14 | Heater Pkg - LCS,LCP,JB | 1
567 | 2024-04-12 | B224 | Megha(Pkg9) | Enginemates/Schneider | SV | Drives | [9 empty] | 2024-04-12 | 2024-04-19 | Rev4 ITP commented | 0.5
568 | 2024-04-17 | B224 | L&T(DFCU) | YIL | NV | Analysers | 3 | 3 | 2024-04-25 | 2024-04-26 | 2024-05-07 | 2024-05-08 | 2024-06-03 | 2024-06-03 |  |  |  | postponed based on readiness & L&Ts request | 2
569 | 2024-04-18 | B224 | Megha(Pkg9) | [12 empty] | 2024-04-18 | 2024-05-06 | UPS Rev2 & Batt Rev 0 ITP
570 | 2024-04-05 | B411 | Likita | Birla Cable | NV | OFC | [9 empty] | 2024-04-05 | 2024-04-22 | Rev1 QAP | 0.5
571 | 2024-04-19 | B224 | Megha(LLDPE) | Schenck Process Solns | NV | Solid Additive Pkg System | [9 empty] | 2024-04-19 | 2024-05-09 | Rev3 - 2 sets of QAPs
572 | 2024-04-22 | B448 | Bridge & Roof | Belgaum Aqua | BT | Valves | 70 | 55 | 2024-04-23 | 2024-04-24 | 2024-04-29 | 2024-04-30 | [5 empty] | BPCL Uran-only cryo BV>2" EIL insp
573 | 2024-04-23 | B224 | Megha(sru) | ABB | SV | Motors | [9 empty] | 2024-04-23 | 2024-04-24 | FS s/o- 3QAPs of Motors reviewed on 24/4 | 1
574 | 2024-04-26 | B224 | Megha(Pkg10) | Tmeic | SV | Motors | 10 | 10 | 2024-05-06 | 2024-05-10 | 2024-05-06 | 2024-05-10 | 2006-06-14 | 2024-06-14 |  |  |  | 6.6kV 1750kW -3nos & 450kW -8 nos resld on 14/6
575 | 2024-04-26 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 8 | 8 | 2024-05-02
576 | 2024-04-22 | B224 | Megha (LLDPE) | Japan Steel Works | SV | [10 empty] | 2024-04-22 |  | ITP for Elec Instrument
| 2024-04-22 | B224 | VTV | Microfinish | US | Valves | 35 | 35 | 2024-04-29 | 2024-04-30 | 2024-04-29 | 30-04-2024, 08&09-May-24 | [6 empty] | 2
| 2024-04-30 | B302 | Manasa Ganga Builders & Engrs | KEC Intl | NV | OFC |  |  | 2024-05-03 | 2024-05-04 | 2024-05-03 | 2024-05-04 | 2024-05-08 | 2024-05-08 |  |  |  |  | 2.5
567 | 2024-05-02 | B436 | Delval | Auma | NV | MOV | 33 | 33 | 2024-05-07 | 2024-05-08 | 2024-05-16 | 2024-05-17
568 | 2024-05-06 | B378 | Coperion | ABB | SV | Drives | 8 | 8 | 2024-05-08 | 2024-05-09 | 2024-05-15 | 2024-05-16 | 2024-06-14 | 2024-06-14
569 | 2024-05-03 | B016 | Schneider |  | SV | Sw Bds | [6 empty] | 2024-05-03 | 2024-05-03 |  |  |  | End. Of Man spares | 0.5
570 | 2024-05-06 | B224 | YIL |  | NV | DCS |  |  | 2024-05-09 | 2024-05-14 | 2024-05-09 | 2024-05-14 | 2024-05-22 | 2024-05-22 |  |  |  | POMS Engg stn/FF JBs etc. | 3
571 | 2024-05-08 | B016 | L&T | Hitachi Energy | SV | SAS | [6 empty] | 2024-05-13 | 2024-05-13 |  |  |  | End. Of TPI IRN for SAS
572 | 2024-05-06 | B224 | Thermax | Tmeic | SV | Drives |  |  | 2024-05-11 | 2024-05-11 |  |  | 28-05-2024,11-jun-24 | 2024-06-11 |  |  |  |  | 2
573 | 2024-05-13 | B224 | Tata Pjts (DCU) | Enginemates | US | 114-A-1005(MB) B1 & B2 | 1 | 1 | 2024-05-15 | 2024-05-15 | 2024-05-30 | [6 empty] | Hyd,Vis,Dim
574 | 2024-05-14 | B224 | Megha(LLDPE) | Atlas Copco | SV | Motor | [9 empty] | 2024-05-14
575 | 2024-05-14 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Analysers | 5 | 5 | 2024-05-29 | 2024-05-30 | 2024-06-13 | 2024-06-14 | [5 empty] | ITP comment issues - resch. By YIL due to non availability of shopfloor space from 29/30May to 13/14 jun
576 | 2024-05-15 | B378 | Coperion | Micon | BT | Valves | 204 | 204 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | [5 empty] | S/O of B378/544
577 | 2024-05-15 | B411 | Likita | Birla Cable | NV | OFC | [9 empty] | 2024-05-15 | 2024-05-22 | Rev2 QAP
578 | 2024-04-12 | B224 | YIL |  | NV | Blending Automation | [9 empty] | 2024-04-12 | 2024-05-15 | Thermo couple & OFC cable | 0.5
579 | 2024-05-17 | B224 | Tata Pjts (DCU) | Enginemates | US | 114-A-1005 (MB) C1, C2, D1 & D2 | 1 | 1 | 2024-05-28 |  | 2024-05-31 | [6 empty] | Hyd,Vis,Dim
580 | 2024-05-17 | B378 | BHEL | Forbes Marshall | NV | MMS | [9 empty] | 2024-05-17 | 2024-05-23 | B378/487 s/o (Forbes Marshall/Shinkawa) - MQP & FAT proc Rev1
581 | 2024-05-21 | B224 | Megha(Pkg9) | Siemens | SV | GIS | [9 empty] | 2024-05-21 | 2024-05-24 | Rev0
582 | 2024-05-21 | B224 | Megha(Pkg9) | Siemens | SV | CRP | [9 empty] | 2024-05-21 | 2024-05-24 | RevA
583 | 2024-05-20 | B224 | Megha(Pkg10) | Tmeic | SV | Motors | 13 | 13 | 2024-06-03 | 2024-06-07 | 2024-06-03 | 2024-06-07 | 26-06-2024,10-jul-24 | 2024-07-10 |  |  |  | TKIL s/o on Tmeic - HT Motors | 6
584 | 2024-05-22 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valvestachi | 10 | 10 | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-28 | 2024-06-03 | 2024-06-03 |  |  |  | 10nos in 3 Pos | 0.5
585 | 2024-05-22 | B224 | YIL |  | NV | Mass Flow Meters | 3 | 3 | 2024-05-28 | 2024-05-30 | 2024-05-28 | 2024-05-30 | [5 empty] | Part of Blending Automation- FCRI - Wet Cal.
586 | 2024-05-22 | B224 | YIL | KSBMIL | NV | Control Valves | 15 | 15 | 2024-05-27 | 2024-05-28 | 2024-05-27 | 2024-05-28 | [5 empty] | Part of Blending Automation- FCRI - Wet Cal.
587 | 2024-05-27 | B378 | BHEL | ABB | SV | Motors | [9 empty] | 2024-05-27 | 2024-05-28 | BHEL Vizag S/o
588 | 2024-05-02 | B224 | YIL |  | NV | Mass Flow Meters | [9 empty] | 2024-05-02 | 2024-05-02 | Blending pkg - MFM QAP rev. | 0.5
589 | 2024-05-29 | B016 | L&T | Flowserve | BT | Pumps | 2 | 2 | [7 empty] | 2024-05-29 | 2024-06-13 | Rev & IRN endorsement - 2 IRNs | 1
590 | 2024-05-30 | B571 | HPE | Climaveneta | BT | Chiller |  |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-06 | [5 empty] | earlier inspns done on Insp(Alt-6nos) - 21,22,23/2; Eaton(UPS-24nos)-22-25/2EATON UPS doc rev on 7/3(IFTAS rept for 4 UPS); Nidec -Alternator (3,4/4),NGR-Ohmark Controls (23/4); Chiller: 6,7,10,14,15,20,21/5; NIS & CRP panels insp @ Ohmark & PCE on 28/29th May
591 | 2024-05-31 | B448 | Plantech |  | BT | Stopple Tee & TOR Fitting | [9 empty] | 2024-05-31 | 2024-06-04 | QAP for stopple tee
592 | 2024-06-04 | B224 | Afcons/DMW | Tmeic | SV | Motors | 2 | 2 | 2024-06-19 | 2024-06-20 | 2024-06-18 | 2024-06-19 | 2024-08-21 | 2024-08-21 |  |  |  | 6.6kV/6P | 1
593 | 2024-06-04 | B224 | Megha(PPU) | Schenck Process Solns | NV | Solid Additive Pkg System | [9 empty] | 2024-06-04 | 2024-06-18 | Rev2
594 | 2024-06-09 | B224 | Megha(SRU) | Schneider | SV | Sw Bds | [9 empty] | 2024-06-09 | 2024-06-13 | R0 | 0.5
595 | 2024-06-07 | B224 | L&T(DFCU) | E&H | NV | Vortex FM | 5 | 5 | 2024-06-18 | 2024-06-21 | 2024-06-18 | 2024-06-21 | [5 empty] | FCRI wet cal- rev. on 25/6 | 4
596 | 2024-05-31 | B224 | L&T(DFCU) | YIL | NV | Analysers |  |  | 2024-06-10 | 2024-06-11 | [7 empty] | HCD,TOC - on 13,14th visit also not ready -not offered
597 | 2024-06-03 | B224 | L&T(DFCU) | YIL | NV | Analysers |  |  | 2024-06-05 |  | 2024-06-05 |  | 2024-06-28 | 2024-06-28 |  |  |  | AS03-bal insp
598 | 2024-05-29 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Analysers | 3 | 3 | 2024-06-13 | 2024-06-14 | 2024-06-13 | 2024-06-14 | [5 empty] | Anal shelter 108AS001 & Analyser Cabinet-N2 & Sulphur
599 | 2024-06-03 | B224 | VTV | Microfinish | BT | Valves | 4 | 4 | 2024-06-03 | [8 empty] | 2nd lot ROV
600 | 2024-06-11 | B378 | BHEL | Raychem | SV | T/F | [9 empty] | 2024-06-11 | 2024-06-13 | B378/487 s/o
601 | 2024-06-11 | B224 | Megha | Flowserve | BT | Pumps |  |  | 2024-06-20 | 2024-07-02 | [7 empty] | EPCC06 - 15 pumps (witness insp+rev) | 10
602 | 2024-06-14 | B224 | L&T(DFCU) | KSBMIL | NV | Valves | 1 | 1 | 2024-06-21
603 | 2024-06-14 | B224 |  | YIL | NV | DCS |  |  | 2024-06-24 | 2024-06-28 | 2024-07-08 | 2024-07-12 | [5 empty] | POMS & SRR8 FAT | 3
604 | 2024-06-07 | B448 | Plantech |  | BT | Stopple Tee & TOR Fitting | [9 empty] | 2024-06-07 | 2024-06-17 | QAP for Tee, weldolet and LOR fittings. | 1
605 | 2024-06-12 | B224 | Megha(Pkg09) | Cords Cables | SV | Cables | [9 empty] | 2024-06-12 | 2024-06-17 |  | 0.5
606 | 2024-06-21 | B016 | BHEL | Schneider | SV | Sw Bds | [11 empty] | TPI IRN endors.request
607 | 2024-06-24 | B224 | Megha(Pkg09) | Cords Cables | SV | Cables | [9 empty] | 2024-06-24 | 2024-06-26 | R2-3 QAPs | 0.5
608 | 2024-06-24 |  |  | Schneider | SV | Sw Bds |  |  | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-06-25
609 | 2024-06-24 | B378 | BHEL | BHEL | NV | ASC |  |  | 2024-06-25 | 2024-06-26 | 2024-06-25 | 2024-06-26 | [5 empty] | ASC reinsp.
610 | 2024-06-24 | B224 | Megha(PPU) | Schenck Process Solns | NV | Solid Additive Pkg System | [9 empty] | 2024-06-24 | 2024-07-05 | Rev3-QAP appd after deliberation with HO on sourcing & scope
611 | 2024-06-24 | B224 | Tata Pjts (DCU) | Enginemates | BT | AFC | 4 | 4 | [9 empty] | All Insp Docs for rev./endorsement
612 | 2024-06-24 | B035 | Kalpataru | Micon | BT | Valves | 25 | 25 | 2024-06-24 |  | 2024-07-02 | [6 empty] | reinsp date to be given by KPCL
613 | 2024-06-25 | B224 | L&T(PFCCU) | YIL | NV | Analysers | 8 | 8 | 2024-06-27 | 2024-06-28 | 2024-06-27 | 2024-06-28 | [5 empty] | HCD,TOC - on 13,14th visit also not ready -resch.now. | 2
614 | 2024-06-26 | B398 | KECRPG | Microfinish | BT | Valves |  |  | 2024-07-02 |  | 2024-07-02 |  | 2024-08-20 | 2024-08-20 |  |  |  | Hold due to non avl of 3.2 cert | 1
615 | 2024-06-21 | B571 | HPE | Climaveneta | BT | Chiller |  |  | 2024-06-27 | 2024-06-29 | 2024-06-27 | 2024-06-29 | [5 empty] | earlier inspns done on Insp(Alt-6nos) - 21,22,23/2; Eaton(UPS-24nos)-22-25/2EATON UPS doc rev on 7/3(IFTAS rept for 4 UPS); Nidec -Alternator (3,4/4),NGR-Ohmark Controls (23/4); Chiller: 6,7,10,14,15,20,21/5; NIS & CRP panels insp @ Ohmark & PCE on 28/29th May | 3
616 | 2024-06-28 | B414 | Ruhrpumpen | Tmeic | SV | Drives | [11 empty] | 1440kVA/6.6kV rating drive- 3 nos - presently,T/F insp call given on Raychem Pune
617 | 2024-06-26 | B448 | Bridge & Roof | Belgaum Aqua | BT | Valves | 5 | 5 | 2024-07-03 |  | 2024-07-17 | [6 empty] | BPCL Uran-only cryo BV>2" EIL insp
618 | 2024-07-02 | B224 | Megha | Flowserve | BT | Pumps | 14 | 14 | 2024-07-03 | 2024-07-12 | 2024-07-03 | 2024-07-12 | [5 empty] | EPCC06 - 14 pumps (witness insp+rev) | 8
619 | 2024-07-02 | B224 | L&T(PFCCU) | YIL | NV | WirelessTx | 27 |  | 2024-07-11 |  | 2024-07-16 | 2024-07-17 | 24-09-2024, | 24-09-2024, |  |  |  |  | 2
620 | 2024-07-01 | B224 | Megha(Pkg9) | CGL | SV | LV Motors | [9 empty] | 2024-07-01 | 2024-07-15 | Rev1
621 | 2024-07-02 | B224 | Megha(Pkg6) | ABB | SV | LV Motors | 21 | 21 | 2024-07-08 | 2024-07-12 | 2024-07-08 | 2024-07-12 | 07,26-08-2024 | 2024-08-26 |  |  |  | 75 to 160kW motors - 21nos - 19 nos clrd on 26/8 | 5.5
622 | 2024-06-10 | B224 | Megha(Pkg9) | JSW | SV | Pelletiser Pkg. | [9 empty] | 2024-06-10 | 2024-07-05 | JSW -Pelletiser Motor/VFD/T/f | 1
623 | 2024-07-04 | B224 | L&T(PFCCU) | YIL | NV | Analyser |  |  | 2024-07-08 |  | 2024-07-16 | 2024-07-17 | [5 empty] | Addl items as per PO Amdt - Analyser Shelter & Analysers | 1
624 | 2024-07-08 | B224 | Megha(PPU) | Schenck Process Solns | NV | Solid Additive Pkg System |  |  | 2024-07-12 | 2024-07-15 | 2024-07-18 | 2024-07-19 | 29-jul,01,16-08-2024 | 01,16-08-2024 |  |  |  | clrd cables;16th - Inst panel/vfd/cables | 2
625 | 2024-07-09 | B378 | BHEL | ABB | SV | Drives |  |  | 2024-07-18 | 2024-07-19 | 2024-07-22 | 2024-07-24 | 2024-09-17 |  |  |  |  | B378/458: Combined Testing of VFD & Motor | 3
626 | 2024-07-03 | B224 | VTV | Microfinish | BT | Valves | 29 | 29 | 2024-07-12 |  | 2024-07-18 | [7 empty] | 1
627 | 2024-07-12 | B224 | Tata Pjts (DCU) | YIL | NV | Mass Flow Meters | 6 | 6 |  |  |  |  | 2024-07-12 | 2024-07-12 |  |  |  | after engg. Acceptance of accuracy values | 0.5
628 | 2024-07-16 | B795 |  | Welspun | US | Pipes |  |  | 2024-07-25 | 2024-08-08 | [7 empty] | BPCL Rasayani-Pipe mill deputation - cancelled
629 | 2024-07-17 | B571 | RBIDC | Climaveneta | BT | Chiller |  |  | 2024-07-26 |  | 2024-07-26 | [6 empty] | 4th chiller | 16
630 | 2024-07-17 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Analyser | 17 | 17 | 2024-07-22 | 2024-07-23 | 2024-07-22 | 2024-07-23 | [5 empty] | GC’s/ Moisture/ pH/ Conductivity/ pH/ Conductivity+shelter;SOX-NOX-CO Analyser / SPM Analysers Analyzer | 2
631 | 2024-07-17 | B224 | L&T(DFCU) | YIL | NV | Magnetic Flowmeters | 35 | 35 | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-25 | [5 empty] | Wet Cal @FCRI | 2
632 | 2024-07-24 | B224 | Megha(Pkg9) | TDPS | SV | Generator | 1 | 1 | 2024-08-05 | 2024-08-06 | 2024-08-05 | 2024-08-06 | [5 empty] | Siemens s/o | 2
633 | 2024-07-17 | B224 | Megha(EPCC06) | Flowserve | AG | Pumps | 12 | 12 | 2024-07-22 | 2024-07-27 | [7 empty] | perf. | 5
634 | 2024-07-24 | B471 | Sharp Tanks | Microfinish | US | Valves | 75 | 75 | 2024-07-26 |  | 2024-07-26 | [7 empty] | 2
635 | 2024-07-25 | B378 | Isgec | Triveni | BT | Turbine | 3 | 3 | 2024-07-26 | 2024-08-02 | 2024-07-29 | 2024-08-05 | [5 empty] | Tender B378…-479 on ISGEC - Turb on Triveni-CatA -Casing Hydro | 3
636 | 2024-07-31 | B224 | Megha(Pkg9) | CGL | SV | LV Motors | [9 empty] | 2024-07-31 | 2024-08-01 | Rev2 | 0.5
637 | 2024-08-01 | B378 | Isgec | Triveni | BT | Turbine | 2 | 2 | 2024-08-05 | [8 empty] | Hyd.test | 1
638 | 2024-08-02 | B224 | Megha(PPU) |  | NV | [10 empty] | 2024-08-02 | 2024-08-26 | Buckhardt Comp Inst ICPRev3/4-3 nos ITPs
639 | 2024-08-02 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Analyser |  |  | 2024-08-05 | 2024-08-06 | 2024-08-05 | 2024-08-06
640 | 2024-08-06 | B378 | Isgec | Triveni | BT | Turbine | 2 | 2 | 2024-08-21 | 2024-08-22 | 2024-08-21 | 2024-08-22 | [5 empty] | Dynamic balancing | 2
641 | 2024-08-07 | B224 | L&T(PFCCU) | YIL | NV | Analyser |  |  | 2024-08-08 |  | 2024-08-08 |  | 2024-08-19 | 2024-08-19 |  |  |  | HC detectors | 2
642 | 2024-08-07 | B224 |  | YIL | NV | DCS |  |  | 2024-08-08 |  | 2024-08-08 |  |  | 2024-08-08 |  |  |  |  | 1
643 | 2024-08-07 | B224 | L&T(DFCU) | YIL | NV | WirelessTx |  |  | 2024-08-07 |  | 2024-08-07 | [7 empty] | 1
644 | 2024-08-07 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 2 | 2 | 2024-08-09 |  | 2024-08-09 | [7 empty] | 1
645 | 2024-08-12 | B414 | Ruhrpumpen | Tmeic | SV | Drives |  |  | 2024-08-20 | 2024-08-23 | [8 empty] | 3
646 | 2024-08-19 | B224 | Megha(Pkg9) | Triveni | BT | Gear Box | 1 | 1 | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-23 | [5 empty] | NLMRT+Strip+Doc rev. | 2
647 | 2024-08-17 | B224 | L&T(DFCU) | YIL | NV | Analyser |  |  | 2024-08-27 | 2024-08-28 | 2024-08-28 | 2024-08-29 | [5 empty] | OEM n.a on 29th | 2
648 | 2024-08-21 | B224 | Technip Energies(MS Block/PFCC) | Micon | BT | Valves | 119 | 119 | 2024-08-26 |  | 2024-08-28 | [7 empty] | 1
649 | 2024-08-23 | B224 | Megha(Pkg6) | ABB | SV | LV Motors | 2 | 2 | 2024-08-28 |  | 2024-08-28 |  |  | 2024-09-16 | 2024-09-16 |  |  | A/c FS Pumps - 132kW - reinsp.after failure in Temp Rise test
650 | 2024-08-26 | B224 | Megha(Pkg9) | Triveni | AG | Gear Box | 1 | 1 | 2024-09-04 | 2024-09-05 | 2024-09-04 | 2024-09-05
651 | 2024-08-23 | B795 | Welspun |  | US | Pipes |  |  | 2024-08-27 | 2024-09-13 | 2024-08-27 | 2024-09-13 | [5 empty] | Pipe mill
652 | 2024-08-24 | B224 | Megha(Pkg9) | Southern Lubrication | BT | Lub Oil Sys |  |  | 2024-09-04 | 2024-09-05 | 2024-09-10 | 2024-09-11 | [5 empty] | a/c siemens
653 | 2024-08-24 | B224 | Megha(PPU) | JSW/GE Energy | SV | Motor | [9 empty] | 2024-08-24 | 2024-08-29 | 17500W;6.6kV Motors -2nos ex-pzc
654 | 2024-08-23 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Analyser |  |  | 2024-08-29 |  | 2024-08-29 |  | 2024-09-25 | 2024-09-25 |  |  |  | O2Anal+Chem filter
655 | 2024-08-27 | B224 | Megha(Pkg10) | Schenck Process Solns | SV | Electricals for Low Pr Gravimetric Coal feeder | [9 empty] | 2024-08-27 | 2024-08-29 | VFD for Gravimetric coal feeder | 0.5
656 | 2024-08-29 | B224 | Megha(PPU) | Schenck Process Solns | NV | Solid Additive Pkg System | [9 empty] | 2024-08-29 | 2024-09-18 | Rev4 QAP for Elec. Items
657 | 2024-08-30 | B224 | YIL(DFCU) |  | NV | DCS |  |  | 2024-08-29 | 2024-09-06 | 2024-09-02 | 2024-09-06
658 | 2024-08-29 | B224 | Thermax(Pkg 9) | YIL | NV | DCS |  |  | 2024-08-30 |  | 2024-08-30 | [6 empty] | HWC | 1
659 | 2024-08-30 | B224 | Megha(PPU) | KSB/CGL | SV | Motor | [9 empty] | 2024-08-30 | 2024-08-30 | Rev2 | 0.5
670 | 2024-09-02 | B224 | YIL |  | NV | DCS |  |  | 1934-09-03 |  | 2024-09-03 | [6 empty] | RMCR /PMCR DCS
671 | 2024-09-02 | B436 | E&H | FCRI | NV | Density Meter |  |  | 2024-09-05 | 2024-09-06 | 2024-09-05 | 2024-09-06
672 | 2024-09-02 | B436 | KSBMIL |  | NV | Control Valves |  |  | 2024-09-10 |  | 2024-09-10
673 | 2024-09-02 | B414 | KSBMIL |  | NV | Control Valves |  |  | 2024-09-09 |  | 2024-09-09
674 | 2024-09-03 | B224 | Siemens | TDPS | SV | Generator |  |  | 2024-09-11 | 2024-09-13 | 2024-09-12 | 2024-09-13 | [5 empty] | 11kV 37MW | 2
675 | 2024-09-03 | B224 | Siemens | TDPS | SV | Generator |  |  | 2024-09-16 | 2024-09-18 | 2024-09-16 | 2024-09-18 | [5 empty] | 11kV 48MW | 3
676 | 2024-08-31 | B224 | Megha(Pkg09) |  | SV | Turbine Sup. Panel | [9 empty] | 2024-08-31 | 2024-09-12 | ITP Rev0
677 | 2024-08-30 | B224 | Megha(LLDPE) | Neuman Esser | SV | Elec.&Inst Items | [9 empty] | 2024-08-30 | 2024-09-27 | ITP Rev0 | 0.5
678 | 2024-09-04 | B224 | L&T(DFCU) | YIL | NV | CEMS | 1 | 1 | 2024-09-11 | [8 empty] | CDSU server cabinet of CEMS
679 | 2024-09-05 | B378 | Isgec | Triveni | AG | Steam Turbine | 1 | 1 | 2024-09-13 | 2024-09-13 | [7 empty] | NLMRT with main rotor
680 | 2024-09-05 | B378 | Isgec | Triveni | AG | Steam Turbine | 1 | 1 | 2024-09-18 |  | 2024-09-18 | [6 empty] | NLMRT with spare rotor
681 | 2024-09-05 | B378 | Isgec | Triveni | AG | Steam Turbine | 1 | 1 | 2024-09-19 |  | 2024-09-19 | [6 empty] | Strip/Vis/Dim
682 | 2024-09-06 | B378 | BHEL | BHEL | NV | ASC |  |  | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-20 | [5 empty] | ASC - re-FAT
683 | 2024-09-06 | B414 | Ruhrpumpen | Tmeic | SV | Drives | 1 | 1 | 2024-09-05 | 2024-09-06 | 2024-09-05 | 2024-09-06
684 | 2024-09-06 | B414 | Ruhrpumpen | Tmeic | SV | Drives | 1 | 1 | 2024-09-09 | 2024-09-10 | 2024-09-09 | 2024-09-10
685 | 2024-09-11 | B016 | L&T | ABB | SV | Drives | 1 | 1 | [5 empty] | 2024-09-11 |  |  |  | Rev+IRN endors.
686 | 2024-09-13 | B224 | L&T | YIL | NV | Magnetic Flowmeters | 17 | 17 | 2024-09-19 |  | 2024-09-19 |  |  | 2024-09-29 |  |  |  | Fin. Insp @ YIL
687 | 2024-06-03 | B448 | Plantech |  | BT | Stopple Tee & TOR Fitting | [6 empty] | 2024-09-13 |  |  |  |  | WPS/PQR/WQT for Hot Tapping | 1
688 | 2024-09-11 | B414 | Ruhrpumpen | Tmeic | SV | Drives | 1 | 1 | 2024-09-20 |  | 2024-09-20 | [6 empty] | VFD light load test
689 | 2024-09-17 | B224 | Megha(Pkg10) | Schenck Process Solns | AG & SV | Gravimetric Fuel Feeders | 1 | 1 | 2024-09-26 | 2024-09-27 | 2024-09-30 | [6 empty] | FAT-Mech portion on 30/9
690 | 2024-09-17 | B224 | Megha(Pkg10) | Schenck Process Solns | SV | Gravimetric Fuel Feeders | 1 | 1 | 2024-10-16 | 2024-10-18 | 2024-10-16 | 2024-10-18 | [5 empty] | FAT - PLC+VFD+Thermal MFM
691 | 2024-09-17 | B297 | HVAC Airconditioning Pvt ltd | Schneider | SV | Sw Bds | 2 | 2 | 2024-09-25 | 2024-09-26 | 2024-09-25 | 2024-09-26
692 | 2024-09-17 | B224 | Thermax | YIL | NV | CEMS | 5 | 5 | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-20
693 | 2024-09-16 | B440 | BHEL | Tmeic | SV | VFD | [9 empty] | 2024-09-16
694 | 2024-09-16 | B440 | BHEL | Tmeic | SV | VFD T/f | [9 empty] | 2024-09-16
695 | 2024-08-28 | B224 | Mahati Infra | Fittech Equipments | NV | PLC | [9 empty] | 2024-08-28 | 2024-09-14 | comments given again on 3/10/24
696 | 2024-09-14 | B224 | Megha(Pkg10) | Schenck Process Solns | SV | Electricals for Low Pr Gravimetric Coal feeder | [9 empty] | 2024-09-14 | 2024-09-14 | Rev1
697 | 2024-09-13 | B440 | Tecnicas Reunidas |  | BT | Cast Support Pipes | [7 empty] | 2024-09-13
698 | 2024-09-18 | B224 | Megha(Pkg09) |  | SV | Turbine Sup. Panel | [9 empty] | 2024-09-18 | 2024-10-09 | ITP Rev1
699 | 2024-09-18 | B378 | BHEL | GEA Westfalia | BT | Lub Oil Purifier Skid | 1 | 1 | 2024-10-24 |  | 2024-10-24 | [6 empty] | B378/487 s/o
700 | 2024-09-19 | B378 | BHEL | ABB | SV | VFD | [6 empty] | 2024-09-19 | 2024-09-23 |  |  |  | B378/487 s/o - Spare for VFD,Motor & T/f for 15.88MW Motor - rev. +IRN endors. | 1
701 | 2024-09-19 | B224 | Megha(PPU) | KSB/CGL | SV | Motor | [9 empty] | 2024-09-19 | 2024-09-23 | Rev3
702 | 2024-09-17 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 14 | 14 | 2024-09-26 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2024-10-07 | 2024-10-07 |  |  |  | 14pumps final +2 perf
703 | 2024-09-19 | B378 | Isgec | Triveni | AG | Steam Turbine | 1 | 1 | 2024-09-24 | 30-sep-24 | 2024-09-24 | 30-sep-24 | [5 empty] | NLMRT & strip with main & spare rotor - AG/US/BT-24, BT-27
704 | 2024-09-20 | B440 | Plantech |  | BT | [12 empty] | Rev. of IRN/wps/pqr/wpq
705 | 2024-09-24 | B414 | Ruhrpumpen | Tmeic | SV | Drives | 2 | 2 | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2024-10-04 | [5 empty] | Light load test
706 | 2024-09-24 | B224 | Megha(Pkg9) | Southern Lubrication | US | Lub Oil Sys |  |  | 2024-09-26 |  | 2024-09-27
707 | 2024-09-24 | B519 |  | YIL | NV | Field Insts | 51 | 51 | 2024-09-27 |  | 2024-09-27
708 | 2024-09-24 | B297 |  | YIL | NV | Shelters | 2 | 2 | 2024-09-26 | 2024-09-27 | 2024-09-26 | 2024-09-27 | [5 empty] | B297/158
709 | 2024-09-20 | B224 | L&T(DFCU) | YIL | NV | WirelessTx | 48 | 48 | 2024-09-20 |  | 2024-09-20 |  | 2024-09-24 | 2024-09-24 |  |  |  |  | 1.5
710 | 2024-09-11 | B224 | Airoil | E&H | NV | Vortex FM | 3 | 3 |  |  |  |  | 2024-09-20 |  |  |  |  | Reviewed & Comments on FCRI cal. Reports conveyed. | 1
711 | 2024-09-24 | B224 | L&T(DFCU) | YIL | NV | CDSU pkg | 1 | 1 | 2024-09-26 |  | 2024-09-26
712 | 2024-09-25 | B378 |  | Flowserve | BT | Control Valves | 65 | 65 | 2024-09-25 |  | 2024-09-25 | [6 empty] | IRN relsd on 26/9
713 | 2024-09-11 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Analyser | 15 | 15 | 2024-09-11 |  | 2024-09-11 |  | 2024-09-25 | 2024-09-25 |  |  |  | Anal Shelter+ph/cond,NDIR & SPM anal.
714 | 2024-09-25 | B571 | HPE | Ohmark | SV | NGR | 2 | 2 | 2024-09-26 | 2024-09-27 | 2024-10-01 | 2024-10-03 | [6 empty] | 2
715 | 2024-10-30 | B297 |  | Swims | BT | Valves | 14 | 14 | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2024-10-04 | [5 empty] | B297/168
716 | 2024-10-03 | B436 | E&H | FCRI | NV | Density Meter |  |  | 2024-10-03 | 2024-10-04 | 2024-10-04 | [6 empty] | Calibration witness @ FCRI
717 | 2024-10-03 | B795 | Welspun |  | BT | Pipes |  |  | 2024-10-06 | 2024-10-17 | 2024-10-06 | 2024-10-17 | [5 empty] | Coating insp. - 9 days
718 | 2024-10-03 | B224 | L&T(DFCU) | YIL | NV | Magnetic Flowmeters | 3 | 3 | 2024-10-07 | 2024-10-09 | [7 empty] | Wet Cal @ FCRI
719 | 2024-10-03 | B224 | Megha(LLDPE) | Buckhardt | NV | Control Panel | [9 empty] | 2024-10-03 |  | 2ITPs-Rev2
720 | 2024-10-03 | B224 | Megha(LLDPE) | JSW | SV | Motor | [9 empty] | 2024-10-03 | 2024-10-14 | Rev1 For Tag No.136-P-7012 A/B & 136-P-7312-A/B)
721 | 2024-10-03 | B224 | Thermax | YIL | NV | SWAS | 2 | 2 | 2024-10-14 |  | 2024-10-15 |  | 2024-10-28
722 | 2024-10-01 | B440 | Weir Mineral |  | BT | Hydrocyclone | [9 empty] | 2024-09-20 | 2024-10-01
723 | 2024-10-08 | B224 | Thermax | Microfinish | US | Valves |  |  | 2024-10-15
724 | 2024-10-14 | B224 | Megha(LLDPE) | JSW | SV | Motor | [9 empty] | 2024-10-14 |  | Rev2
725 | 2024-10-09 | B414 | Eratronics | Tejas Networks | VR | Telecom System |  |  | 2024-10-14 | 2024-10-15 | 2024-10-14 | 2024-10-15 | [5 empty] | POC for proposed MPLS-TP model.
726 | 2024-10-05 | B795 |  | Welspun | BT | Pipes |  |  | 2024-10-07 | 2024-10-17 | 2024-10-07 | 2024-10-17
727 | 2024-10-01 | B297 |  | Swims | BT | Valves | 14 | 14 | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2024-10-04 | [5 empty] | B297/188
728 | 2024-10-15 | B440 | Tecnicas Reunidas/TLT | ABB | SV | Motors | 7 | 7 |  |  |  |  | 2024-10-16 | 16-10-2024,13-Nov-24 |  |  |  | Doc rev+TPI IRN end.; Combined testing of ABB motors with CGL VFD doc rev+IRN-13/11
729 | 2024-10-11 | B224 | L&T(DFCU) | YIL | NV | CDSU pkg |  |  | 2024-10-18 |  | 18-0ct-24
730 | 2024-10-04 | B448 | Plantech |  | BT | Stopple Tee & TOR Fitting | [6 empty] | 2024-10-10 | 2024-10-10 |  |  |  | Lot-2 stopple tee
731 | 2024-10-08 | B440 | BHEL | Tmeic | SV | VFD | 1 | 1 | 2024-10-24 | 2024-10-25 | 2024-10-28 | 2024-10-29 | [5 empty] | 2200kVA;6.6kV
732 | 2024-10-07 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 15 | 15 | 2024-10-17 | 2024-10-18 | 2024-10-17 | 2024-10-18 | [5 empty] | Final
733 | 2024-09-30 | B224 | L&T(PFCCU) | YIL | NV | WirelessTx | 27 | 27 |  |  |  |  | 2024-10-07 | 2024-10-07
734 | 2024-10-11 | B378 |  | Belgaum Aqua | US |  | 338 | 338 | 2024-10-22 | 2024-10-24 | 2024-10-22 | 2024-10-24 | [5 empty] | B378/527
735 | 2024-10-11 | B448 | B&R | Belgaum Aqua |  | MOV | 4 | 4 | 2024-10-22 | 2024-10-24 | 2024-10-22 | 2024-10-24
736 | 2024-10-11 | B224 | Thermax | Microfinish |  | Valves | 1 | 1 | 2024-10-22 | 2024-10-24 | 2024-10-22 | 2024-10-24 | 2024-12-05 | 2024-12-05 |  |  |  | 3-way vlv
737 | 2024-10-11 | B297 |  | Microfinish |  | Valves | 11 | 11 | 2024-10-22 | 2024-10-24 | 2024-10-22 | 2024-10-24 | [5 empty] | B297/221
738 | 2024-10-11 | B297 |  | Shivananda | BT | Fittings | 43 | 43 | 2024-10-28 |  | 2024-10-28 | [6 empty] | B297/252
739 | 2024-10-11 | B378 |  | YIL | NV | DCS | 1 | 1 | 2024-10-18 |  | 2024-10-18 | [6 empty] | B378/639 - prototype test
740 | 2024-10-21 | B378 |  | Flowserve | BT | Valves | 2 | 2 | 2024-10-22 |  | 2024-10-22 | [6 empty] | B378/546
741 | 2024-10-19 | B398 | Likita |  | SV | Solar Offgrid system | [9 empty] | 2024-10-19 | 2024-10-21 | 6QAPs-1. Battery chargers. 2. DC-DC Converters. 3. PV Modules. 4. DCDB, AJB, Fuse Box. 5. DC-AC Inverters. 6. Solar Control Chargers.
742 | 2024-10-22 | B378 | Isgec | Triveni | AG | Steam Turbine | 1 | 1 | 2024-10-23 |  | 2024-10-23 | [6 empty] | Final insp.
743 | 2024-10-21 | B378 |  | Flowserve | BT | Valves | 2 | 2 | 2024-10-25 |  | 2024-10-25 | [6 empty] | B378/546 -final
744 | 2024-10-15 | B436 |  | ABB | SV | SCADA | 1 | 1 | 2024-10-24 | 2024-10-25 | 2024-10-24 | 2024-10-25
745 | 2024-10-23 | B414 |  | Tejas Networks | VR | Telecom System | 1 | 1 | 2024-11-06 | 2024-11-07 | 2024-11-06 | 2024-11-07 | [5 empty] | re-PoC +NV
746 | 2024-10-23 | B414 |  | E&H | NV | Density Meter | 2 | 2 | 2024-11-01 | 2024-11-06 |  |  | 2024-12-26 | 2024-12-26 |  |  |  | 2 nos cal @ FCRI
747 | 2024-10-04 | B378 | BHEL | GEA Westfalia | BT | Oil Purification Unit | 1 | 1 | 2024-10-24 |  | 2024-10-24 | [6 empty] | BT & AG
748 | 2024-10-22 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 13 | 13 |  |  |  |  | 2024-10-24 | 2024-10-24
749 | 2024-10-25 | B440 | Tecnicas Reunidas | Neo Structo Construction | BT | Radiant Coils | [6 empty] | 2024-10-29 | 2024-10-29 |  |  |  | Rev. of IRN for Radiant Coils
750 | 2024-10-25 | B224 | Megha(PPU) | Buckhardt | NV | MMS Panel | [9 empty] | 2024-10-25 |  | 3ITPs - Prognost
751 | 2024-10-28 | B285 | Megha | SARK EPC | SV | CP,TR & RTU | [9 empty] | 2024-10-28 | 2024-11-25 | Mongol Refinery: QAP of Cathodic Prot, T/f Rect. & RTU Rev0
752 | 2024-10-30 | B224 | L&T(DFCU) | YIL | NV | Analyser | 27 | 27 | 2024-11-11 | [8 empty] | Moisture Analyser Racks
753 | 2024-10-30 | B378 | Zeeco | Micon | BT | Valves | 11 | 11 | [9 empty] | Zeeco S/o
754 | 2024-11-05 | B440 | BHEL | Tmeic | SV | VFD | 1 | 1 | 2024-11-08 |  | 2024-11-08 |  | 2024-11-18 | 2024-11-18 |  |  |  | 2200kVA;6.6kV - light load test
755 | 2024-10-23 | B414 |  | E&H | NV | Density Meter | 4 | 4 | 2024-11-04 |  | 2024-11-04 |  | 2024-12-26 | 2024-12-26 |  |  |  | Wet cal @ FCRI - B414/34
756 | 2024-10-31 | B378 |  | YIL | NV | DCS |  |  | 2024-11-05 | 2024-11-06 | 2024-11-05 | 2024-11-06 | [5 empty] | B378/639 - Digital Solns. Mtg.
757 | 2024-11-11 | B224 | Megha(SRU) | Flowserve | BT | Pumps | 4 | 4 | 2024-11-13 | 2024-11-14 | 2024-11-14 | 2024-11-15 | 2024-11-28 | 2024-11-28 |  |  |  | 3HED16DS-2 large m/c perf+2 Fin. Insp
758 | 2024-11-09 | B224 | Megha(Pkg10) | Schenck Process Solns | SV | Gravimetric Fuel Feeders | 1 | 1 | 2024-11-14 |  | 2024-11-15 |  | 2024-12-02 | 2024-12-02 |  |  |  | FAT - PLC+VFD+Thermal MFM- compl. Verification
759 | 2024-11-07 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | TOC Analyser |  |  | 2024-11-07 |  | 2024-11-07 |  | 2024-11-10 | 2024-11-10
760 | 2024-11-08 | B224 | Megha(Pkg10) |  | SV | [10 empty] | 2024-11-08 |  | NGR -B224-511-10A-EEL-ITP-VD58-0005
761 | 2024-11-06 | B224 | Megha(LLDPE) | JSW | SV | VFD | [9 empty] | 2024-11-06 | 2024-11-11 | 6.6kV,17.6MW VFD- GE Power Conversion- QAP ITP Rev2
762 | 2024-11-05 | B224 | L&T(DFCU) | YIL | NV | Magnetic Flowmeters | 3 | 3 | 2024-12-03 | 2024-12-05 | [7 empty] | recal. @ FCRI
763 | 2024-11-11 | B224 | Megha(LLDPE) | Schneider | SV | Sw Bds | [9 empty] | 2024-11-11 | 2024-11-13
764 | 2024-11-04 | B414 |  | Microfinish | US | Valves |  |  | 2024-11-13 |  | 2024-11-19 | [6 empty] | B414/21
765 | 2024-11-05 | B378 |  | Flowserve | BT | Valves |  |  | 2024-11-08 |  | 2024-11-08 | [6 empty] | B378/600 -
766 | 2024-11-05 | B269 |  | YIL | NV | DCS | 1 | 1 | 2024-11-25 | 2024-11-30 | [7 empty] | DHDT FAT | 3
767 | 2024-11-07 | B224 |  | YIL | NV | Mass Flow Meters | 10 | 10 |  |  |  |  | 2024-11-13 | 2024-11-13
768 | 2024-11-12 | B224 | Megha(SRU) | Flowserve | BT | Pumps | [9 empty] | 2024-11-12 | 2024-11-13
769 | 2024-11-13 | B224 | Megha | Schneider | SV | Sw Bds | [9 empty] | 2024-11-13 | 2024-11-19 | Req.frm Pjts (only Num. Rel. QAP fwded)
770 | 2024-11-14 | B725 |  | YIL | NV | Temp.Txers | [9 empty] | 2024-11-14 |  | mail frm Sanjeev Kr.
771 | 2024-11-14 | B224 | Megha | RSI Switchgear | SV | NGR | [9 empty] | 2024-11-14 | 2024-11-19
772 | 2024-11-14 | B224 | Megha(LLDPE) | Buckhardt | NV | MMS Panel | [9 empty] | 2024-11-14
773 | 2024-11-18 | B269 | Hyosung | Ohm Energy Mgmt | SV | LCC Panel |  |  | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-21 | 2024-11-27 | 2024-11-27
774 | 2024-11-18 | B378 |  | Dynafluid | US | Flow Nozzle |  |  | 2024-11-20 |  | 2024-11-20 | [6 empty] | B378/410
775 | 2024-11-18 | B302 |  | Belgaum Aqua | US | Valves | 34 | 34 | 2024-11-20 | 2024-11-21 | 2024-11-20 | 2024-11-21 | [5 empty] | B302/63
776 | 2024-11-18 | B414 |  | 2L | US
777 | 2024-11-18 | B378 |  | Schneider | SV | Sw Bds | 6 | 6 | 2024-11-25 | 2024-11-28 | 2024-11-25 | 2024-11-28 | [5 empty] | B378/725
778 | 2024-11-19 | B378 | Isgec | ABB | NV | Analyser | 1 | 1 | 2024-11-25 |  | 2024-11-27 | 2024-12-03 | 2024-12-24 | 2024-12-24 |  |  |  | O2 Anal. | 2
779 | 2024-11-19 | B519 |  | KSBMIL | NV | Control Valves | 20 | 20 | 2024-11-22 |  | 2024-11-22 | [6 empty] | B519/6823
780 | 2024-11-19 | B440 | Tecnicas Reunidas | CGL | SV | VFD | [6 empty] | 2024-11-19 | 2024-11-19
781 | 2024-11-22 | B224 | Afcons | Schneider | SV | Sw Bds | 9 | 9 | 2024-11-25 | 2024-11-28 | 2024-11-25 | 2024-11-28 | 2024-12-19 |  |  |  |  | Mundhra COT
782 | 2024-11-21 | B224 | L&T(DFCU) | YIL | NV | CDSU pkg | 5 | 5 | 2024-11-26 |  | 2024-11-28 |  | 2024-12-24 | 2024-12-24 |  |  |  | Sox/Nox/CO,O2,TDLS,TOC
783 | 2024-11-21 | B548 | Petronet LNG/Emerson | Microfinish | US | Ball Valves | 1 | 1 | 2024-11-25 |  | 2024-11-28 | [6 empty] | 30"BV-
784 | 2024-11-22 | B224 | Megha(Pkg09) |  | SV | NGR | [9 empty] | 2024-11-22 | 2024-11-27 | QAP R1
785 | 2024-11-23 | B224 | Megha(LLDPE) | Schenck Process Solns | SV | PLC | [9 empty] | 2024-11-23 |  | Docs of PLC,VFD,MFM-for rev/TPI IRN endors
786 | 2024-11-21 | B224 | Megha(PPU) | Buckhardt | NV | MMS Panel | [9 empty] | 2024-11-21 |  | 3ITPs-R2 - Prognost
787 | 2024-11-20 | B440 | Tecnicas Reunidas | TLT Engg | BT | FD/ID Fans | [6 empty] | 2024-11-20 | 2024-11-20
788 | 2024-11-25 | B414 |  | IL | NV | Control Valves | 2 | 2 | 2024-11-29 |  | 2024-11-29 |  |  | 2024-12-05 |  |  |  | B414/25
789 | 2024-11-26 | B378 |  | ABB | NV | Analyser | 1 | 1 | 2024-12-02 | 2024-12-03 | 2024-12-02 | 2024-12-03 | [5 empty] | B378/569
790 | 2024-11-26 | B378 |  | ABB | NV | Field Insts | 45 | 45 | 2024-11-27 |  | 2024-11-27 | [6 empty] | B378/677 & 672
791 | 2024-11-26 | B378 |  | BHEL | NV | Governer Control Panel | 1 | 1 | 2024-12-10 | 2024-12-11 | 2024-12-10 | 2024-12-11 | 2024-12-24 | 2024-12-24
792 | 2024-11-27 | B224 | Megha (SRU) | Emerson | NV | Mass Flow Meters | [9 empty] | 2024-11-27 |  | QAP R0
793 | 2024-11-27 | B224 | Megha (SRU) | Emerson | NV | Magnetic Flowmeters | [9 empty] | 2024-11-27 |  | QAP R0
794 | 2024-11-28 | B302 | B&R/IAVL | ABB | SV | EPABX System | 1 | 1 | 2024-11-28 |  | 2024-12-03 | [6 empty] | S/o from B&R/IAVL
795 | 2024-11-27 | B224 | Megha(Pkg09) |  | SV | NGR | [9 empty] | 2024-11-27 | 2024-11-30 | QAP R2 - 2 QAPs
796 | 2024-11-28 | B224 | L&T(DFCU) | YIL | NV | Analysers | 1 | 1 |  |  |  |  | 2024-11-28 | 2024-11-28 |  |  |  | Wobbe Analyser
797 | 2024-11-27 | B297 |  | YIL | NV | Analyser Shelter | 1 | 1 | 2024-11-28 |  | 2024-11-28 | [6 empty] | B297/158-punch pt witness
798 | 2024-11-27 | B224 | Megha (SRU) | Emerson | NV | Magnetic Flowmeters | 3 | 3 | 2024-12-04 | 2024-12-05 | 2024-12-04 | 2024-12-05 | [5 empty] | FCRI witness
799 | 2024-11-29 | B414 |  | E&H | NV | Mass Flow Meters | 6 | 6 | 2024-12-04 | 2024-12-05 | 2024-12-04 | 2024-12-05 | [5 empty] | FCRI witness
800 | 2024-11-29 | B297 |  | YIL | NV | Field Insts | 127 | 127 | 2024-12-06 |  | 2024-12-06 | [6 empty] | B297/194-127 insts
801 | 2024-11-30 | B224 | HRRL(U&O) | YIL | NV | DCS | 1 | 1 | 2014-12-09 | 2024-12-12 | [7 empty] | SRR07 & RMCR FAT
802 | 2024-11-28 | B224 | Megha(PPU) | Sundyne/Hitachi Hirel | SV | VFD | [9 empty] | 2024-11-28
803 | 2024-12-02 | B795 |  | Jindalsaw | BT | Pipes |  |  | 2024-12-04 | 2024-12-12 | 2024-12-04 | 2024-12-12 | [5 empty] | 8 days- coating
804 | 2024-12-03 | B297 |  | YIL | NV | Shelters | 1 | 1 | 2024-12-11 | 2024-12-13 | 2024-12-11 | 2024-12-13 | [5 empty] | B378/160
805 | 2024-12-02 | B767 |  | OLA/ACC | SV | ACC |  |  | 2024-12-11 | 2024-12-13 | 2024-12-11 | 2024-12-13 | [5 empty] | Qtrly visit to OLA & ACC
806 | 2024-12-03 | B224 | Megha(SRU) | RSI Switchgear | SV | NGR | [9 empty] | 2024-12-03 | 2024-12-04 | R0
807 | 2024-12-03 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Analysers | 11 | 11 | 2024-12-11 |  | 2024-12-11 |  | 2025-01-17 | 2025-01-17 |  |  |  | 1108-AS-02;3 GCs+2PAC & 6Moisture Analyser
808 | 2024-12-05 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 6 | 6 | 2024-12-09 |  | 2024-12-09 |  | 13,30-dec-24 |  |  |  |  | last lot
809 | 2024-12-05 | B519 |  | KSBMIL | NV | Control Valves | 2 | 2 | 2024-12-09 |  | 2024-12-09 | [6 empty] | last lot+spares
810 | 2024-12-05 | B224 | Thermax (Pkg 9A) | Microfinish | US | Valves | 1 | 1 |  |  |  |  | 2024-12-05 | 2024-12-05 |  |  |  | insptd. In Oct
811 | 2024-12-05 | B224 | Tata Pjts (DCU) | Enginemates | BT | Air Fin Coolers | [11 empty] | As per appd. ICP,rev & endors. of Completeness of Fin. Docs sought
812 | 2024-12-06 | B414 |  | ABB | SV | SCADA | 1 | 1 | 2024-12-16 | 2024-12-18 | 2024-12-16 | 2024-12-18 | [5 empty] | PO44
813 | 2024-12-06 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 3 | 3 | 2024-12-10 | 2024-12-12 | 2024-12-10 | 2024-12-12 | [5 empty] | 121P0301A/B/C-3WXB-9C
814 | 2024-12-06 | B224 | Megha(PPU) | JSW/GEPC | SV | Drives | [9 empty] | 2024-12-06 |  | Rev02
815 | 2024-12-06 | B224 | Megha(PPU) | RSI Switchgear | SV | NGR | [9 empty] | 2024-12-06 | 2024-12-10 | Rev0
816 | 2024-12-09 | B224 | Afcons | Emerson | NV | Ultrasonic FM | 3 | 3 | 2024-12-20 | 2024-12-24 | [7 empty] | 12"-2nos;24"-2 nos - resch- only 12" on 23,24&26
817 | 2024-12-11 | B398 | Likita |  | NV | LEL Detector | [9 empty] | 2024-12-11 | 2024-12-24 | Fire alarm system & Gas Det. QAPs
818 | 2024-12-11 | B224 | Megha(Pkg 9) |  | SV | Sw Bds | [9 empty] | 2024-12-11 | 2024-12-13 | HT Swbd R0
819 | 2024-12-11 | B378 |  | Belloseal | US | Valves | 151 | 151 | 2024-12-17 | 2024-12-18 | 2024-12-17 | 2024-12-18 | [5 empty] | B378/755
820 | 2024-12-11 | B378 |  | Schneider | SV | Sw Bds | 5 | 5 | 2024-12-23 | 2024-12-24 | 2024-12-23 | 2024-12-24 | 2024-12-31 | 2024-12-31 |  |  |  | B378/725 5Bds with TR test
821 | 2024-12-14 | B224 | Thermax | YIL | NV | CEMS | 1 | 1 |  |  |  |  | 2024-12-14 | 2024-12-14 |  |  |  | Compl.rev+IRN endors.
822 | 2024-12-13 | B440 | Tecnicas Reunidas |  | BT | Exp.Joints & Tube seals | [6 empty] | 2024-12-17 | 2024-12-17 |  |  |  | Rev+endors of IRN
823 | 2024-12-16 | B378 |  | Belgaum Aqua | BT | Valves | 210 | 210 | 2024-12-20 |  | 2024-12-20 | [6 empty] | B378/763
824 | 2024-12-16 | 4994 |  | 2L Engineers | US/BT | Valves |  |  | 2024-12-19 |  | 2024-12-19 | [6 empty] | B414/39
825 | 2024-12-16 | B414 |  | Microfinish |  | Valves | 70 | 70 | 2024-12-20 |  | 2024-12-20 | [6 empty] | PO 39
826 | 2024-12-16 | B548 | Emerson | Microfinish |  | Valves | 1 | 1 | 2024-12-20 |  | 2024-12-20
827 | 2024-12-16 | B224 | L&T(DFCU) | YIL | NV | Magnetic Flowmeters | 19 | 19 | 2024-12-19 |  | 2024-12-19 |  | 2024-12-30 | 2024-12-30 |  |  |  | final insp @ YIL
828 | 2024-12-19 | 7716 |  | Godrej | SV | Busducts | 1 | 1 | 2024-12-26 |  | 2024-12-26 | [6 empty] | For EIB.
829 | 2024-12-20 | B224 | Megha (srU) | Flowserve | AG | Pumps | 46 | 46 |  |  |  |  | 2024-12-20 | 2024-12-20
830 | 2024-12-19 | B224 | Megha(SRU) |  | SV | MOV | [9 empty] | 2024-12-19 | 2024-12-30 | MCT QAP
831 | 2024-12-24 | B378 |  | YIL | NV | DCS | [9 empty] | 2024-12-18 | 2024-12-24 | B378/639 - DCS + MCT QAPs
832 | 2024-12-24 | B269 |  | YIL | NV | DCS | [6 empty] | 2024-12-24 | 2024-12-24 |  |  |  | FF JB TPI IRN
833 | 2024-12-24 | B224 | Megha(PPU) | RSI Switchgear | SV | NGR | [9 empty] | 2024-12-24 | 2024-12-30 | Rev1
834 | 2024-12-24 | B224 | Megha(PPU) | Sundyne/Hitachi Hirel | SV | VFD | [9 empty] | 2024-12-24 | 2024-12-30
835 | 2024-12-24 | B224 | Megha(PPU) | JSW/GEPC | SV | HV VFD | [9 empty] | 2024-12-24 | 2024-12-31 | Rev2
836 | 2024-12-26 | B224 | Megha (srU) | Flowserve | AG | Pumps | 6 | 6 |  |  |  |  | 2024-12-26 | 2024-12-26
837 | 2024-12-30 | B414 |  | E&H | NV | Mass Flow Meters | 4 | 4 | 2025-01-23 | 2025-01-31 | 2025-01-28 | [6 empty] | 414/34 FCRI witness
838 | 2024-12-27 | B414 | Narmada Offshore | Micon | BT | Valves | 10 | 10 | 2024-12-30
839 | 2024-12-27 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 4 | 4 |  |  |  |  | 2024-12-30 | 2024-12-30 |  |  |  | Doc rev+IRN end.
840 | 2024-12-27 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 6 | 6 |  |  |  |  | 2024-12-30 | 2024-12-30 |  |  |  | Doc rev+IRN end.
841 | 2025-01-02 | B269 |  | YIL | NV | DCS |  |  | 2025-01-20 | 2025-01-24 | [7 empty] | VGO FAT
842 | 2025-01-02 | B224 |  | YIL | NV | DCS |  |  | 2025-01-05 | 2025-01-13
843 | 2025-01-03 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 2 | 2 | 2025-01-09 | 2025-01-10 | 2025-01-09 | 2025-01-10
844 | 2025-01-03 | B414 |  | Microfinish | US | Valves | 110 | 110 | 2025-01-09 | 2025-01-10 | 2025-01-09 | 2025-01-10 | [5 empty] | 414/39
845 | 2025-01-03 | B224 | Megha(LLDPE) | KBL/CGISPL | SV | Motors | [9 empty] | 2025-01-03 | 2025-01-08
846 | 2025-01-03 | B224 | Megha(LLDPE) | NOV India | SV | VFD | [9 empty] | 2025-01-03 | 2025-01-08 | Rev2
847 | 2025-01-06 | B448 |  | ABB | SV | Plant Automation system | [9 empty] | 2025-01-06 | 2025-01-08 | DCS/ESD FAT proc.
848 | 2025-01-08 | B302 |  | Shirdi Sai | SV | [12 empty] | online mtg. on 8/1
849 | 2025-01-08 | B224 | Megha(PPU) | Fainger Leslie | BT | Pressure Relief Valves | [9 empty] | 2025-01-08
850 | 2025-01-13 | B795 |  | Esennar Transformer | SV | Transformer | [9 empty] | 2025-01-13
851 | 2025-01-14 | B378 |  | Belgaum Aqua | BT | Valves | 1 | 1 | 2025-01-21 | [8 empty] | B378/823
852 | 2025-01-14 | B229 |  | Belgaum Aqua | BT | Valves | 58 | 58 | 2025-01-21 | [8 empty] | B229/597
853 | 2025-01-14 | B229 |  | Belgaum Aqua | BT | Valves | 110 | 39 | 2025-01-21 | [8 empty] | B229/594
854 | 2025-01-14 | B378 |  | Schneider | SV | Sw Bds | 6 | 6 | 2025-01-22 | 2025-01-24 | 2025-01-22 | 2025-01-24 | [5 empty] | B378/725
855 | 2025-01-14 | B378 |  | Schneider | SV | Sw Bds |  |  | 2025-01-27 | [8 empty] | B378/725
856 | 2025-01-14 | B224 | NPB Pkg | Schneider | SV | Sw Bds | 5 | 5 | 2025-01-20 | 2025-01-22 | 2025-01-22 | 2025-01-24 | 2025-01-30 | 2025-01-30 |  |  |  | Pjts clarified our scope is only rev & end. Of TPI IRN
857 | 2025-01-13 | B224 | Chemtrols | KSBMIL | NV | Control Valves | 15 | 15 | [9 empty] | Request for S/O expediting from RPOM
858 | 2025-01-20 | B269 |  | YIL | NV | DCS | 1 | 1 | 2025-01-23 | 2025-01-30 |  |  | 2025-03-01 | 2025-03-01 |  |  |  | VGO FAT
859 | 2025-01-20 | B378 |  | Micon | US | Valves | 260 | 260 | 2025-01-22 | 2025-01-23 | 2025-01-28 | 2025-01-29 | [5 empty] | B378/765
860 | 2025-01-20 | B378 |  | Micon | US | Valves | 19 | 19 | 2025-01-22 | 2025-01-23 | 2025-01-28 | 2025-01-29 | [5 empty] | B378/807
861 | 2025-01-21 | B378 |  | Spraying India | BT | Injection Quill |  |  | 2025-01-23 |  | 2025-01-23 | [6 empty] | B378/741 - Hydro/PMI/TC & RT film rev.
862 | 2025-01-21 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | Moisture Analyser |  |  | 2025-01-28
863 | 2025-01-21 | B224 | Mahati Infra | Suyog Electricals | NV | Signal Cables | [9 empty] | 2025-01-21 | 2025-01-24
864 | 2025-01-22 | B224 | Megha(SRU) | Hitachi Energy | SV | Capacitor Package | [9 empty] | 2025-01-22 | 2025-01-23
865 | 2025-01-23 | B224 | Megha(SRU) | Hitachi Hirel | SV | UPS | [9 empty] | 2025-01-23 | 2025-02-12 | UPS & Batteries - 3 QAPs
866 | 2025-01-27 | B448 | B&R | Belgaum Aqua | US | Valves | 1 | 1 | 2025-01-29 | [8 empty] | 20" 300# Cryogenic Ball Valve (Top Entry) - not offered as not ready
867 | 2025-01-27 | B378 |  | Spraying India | BT | Injection Quill |  |  | 2025-01-28 |  | 2025-01-30 | [6 empty] | B378/741 - fin. Insp.
868 | 2025-01-29 | B224 | Megha(SRU) | Flowserve | BT | Pumps | 3 | 3 | 2025-01-29 |  | 2025-01-29 |  | 2025-01-30 | 2025-01-30 |  |  |  | Fin. Insp
869 | 2025-01-27 | B414 |  | E&H | NV | Turbine Flow Meters | 2 | 2 | 2025-01-23 | 2025-01-31 | 2025-01-28 | [6 empty] | 414/34 FCRI witness - 8"600 & 4"150
870 | 2025-01-24 | B378 | Paramount | Control & Schematics | SV | MV Sw Bds | 1 | 1 | 2025-01-30 | 2025-02-01 | [7 empty] | MCC
871 | 2025-01-24 | B224 | L&T(DFCU) | YIL | NV | Analyser | 1 | 1 | 2025-01-28 | [8 empty] | GC - insp of Heat tracer tube/sample probes
872 | 2025-01-24 | B359 | Corrtech | Ramtek Electronics | SV | DC-DC Converter | 18 | 18 | 2025-01-20 |  | 2025-01-29 |  | 2025-03-04 | 2025-03-04 |  |  |  | DC-DC conv for Solar PV system
873 | 2025-01-23 | B378 | Siemens | Schneider | SV | Sw Bds | 2 | 2 | [9 empty] | Expediting Siemens S/o based on specific request
874 | 2025-01-23 | B378 |  | Belgaum Aqua | US | Valves | 1 | 1 | 2025-01-29 |  | 2025-01-29 | [6 empty] | B378/823
875 | 2025-01-30 | B058 | FLSmidth | Yaskawa | SV | VFD | 9 | 9 | 2025-02-03 | 2025-02-07 | 2025-02-05 | 2025-02-06 | [5 empty] | 37,45 & 75kW
876 | 2025-01-30 | B224 | Megha(LLDPE) | Buckhardt | NV | MMS Panel | [9 empty] | 2025-01-30 | 2025-02-09 | ITP R1 - 2 nos
877 | 2025-01-29 | B448 |  | ABB | SV | Plant Automation system | [9 empty] | 2025-01-29 | 2025-01-31 | Telecom Sys QAP
878 | 2025-02-05 | B269 |  | YIL | NV | DCS | [6 empty] | 2025-02-05 | 2025-02-05 |  |  |  | Rev & IRN end. Of FF JBs
879 | 2025-02-04 | B725 |  | YIL | NV | Temp.Txers | [9 empty] | 2025-02-04 | 2025-02-04 | PO B725/22
880 | 2025-01-29 | B414 |  | E&H | NV | Turbine Flow Meters | 2 | 2 | 2025-01-30 | 2025-02-05 | 2025-02-05 | [6 empty] | 414/34 FCRI witness - 8"600
881 | 2025-02-05 | B269 |  | YIL | NV | DCS | [6 empty] | 2025-02-05 | 2025-02-05 |  |  |  | Rev of OFC Cables TPI docs
882 | 2024-11-27 | B224 | Megha (SRU) | Emerson | NV | Mass Flow Meters | [9 empty] | 2024-11-27 | 2025-02-06 | QAP R0
883 | 2024-11-27 | B224 | Megha (SRU) | Emerson | NV | Magnetic Flowmeters | [9 empty] | 2024-11-27 | 2025-02-06 | QAP R0
884 | 2025-02-07 | B414 | Pace Process Controls |  | NV | FLP Lights/Transmitters/GDs | [9 empty] | 2025-02-06 |  | 5 ITPs against EIL Tender LOA No. KHPL/E&I/ SM/B414-000-EJ-T-0901/47 Date: 27.11.2024 (E&I works for KHPL valued at 641900000)
885 | 2025-02-06 | B448 | B&R | Belgaum Aqua | US | Valves | 20 | 20 | 2025-02-07 |  | 2025-02-18 |  | 2025-02-18 | 2025-02-18 |  |  |  | 20" 300# Cryogenic Ball Valve (Top Entry)+19nos rev./endors
886 | 2025-02-10 | B224 | Megha(SRU) | KSBMIL | US | Control Valves | [9 empty] | 2025-02-10
887 | 2025-02-09 | B224 | L&T(PFCCU) | YIL | NV | DCS | [6 empty] | 2025-02-09 | 2025-02-09 |  |  |  | IRN endors. Of loose items
888 | 2025-02-09 | B224 | Technip Energies(MS Block/PFCC) | YIL | NV | DCS | [6 empty] | 2025-02-09 | 2025-02-09 |  |  |  | IRN endors. Of Moist. Anal.
889 | 2025-02-11 | B378 |  | Schneider | SV | Sw Bds | 7 | 7 | 2025-02-17 | 2025-02-20 | 2025-02-17 | 2025-02-20 | [5 empty] | B378/725
890 | 2025-02-16 | B229 |  | Belloseal | US | Valves |  |  | 2025-02-19 |  | 2025-02-19 | [6 empty] | Mtg. with Pjts to expedite supply
891 | 2025-02-15 | B224 | L&T(DFCU) | YIL | NV | Analysers | 3 | 3 | 2025-02-20 |  | 2025-02-20 |  | 2025-03-03 |  |  |  |  | 3 Methane Analysers (Servomax)+O2 Analysers(ABB)
892 | 2025-02-14 | B224 | Megha(PPU) | Sundyne/Hitachi Hirel | SV | VFD | [9 empty] | 2025-02-14 | 2025-02-18 | Rev2 QAP
893 | 2025-02-17 | B224 | Vijay Tanks(DWST pkg) | Schneider | SV | Sw Bds | 1 | 1 | 2025-02-20 |  | 2025-02-20 |  | 2025-02-27 | 2025-03-03
894 | 2025-02-11 | B224 | Thermax | YIL | NV | DCS | [6 empty] | 2025-02-18 |  |  |  |  | DCS-2nd lot - rev. of TPI IRNs
895 | 2025-02-14 | B224 |  | ABB | SV | DCS | [6 empty] | 2025-02-18 |  |  |  |  | Rev/IRN end of man spares
896 | 2025-02-19 | B224 | Afcons | Godrej | SV | Busducts | 4 | 4 | 2025-02-27 | 2025-02-28 | 2025-02-27 | 2025-02-28 | [5 empty] | Mundhra COT - 4000A,433V sandwich BD
897 | 2025-02-17 | B378 |  | YIL | NV | DCS |  |  | 2025-02-20 | 2025-02-28 | 2025-02-20 | 2025-02-28 | [5 empty] | B378/631-U&O FAT
898 | 2025-02-20 | B297 |  | Flowserve | BT | Control Valves | 12 | 12 | 2025-02-21 |  | 2025-02-21 | [6 empty] | B297/188
899 | 2025-02-20 | B378 | Isgec | KSBMIL | BT | Control Valves | 20 | 20 | 2025-02-27 |  | 2025-02-27
900 | 2025-02-24 | B378 |  | ABB | NV | Field Insts | 37 | 37 | 2025-02-24 |  | 2025-02-24 | [6 empty] | PO677
901 | 2025-02-25 | B224 | Thermax | Schneider | SV | Sw Bds | 17 | 17 | 2025-03-05 |  |  |  | 2025-03-12 | 2025-03-12 |  |  |  | Insp of spares
902 | 2025-02-27 | B224 | Megha(SRU) | Flowserve | AG | Pumps | 30 | 30 |  |  |  |  | 2025-02-27 | 2025-02-27 |  |  |  | TPI fin. Insp on 18,19/2/25
903 | 2025-03-01 | B414 |  | Microfinish | US | Valves | 29 | 29 | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-06 | [5 empty] | B414/39-
904 | 2025-03-01 | B378 |  | Microfinish | US | Valves | 39 | 39 | 2025-03-06 | 2025-03-07 | 2025-03-06 | 2025-03-07 | [5 empty] | B378/611
905 | 2025-02-28 | B224 | Megha(LLDPE) | Buckhardt/Kaysons | SV | Local Control Panel | [9 empty] | 2025-02-28 | 2025-03-03 | Rev4
906 | 2025-02-28 | B224 | Megha(SRU) | United Electric | SV | Busducts | [9 empty] | 2025-02-28 |  | Rev0
907 | 2025-03-03 | B414 |  | Schneider | SV | Sw Bds | [6 empty] | 2025-03-03 |  |  |  |  | Rev.mtg. with BPCL & Sch. For ord. stat. rev.
908 | 2025-03-03 | B767 |  | OLA/ACC | SV | ACC |  |  | 2025-03-05 | 2025-03-06 | 2025-03-05 | 2025-03-06
909 | 2025-03-05 | B224 | Megha(LLDPE) | United Electric | SV | Busducts | [9 empty] | 2025-03-05 | 2025-03-06 | Rev0
910 | 2025-03-06 | B224 | L&T(DFCU) | YIL | NV | Analyser | 2 | 2 | 2025-03-12 |  | 2025-03-12 | [6 empty] | GC+Moist. Anal
911 | 2025-03-07 | B224 | Megha(SRU) | Sherman | NV | Mass Flow Meters | [9 empty] | 2025-03-07 | 2025-03-27 | Rev0
912 | 2025-03-07 | B378 |  | YIL | NV | DCS | [9 empty] | 2025-03-04 | 2025-03-07 | Rev of QAP for FF JBs
913 | 2025-03-10 | B224 | Afcons | Emerson | NV | Ultrasonic FM | 3 | 3 | 2025-03-13 | 2025-03-21 | [7 empty] | 12"-1no;24"-1 no - 20"-1no (2 days each)
914 | 2025-03-10 | B795 |  | Esennar Transformer | SV | Transformer | [9 empty] | 2025-02-10 | 2025-03-10 | QAP appl.
915 | 2025-03-11 | B378 |  | YIL | NV | DCS | [9 empty] | 2025-03-11 | 2025-03-12 | FFJB QAP appl
916 | 2025-03-11 | B302 |  | YIL | NV | Turnkey Instn | [11 empty] | Mtg.with YIL- VR &NV on Kom for Turnkey Instn job
917 | 2025-03-13 | B224 |  | YIL | NV | DCS | [6 empty] | 2025-03-13 | 2025-03-13 |  |  |  | IRN end. For SSR7, POMS, RMCR, PMCR
918 | 2025-03-13 | B448 |  | ABB | SV | Plant Automation system |  |  | 2025-03-24 | 2025-03-25 | [7 empty] | ESD pkg.
919 | 2025-03-13 | B448 | Kalpataru | Schneider | SV | Sw Bds
920 | 2025-03-17 | B414 | Pace Process Controls | Universal Cables | SV | Capacitor Package | [9 empty] | 2025-03-14 | 2025-03-21 | Capac. Bank,series reactor & APFC panel
921 | 2025-03-13 | B224 | Megha(PPU) | CGL | SV | Motor | [9 empty] | 2025-03-13 | 2025-03-14
922 | 2025-03-11 | B378 | Siemens | Schneider | SV | Sw Bds | 2 | 2 | 2025-03-27 |  | 2025-03-27 |  | 2025-04-04 | 2025-04-04
923 | 2025-03-14 | B448 | Kalpataru | Schneider | SV | Sw Bds | 3 | 3 | 2025-03-26 | 2025-03-27 | 2025-03-26 | 2025-03-27 | 2025-04-08 | 2025-04-08 |  |  |  | 2 units other than PCC released- PCC not ready/offered | 2
924 | 2025-03-05 | B414 | Pace Process Controls | [12 empty] | 2025-03-05 | 2025-03-13 | QAP for GDs,Field Insts & Lighting Fixtures
925 | 2025-03-18 | 8590 | EIL/Godrej & Boyce | Climaveneta | BT | Heat Pumps | 2 | 2 | 2025-03-21 |  | 2025-03-21
926 | 2025-03-18 | B448 |  | ABB | SV | Plant Automation system | [9 empty] | 2025-03-18 | 2025-03-18 | APPS FAT proc. Rev.
927 | 2025-03-18 | B269 |  | YIL | NV | DCS | [9 empty] | 2025-03-17 | 2025-03-18 | FFJB QAP
928 | 2025-03-18 | B378 |  | Schneider | SV | Sw Bds |  |  | 2025-03-24 | 2025-03-26 | 2025-03-24 | 2025-03-26 | [5 empty] | B378/725-SAS panels
929 | 2025-03-18 | B414 |  | Schneider | SV | Sw Bds | 3 | 3 | 2025-03-24 | 2025-03-26 | 2025-03-24 | 2025-03-26 | [5 empty] | B414/55
930 | 2025-03-18 | B224 |  | Schneider | SV | Sw Bds | 21 | 21 |  |  |  |  | 2025-03-19 | 2025-03-19 |  |  |  | Rev & Endorsement of TPI IRNs- Lot3
931 | 2025-03-24 | B224 | Megha(Pkg09) | Triveni | BT | Gear Box | 1 | 1 |  |  |  |  | 2025-03-24 | 2025-03-24 |  |  |  | Rev & Endorsement of TPI IRN
932 | 2025-03-22 | B224 | Megha(SRU) | Anderson Crosby | US | PSV | [9 empty] | 2025-03-22 | 2025-03-25
933 | 2025-03-19 | B224 | Megha(Pkg09) | TDPS | SV | Alternators | 3 | 3 |  |  |  |  | 2025-03-22 | 2025-03-22 |  |  |  | Rev & IRN endorsement
934 | 2025-03-19 | B440 |  | KSBMIL | NV | Control Valves | 2 | 2 |  |  |  |  | 2025-03-20 | 2025-03-20 |  |  |  | Rev & IRN endorsement - 4 IRNs
935 | 2025-03-26 | B378 |  | YIL | NV | DCS | [6 empty] | 2025-03-26 | 2025-03-26 |  |  |  | Rev&IRN endorsement of FFJBs
936 | 2025-03-25 | B224 | Megha(PPU) | Flowmore/CGL | SV | Motors | [9 empty] | 2025-03-24 | 2025-03-25 | Rev.03 ITP appl
937 | 2025-04-02 | B224 | L&T(DFCU) | YIL | NV | Analysers | 5 | 5 | 2025-04-07 |  | 2025-04-07 | [6 empty] | Inlet pump skids
938 | 2025-04-02 | B224 | Megha(PPU) | Schneider | SV | Sw Bds | [9 empty] | 2025-04-02 | 2025-04-02 | 6.6kV Sw.Gear
939 | 2025-04-02 | B224 | Afcons | Emerson | NV | Ultrasonic FM | [6 empty] | 2025-04-02 |  |  |  |  | Compl. Rev.
940 | 2025-03-26 | B224 | Megha(SRU) | E&H | NV | Servo Level Inst | [9 empty] | 2025-03-26 | 2025-03-29 | servo level txer with accessories
941 | 2025-03-27 | B224 | L&T(DFCU) | YIL | NV | Analysers | [7 empty] | 2025-03-27 |  |  |  | GCs-Compl.rev & IRN endors.
942 | 2025-03-27 | B448 | ABB | Emerson | NV | Mass Flow Meters | [7 empty] | 2025-03-27
943 | 2025-03-27 | B224 | Thermax | YIL | NV | CEMS |  |  | 2025-03-24 | 2025-03-24 |  |  |  | 2025-03-27 |  |  |  | CEMS N/w Cab & spares
944 | 2025-03-26 | B348 |  | YIL | NV | DCS | [9 empty] | 2025-03-26 |  | B348/164
945 | 2025-03-21 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | [7 empty] | 2025-03-25
946 | 2025-04-04 | B297 |  | Belgaum Aqua | BT | Valves | 2 | 2 | 2025-04-04 |  | 2025-04-04 | [6 empty] | B297/301
947 | 2025-04-08 | B440 | Technicas Reunidas | Neo Structo Construction | BT | Convection Modules of DCU Heater | [11 empty] | Req. for doc & IRN endors.
948 | 2025-04-07 | B653 |  | Universal Insts | VR/SV | Battery Charger & Batteries | [6 empty] | 2025-04-07 |  |  |  |  | Rev. mtg & Show Cause Notice issue reco. -8h
949 | 2025-04-07 | 7716 | Climaveneta | Godrej | BT | Heat Pumps | [11 empty] | VC o 7/4- 4hrs
950 | 2025-04-10 | B378 |  | ABB | VR/NV | Field Insts | [6 empty] | 2025-04-10 |  |  |  |  | mtg @ Off with team ABB - B378,B269 rev - 8h
951 | 2025-04-10 | B448 | ABB | Microfinish | US | ON-OFF valves | [9 empty] | 2025-04-10
952 | 2025-04-10 | B224 | Megha(LLDPE) | KSBMIL | NV | Control Valves | [9 empty] | 2025-04-10 | 2025-04-11 | KSB MIL QAP Appl -11/4-0.5d
953 | 2025-04-10 | B725 |  | Flowserve | BT | Pumps | [6 empty] | 2025-04-10 |  |  |  |  | Rev. of Test reports - 4h
954 | 2025-04-11 | B378 |  | YIL | NV | Analysers | 1 | 1 | 2025-04-11 |  | 2025-04-11 | [6 empty] | B378/706-TDLS
955 | 2025-04-11 | B269 |  | YIL | NV | Shelters | 1 | 1 | 2025-04-11 |  | 2025-04-11 | [6 empty] | YIL -B269/1408 -11/4(1d)
956 | 2025-04-14 | B224 | Megha(Pkg09) | Vertiv | SV | ACDB | [9 empty] | 2025-04-14 | 2025-04-15 | Vertiv -ACDBs with Static switch - QAP appl - 4h
957 | 2025-04-14 | B440 |  | KSBMIL | NV | Control Valves | [6 empty] | 2025-04-14 | 2025-04-14 |  |  |  | PO131-rev/end of TPI recds - 4h | 0.5
958 | 2025-02-27 | B414 | Pace Process Controls | E&H | NV | Radar Level Insts | [9 empty] | 2025-02-27 | 2025-04-14 | 2QAPs - 4h
959 | 2025-03-21 | B414 | Pace Process Controls | Cords Cables | NV | Signal Cables | [9 empty] | 2025-03-21 | 2025-04-14
960 | 2025-04-11 | B414 | Pace Process Controls | Bliss Anand | NV | Pressure Relief Valves | [9 empty] | 2025-04-11 | 2025-04-12 | 2 QAPs - 4h
961 | 2025-04-15 | B448 | Kalpataru | Schneider | SV | Sw Bds | 4 | 4 | 2025-04-22 | 2025-04-25 | 2025-04-22 | 2025-04-25 | [5 empty] | 4 PMCCs | 4
962 | 2025-04-15 | B378 |  | Schneider | SV | Sw Bds | 10 | 10 | 2025-04-22 | 2025-04-25 | 2025-04-22 | 2025-04-25 | 2025-05-01 | 2025-05-01 |  |  |  | B378/725 -MCC & LDB -Compl. Rev. & IRN endorsement- 1/5/25 -4h | 0.5
963 | 2025-04-15 | B414 |  | Schneider | SV | Sw Bds | 6 | 6 | 2025-04-22 | 2025-04-25 | 2025-04-22 | 2025-04-25 | 2025-05-01 | 2025-05-01 |  |  |  | B414/55 - 22-25 (4d);Compl. Rev. & IRN endorsement- 1/5/25 -4h | 0.5
964 | 2025-04-15 | B224 | Megha(SRU) | Koso | US | Valves | [9 empty] | 2025-04-15 | 2025-04-17 | 4hrs | 0.5
965 | 2025-04-15 | B224 | Megha(SRU) | ICE Asia | NV | Optical Pyrometer | [9 empty] | 2025-04-15 | 2025-06-12 |  | 0.5
966 | 2025-04-16 | 4994 |  | SBEE Cables | VR/SV | Cables | [11 empty] | Enl. Survey-16h | 2
967 | 2025-04-16 | 4994 |  | Weir Minerals | AG/US | Cyclone | [11 empty] | visit to get potential supplier on board - 8h | 1
968 | 2025-04-25 | 4994 |  | Fluidyne | AG/US | Expansion Bellows | [11 empty] | Enl Survey-16h | 2
969 | 2025-04-29 | 4994 |  | 2L Engineers | AG/US | Valves | [11 empty] | Enh.Survey-16h | 2
970 | 2025-04-19 | B224 | Megha(PPU) | JSW | SV | Motor & VSD | [6 empty] | 2025-04-21 | 2025-04-28 |  |  |  | Motor- ABB Finland, VSD- Hitachi,Korea; TPI doc. Rev. - 4hrs on 21 & 4h on 28/4 | 1
971 | 2025-04-18 | B414 | Pace Process Controls | Cords Cables | NV | Signal Cables | [9 empty] | 2025-04-18 | 2025-04-28 | Rev1 -4h | 0.5
972 | 2025-04-23 | B378 |  | ABB | NV | Shelters |  |  | 2025-04-23 | 2025-04-25 | 2025-04-23 | 2025-04-25 | [5 empty] | B378/569 - 23to25/4 (3d) | 3
973 | 2025-04-24 | B378 |  | Microfinish | US | Valves |  |  | 2025-04-30 |  | 2025-04-30 | [6 empty] | B378/611 | 1
974 | 2025-04-25 | B378 |  | Kequip Global | VR | Lab Equipments | [11 empty] | Mtg. on 28/4/25 - 8h | 1
975 | 2025-04-17 | 7716 | Godrej | Climaveneta | BT | Heat Pumps | [6 empty] | 2025-04-17 |  |  |  |  | Godrej/Climaveneta -Compliance review on 15 & 17/4 - 8h | 1
976 | 2025-04-25 | B224 | Megha(Pkg 09) | Vertiv | SV | UPS | [9 empty] | 2025-04-28 | 2025-04-28 | Vertiv ACDB QAP (0.5d) | 0.5
977 | 2025-04-29 | 4994 |  | Godrej | SV | Busducts | [11 empty] | Survey visit-8h | 1
978 | 2025-04-29 | 4994 |  | ABB | SV | Drives | [11 empty] | 30/4 -Survey visit-8h | 1
979 | 2025-04-28 | B378 | Paramount | Control & Schematics | NV | Sw Bds |  |  | 2025-05-06 |  | 2025-05-06 | [6 empty] | TR test @ CPRI | 1
980 | 2025-04-24 | B448 | ABB | Barco | NV | LVS | [9 empty] | 2025-04-24 | 2025-04-28 | ABB-QAP appl - 28/4(0.5d) | 0.5
981 | 2025-04-24 | B414 | Pace Process Controls | E&H | NV | Radar Level Insts | [9 empty] | 2025-04-24 | 2025-04-28 | Rev0-2QAPs | 1
982 | 2025-04-28 | B414 | Pace Process Controls | Thermal Instrument | NV | RTD | [9 empty] | 2025-04-28 | 2025-06-12 | 2 QAPS | 0.5
983 | 2025-04-17 | B414 | Pace Process Controls | Bliss Anand | NV | Pressure Relief Valves | [9 empty] | 2025-04-17 | 2025-04-28 | 2QAPs-Rev1 - 4hrs | 0.5
984 | 2025-04-21 | B269 |  | YIL | NV | DCS | 1 | 1 | 2025-04-21 | 2025-05-02 | 2025-04-28 | 2025-05-02 | [5 empty] | RHCU FAT- 5d (28/4-2/5) | 5
985 | 2025-04-29 | B560 |  | Microfinish | US | Valves | [6 empty] | 2025-04-30 |  |  |  |  | Rev. mtg along with Client on 30/4-8h | 1
986 | 2025-04-22 | B269 |  | YIL | NV | DCS | [6 empty] | 2025-04-26 | 2025-04-26 |  |  |  | Rev & IRN end. Of FF JBs -8h | 1
987 | 2025-04-26 | B302 | Likita | Statcon Energia/Saft | NV | Battery Charger & Batteries | [9 empty] | 2025-04-26 |  | Offgrid Batt/Batt Ch. QAP
988 | 2025-04-26 | B302 | Likita | Statcon Energia | NV | Solar ON Grid PV system | [9 empty] | 2025-04-26 |  | On Grid Solar PV system QAP
989 | 2025-04-29 | B378 |  | YIL | NV | DCS |  |  | 2025-04-29 |  | 2025-04-29 |  | 2025-05-02 | 2025-05-02 |  |  |  | PO 631 -U&O post FAT compliance, Doc rev & IRN endors 29/4 & 2/5-8h | 1
990 | 2025-05-01 | B224 | Megha(Pkg 09) | JSW | SV | Motor | [6 empty] | 2025-05-06 | 2025-05-06 |  |  |  | Rev on TPI IRNs for Motor/T/f - 4 Nos - 8hrs | 1
991 | 2025-05-02 | 4994 |  | Lighting Technologies | SV | [12 empty] | Survey visit-8h | 1
992 | 2025-05-01 | B224 | L&T(DFCU) | YIL | NV | Analyser | [6 empty] | 2025-05-01 | 2025-05-01 |  |  |  | Rev & IRN end. Of GCs & Moisture Cabinet - 4h | 0.5
993 | 2025-05-02 | B224 | Megha Pkg(10) |  | SV | Magnetic Flowmeters | [8 empty] | 2025-05-02 |  |  | Rev1 ITP appl.
994 | 2025-05-02 | B224 | Megha(LLDPE) | KSBMIL | NV | Control Valves | [9 empty] | 2025-05-02 | 2025-05-21 | Rev2 ITP
995 | 2025-05-03 | B378 |  | YIL | NV | Analysers | [6 empty] | 2025-05-03 | 2025-05-03 |  |  |  | PO706- Compl.rev+IRN issue- 4h | 0.5
996 | 2025-05-02 | B224 | Megha(SRU) | KSBMIL | NV | Control Valves | [9 empty] | 2025-05-02 | 2025-06-11 | ITP Rev 2 | 0.5
997 | 2025-05-05 | B414 |  | Schneider | SV | Sw Bds | 3 | 3 | 2025-05-07 | 2025-05-09 | 2025-05-07 | 2025-05-09 | 2025-05-26 | 2025-05-26 |  |  |  | B414/55-3d+doc rev/IRN | 3.5
998 | 2025-05-05 | B378 |  | Schneider | SV | Sw Bds |  |  | 2025-05-07 | 2025-05-09 | 2025-05-07 | 2025-05-09 | 2025-05-26 | 2025-05-26 |  |  |  | B378/725-3d+doc rev/IRN | 3.5
999 | 2025-05-05 | B224 | Megha(Pkg 09) | KSBMIL | NV | Control Valves | [9 empty] | 2025-05-05 |  | ITP Rev0
1000 | 2025-05-06 | B224 | Megha(SRU) | Cords Cables | SV | Cables | [9 empty] | 2025-05-06 | 2025-05-08 | ITP Rev0 | 0.5
1001 | 2025-05-06 | B224 | Megha(SRU) | KEC | SV | Cables | [9 empty] | 2025-05-06 | 2025-05-08 | ITP Rev0 | 0.5
1002 | 2025-05-05 | B224 | Megha(PPU) | JSW | SV | Motor & VSD | [6 empty] | 2025-05-06 | 2025-05-06 |  |  |  | All Electrical Items - TPI doc. Rev. - 8hrs on 06/5/25 | 1
1003 | 2025-05-12 | B224 | Megha(SRU) | Emerson | NV | Mass Flow Meters | [9 empty] | 2025-05-12 | 2025-05-21 | ITP Rev1 | 0.5
1004 | 2025-05-12 | B224 | Megha(SRU) |  | NV | Magnetic Flowmeters | [9 empty] | 2025-05-12 | 2025-05-21 | ITP Rev1 | 0.5
1005 | 2025-05-09 | B224 | L&T(PFCCU) | YIL | NV | Analysers |  |  | 2025-05-16 | [8 empty] | HC Detectors
1006 | 2025-05-08 | B224 | Megha(Pkg09) | Emerson | NV | Guided Wave Radar Transmitter | [9 empty] | 2025-05-08 | 2025-06-11 | ITP Rev1
1007 | 2025-05-09 | B378 |  | YIL | VR | DCS | [11 empty] | Rev. Mtg. with GAIL for PP FAT readiness- 8h | 1
1008 | 2025-05-09 | B378 | Paramount | Control & Schematics | NV | Sw Bds | [11 empty] | TR test @ CPRI on 8&9/5 -16h | 2
1009 | 2025-05-12 | B448 |  | ABB | SV | Plant Automation system |  |  | 2025-05-19 | 2025-05-23 | 2025-05-19 | 2025-05-23 | 2025-05-28 | 2025-05-28 |  |  |  | Plant Automation System FAT @ ABB -5d | 5.5
1010 | 2025-05-10 | B378 | Paramount | Control & Schematics | SV | Sw Bds |  |  | 2025-05-15 | 2025-05-16 | 2025-05-15 | 2025-05-16 |  | 2025-08-11 |  |  |  | Paramount S/o on C&S for Sw Bds | 3
1011 | 2025-05-15 | B378 |  | YIL | VR | DCS | [11 empty] | Rev. mtg with GAIL &YIL - | 1
1012 | 2025-05-14 | B224 | Megha(Pkg10) |  | NV | Oxygen Analyser | [9 empty] | 2025-05-14 | 2025-06-11 | Rev0 | 0.5
1013 | 2025-05-15 | B224 | Megha(SRU) | CGL | SV | Motors | [9 empty] | 2025-05-15 | 2025-06-05 | ITP Rev1 | 0.5
1014 | 2025-05-15 | B448 | ABB | Continental | US | Control Valves | [9 empty] | 2025-05-15 | 2025-05-15 | 4hrs | 0.5
1015 | 2025-05-17 | B224 | Megha(Pkg09) | Cords Cables | SV | Cables | [9 empty] | 2025-05-17 | 2025-06-11 |  | 0.5
1016 | 2025-05-17 | B302 | KEPL | Tmeic | NV | Drives | 3 | 3 | 2025-05-22 | 2025-05-27 | 2025-05-22 | 2025-05-27 |  | 2025-07-29 |  |  |  | B302/8731-KEPL s/o on Tmeic -3nos -400kVA HV drives -5days | 4
1017 | 2025-05-16 | B224 | Megha(SRU) | Nexon Cables/Polycab | SV | Cables | [9 empty] | 2025-05-16 | 2025-05-27 |  | 0.5
1018 | 2025-05-16 | B224 | Megha(Pkg09) | Anderson Crosby | US | Pressure Relief Valves | [9 empty] | 2025-05-16 | 2025-05-19 | Rev0 - 4h | 0.5
1019 | 2025-05-20 | B302 |  | KSBMIL | NV | Control Valves | 5 | 5 | 2025-05-26 |  | 2025-05-26 |  | 2025-06-26 | 2025-06-26 |  |  |  | B302/2162 -1day | 1.5
1020 | 2025-05-20 | B269 |  | BDK Valves | BT | Valves |  |  | 2025-05-21 | 2025-05-23 | 2025-05-21 | 2025-05-23 | [5 empty] | Site Complaint-H2 Serv Vlvs- Exp. Visit 21-23/5- 3days | 3
1021 | 2025-05-20 | B224 | Tecnip | Micon | BT | Valves | 2 | 2 | 2025-05-22 |  | 2025-05-22
1022 | 2025-05-20 | B378 |  | Microfinish | US | Valves | 27 | 27 | 2025-05-27 | 2025-05-28 | [7 empty] | B378/611-2 days- postponed by a wk, after rect of Vol.Bot.
1023 | 2025-05-20 | B224 | Megha(SRU) | Chabi Electricals | SV | Battery Charger & Batteries | [9 empty] | 2025-05-20 | 2025-05-27 |  | 0.5
1024 | 2025-05-21 | B224 | L&T(PFCCU) | YIL | NV | Wireless Instruments |  |  | 2025-05-26 |  | 2025-05-30 | [6 empty] | HHC | 0.5
1025 | 2025-05-22 | B224 | L&T(DFCU) | YIL | NV | Wireless Instruments |  |  | 2025-05-28 |  | 2025-05-30 | [6 empty] | Tablets | 0.5
1026 | 2025-05-21 | B414 | Pace Process Controls | Schneider | SV | Busducts | [9 empty] | 2025-05-20 | 2025-05-26
1027 | 2025-05-23 | B297 |  | TS Flow Controls | BT | Valves | 2 | 2 | 2025-05-23 |  | 2025-05-23 | [6 empty] | B297/308 | 1
1028 | 2025-05-21 | B378 |  | YIL | NV | DCS |  |  | 2025-05-30 | 2025-06-06 | 2025-05-30 | 2025-06-06 | [5 empty] | PP FAT | 5
1029 | 2025-05-21 | B378 |  | Schneider | SV | Sw Bds |  |  | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-05-30 | 2025-06-09 | 2025-06-09 |  |  |  | B378/725 | 3.5
1030 | 2025-05-28 | B414 |  | Schneider | SV | Sw Bds | 2 | 2 | 2025-05-29 |  | 2025-05-29 | [6 empty] | B414/55-1d-APFC cabs | 1
1031 | 2025-05-28 | B269 |  | YIL | NV | DCS | [6 empty] | 2025-05-28 | 2025-05-28 |  |  |  | B269/1415- RHCU DCS + MCT rev & endors. | 1
1032 | 2025-05-28 | B378 |  | ABB | NV | Analysers |  |  | 2025-05-29 |  | 2025-05-29 | [6 empty] | B378/569 | 1
1033 | 2025-05-28 | B269 |  | YIL | NV | DCS | [6 empty] | 2025-05-28 | 2025-05-28 |  |  |  | B269/1415- Power & Sig. cables rev & IRN endors. | 0.5
1034 | 2025-05-28 | B224 | Megha(Pkg 09) | Endress & Hauser | NV | Radar Level Insts | [9 empty] | 2025-05-28 | 2025-06-02 |  | 0.5
1035 | 2025-05-30 | B378 | Shreem Electricals | Kalpa Electricals | SV | RVT |  |  | 2025-06-10 |  | 2025-06-10 |  |  | 2025-07-24 | 2025-07-24 |  |  | B378/821 | 1
1036 | 2025-05-30 | B302 | KEPL | Tmeic | SV | Drives | 2 | 2 | 2025-06-06 |  | 2025-06-06 | [6 empty] | B302/8731-KEPL s/o on Tmeic -3nos -400kVA HV drives -Light load test
1037 | 2025-05-30 | B224 | Megha(LLDPE) | NOV | SV | Drives | [9 empty] | 2025-05-30 | 2025-06-09 |  | 0.5
1038 | 2025-06-02 | B224 | Megha(SRU) | Flowserve/ABB | SV | Motor | [9 empty] | 2025-05-30 | 2025-06-05 | Motor QAP | 0.5
1039 | 2025-06-02 | B224 | Megha(Pkg09) |  | NV | Level Transmitters | [9 empty] | 2025-06-02 | 2025-07-07
1040 | 2025-06-03 | B378 |  | Hitachi | SV | Capacitor Package | 4 | 4 | 2025-06-13 | 2025-06-16 | 2025-06-13 | 2025-06-16 | 2025-06-20 | 2025-06-20 |  |  |  | B378/836 | 2.5
1041 | 2025-06-04 | B224 | Afcons | Microfinish | US | Valves | [6 empty] | 2025-06-04 | 2025-06-04 |  |  |  | rev. & end. ofTPI IRN | 1
1042 | 2025-06-04 | B224 | Megha(PPU) | KEC Asian Cables | SV | Cables | [9 empty] | 2025-06-04 | 2025-06-09 |  | 0.5
1043 | 2025-06-06 | B767 |  | OLA | VR | ACC |  |  | 2025-06-12 | 2025-06-13 | [7 empty] | RPOB not participated in visit
1044 | 2025-06-06 | B224 | Megha(SRU) |  | SV | Cables | [9 empty] | 2025-06-06 | 2025-07-29 | Inst.Cables | 0.5
1045 | 2025-06-09 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves |  |  | 2025-06-10 | 2025-06-16
1046 | 2025-06-09 | B269 |  | BDK Valves | BT | Valves |  |  |  |  | 2025-06-11 | 2025-06-13 | [5 empty] | Exp. Of rect. Of vlvs recd frm site | 3
1047 | 2025-06-09 | B378 |  | Microfinish | BT | Valves | 27 | 27 | 2025-06-11 | 2025-06-13 | 2025-06-11 | 2025-06-13 | [5 empty] | B378/611 | 3
1048 | 2025-06-09 | B414 | Volksenergie | HBL | SV | Batteries |  |  | 2025-06-11 | 2025-06-12 | 2025-06-11 | 2025-06-12 | [5 empty] | B414/62-LFP Batteries
1049 | 2025-06-09 | B224 | Mahati | HFCL | NV | FO Cables | [9 empty] | 2025-06-09 | 2025-07-10 |  | 0.5
1050 | 2025-06-10 | B224 | Megha(SRU) | Exide | SV | Batteries |  |  | 2025-06-17 | [8 empty] | Hitachi Hirel S/o-NiCd Batteries - App. In CatB by SV-to convert to CatC
1051 | 2025-06-09 | C007 |  | Suryaroshini | US | Pipe Mill |  |  | 2025-06-16 | 2025-06-30 | 2025-06-16 | 2025-06-30 | [5 empty] | Coating-15d | 11
1052 | 2025-06-06 | B224 | Megha(SRU) | Endress & Hauser | NV | [10 empty] | 2025-06-06
1053 | 2025-06-11 | B398 | Likita | KECRPG | NV | FO Cables | [6 empty] | 2025-06-23 | 2025-06-23 |  |  |  | As per Pjt adv. TPI IRN to be reviewed by us | 0.5
1049 | 2025-06-09 | B224 | Megha(Pkg06) | KSBMIL | BT | Control Valves | 100 | 100 | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-20 | 2025-06-30 | 2025-06-30 |  |  |  |  | 3.5
1050 | 2025-06-12 | B224 | Megha(Pkg09) | ABB | SV | Motors | [9 empty] | 2025-06-12 |  | LT Motors
1051 | 2025-06-12 | B224 | Megha(Pkg09) | CG Power | SV | Motors | [9 empty] | 2025-06-12 |  | HT/LT Motors
1052 | 2025-06-16 | B224 | Megha(LLDPE) | JSW/Tmeic | SV | Motors | 4 | 4 | 2025-06-20 | 2025-06-21 | [7 empty] | Motors reported not ready
1053 | 2025-05-01 | B302 | Likita | Statcon | SV | Solar ON Grid PV system | [9 empty] | 2025-05-01 | 2025-06-15 | After rect. Of all ref. docs - 6 QAPs | 1
1054 | 2025-06-16 | B269 |  | YIL | NV | DCS |  |  | 2025-06-23 | 2025-06-28 | 2025-06-23 | 2025-06-28 |  | 2025-07-19 |  |  |  | AVU FAT | 6
1055 | 2025-06-17 | B378 | Paramount | Control & Schematics | NV | Sw Bds | 3 | 3 | 2025-06-18 | 2025-06-23 | 2025-06-18 | 2025-06-23 | 30-06-202514-jul-25 |  | 2025-07-28 |  |  | compl. Rev on 14/7 | 3
1056 | 2025-06-17 | B302 | Ruhrpumpen | Tmeic | SV | Drives | 4 | 4 | 2025-06-17 | 2025-06-20 | 2025-06-17 | 2025-06-20 | [5 empty] | B302/6873-RP s/o on Tmeic -4nos -400kVA HV drives | 4
1057 | 2025-06-17 | B378 | Schneider | Stardrive | NV | Busducts |  |  | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-20 | 2025-06-30 | 2025-06-30 |  |  |  | B378/725 s/o | 2.5
1058 | 2025-06-17 | B548 | NRP | Stardrive | NV | Busducts |  |  | 2025-06-20 |  | 2025-06-20 |  | 2025-07-14 | 2025-08-14 |  |  |  | compl.rev on 14/7 | 1.5
1059 | 2025-06-17 | B224 | Megha(Pkg08) | Atlas Copco/BHEL | SV | Motors | [9 empty] | 2025-06-17
1060 | 2025-06-17 | B269 |  | BDK Valves | BT,AG | Valves | [11 empty] | VC with IOC/HO/site | 0.5
1061 | 2025-06-05 | B414 | Pace Process Controls | Polycab | SV | Cables | [9 empty] | 2025-06-05 | 2025-06-18 |  | 0.5
1062 | 2025-06-18 | B378 |  | Schneider | SV | Sw Bds | 6 | 6 | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-27 | [5 empty] | B378/725 | 3
1063 | 2025-06-18 | B224 | Megha(Pkg09) | MK Engineers | SV | Panels | [9 empty] | 2025-06-18 | 2025-07-14
1067 | 2025-06-19 | B224 | Megha(SRU) | Emerson | NV | Mass Flow Meters | 2 | 2 | 2025-06-23 | 2025-06-24 | 2025-06-24 | [7 empty] | 1
1068 | 2025-06-19 | B224 | Megha(SRU) | Emerson | NV | Magnetic Flowmeters | 2 | 2 | 2025-06-30 | 2025-07-01 |  | 2025-06-25 | 2025-06-26 | [5 empty] | 2
1069 | 2025-06-19 | B224 | Megha(Pkg10) | MTL | VR | Fieldbus JB | [9 empty] | 2025-06-19 | 2025-06-19 |  | 0.5
1070 | 2025-06-19 | B448 | ABB | GM Engg. | US | Valves | [9 empty] | 2025-06-19
1071 | 2025-06-19 | B302 | Fluidyne | Auma | BT | Actuators | 19 | 19 | 2025-06-23 |  | 2025-07-01 | [6 empty] | Insp.resch. For more nos.
1072 | 2025-06-19 | B224 | Tecnip | YIL | NV | Analysers |  |  | 2025-06-26 |  | 2025-06-26 |  | 2025-07-08 | 2025-07-08 |  |  |  | SRR10 panels | 1.5
1073 | 2025-06-19 | B224 | Megha(PPU) | JSW/GE Vernova | SV | Motors | [9 empty] | 2025-06-19 | 2025-06-25 | ITP rev2
1074 | 2025-06-18 | B224 | Megha(Pkg10) | Codel/Forbes Marshall | VR | Analysers | [9 empty] | 2025-06-18 | 2025-06-19 | As per Code2 comments, SO2 & CO anal. To be fully imported frm Codel,UK-QAP not reviewed | 0.5
1075 | 2025-06-18 | B224 | Megha(SRU) | Adage | NV | Analysers | [9 empty] | 2025-06-18 | 2025-07-09 | 4 QAPs with various Analysers | 1
1076 | 2025-06-20 | B224 | Megha(SRU) | HBL | SV | Batteries | [9 empty] | 2025-06-20 | 2025-06-23 |  | 0.5
1077 | 2025-06-17 | B302 | Likita | Chetan Engineers | SV | Fire Alarm System | [9 empty] | 2025-06-17 | 2025-06-23 |  | 0.5
1078 | 2025-06-17 | B302 | Likita | Chetan Engineers | SV | CO2 Flooding System | [9 empty] | 2025-06-17 | 2025-06-23 |  | 0.5
1079 | 2025-06-25 | B224 | Megha(SRU) | Sherman | NV | Thermal Mass Flowmeters | [9 empty] | 2025-06-25 | 2025-07-10 | ITP rev1-Fluid Component
1080 | 2025-06-26 | B440 |  | Microfinish | BT | Valves | 10 | 10 |  |  |  |  | 2025-06-26 | 2025-06-26 |  |  |  | B440/155-rev+end of TPI IRN | 0.5
1081 | 2025-06-26 | B269 |  | BDK Valves | AG/BT | Valves | [11 empty] | VC | 0.5
1082 | 2025-06-30 | B378 |  | YIL | NV | DCS |  |  | 2025-06-26 |  | 2025-06-26 |  | 2025-06-30 | 2025-06-30 |  |  |  | PPU DCS & Dig Sol.IRN | 1.5
1083 | 2025-06-30 | B224 | Megha(LLDPE) | DMW/Tmeic | SV | Drives | 4 | 4 | 2025-07-02 | 2025-07-04 | 2025-07-07 | 2025-07-09 | [5 empty] | 6.6kV,180kW HT motors - 4 nos | 3
1084 | 2025-06-28 | B224 | Megha(Pkg10)/TKIL | Forbes Marshall/Codel | NV | CO Analyser | [9 empty] | 2025-06-28 | 2025-07-10 | ITP Rev1 | 0.5
1085 | 2025-06-30 | B224 | Megha(Pkg 09) | Sterlite | SV | EHV Cables | [9 empty] | 2025-06-30 | 2025-08-08 | HV & EHV-2QAPs
1096 | 2025-06-19 | B302 | Fluidyne | Auma | BT | Actuators | 36 | 36 | 2025-06-30 |  | 2025-07-01
1097 | 2025-06-30 | B414 | Volksenergie | HBL | SV | Batteries | 11 | 11 | 2025-07-02 | 2025-07-03 | 2025-07-02 | 2025-07-03 |  |  | 2025-07-30 |  |  | B414/62-LFP Batteries
1098 | 2025-07-01 | B448 | ABB | Baliga | SV | Telephone Booth | [7 empty] | 2025-07-01 |  |  |  |  | 0.5
1099 | 2025-07-02 | B224 | Megha(Pkg06) | KSBMIL | BT | Control Valves | 54 | 54 | 2025-07-08 | 2025-07-11 | 2025-07-10 |  | 2025-07-24 | 2025-07-24 |  |  |  | 2nd Lot | 4.5
1100 | 2025-07-02 | B224 | Megha(Pkg09) |  | US | ON-OFF valves | [9 empty] | 2025-07-02 | 2025-07-07 |  | 0.5 | 1
1101 | 2025-07-02 | B224 | Megha(Pkg09) | Siemens Energy | SV | GRP | [9 empty] | 2025-07-03 | 2025-07-08 | Gen. Relay Panel | 0.5
1102 | 2025-07-05 | B224 | Afcons | Emerson | NV | Ultrasonic FM | 3 | 3 | 2025-07-14 | 2025-07-22 | 2025-07-21 | 2025-07-22 |  | 2025-07-23 | 2025-07-23 |  |  | 24"-3 nos - recal. | 2.5
1103 | 2025-07-17 | B224 | Megha(SRU) | Emerson | NV | Mass Flow Meters | 2 | 2 | 2025-07-21 | 2025-07-22 | 2025-07-21 | 2025-07-22 | [5 empty] | FCRI-recal. | 2
1104 | 2025-07-04 | B224 | Megha(SRU) | Godrej | SV | Busducts | [9 empty] | 2025-07-04 | 2025-07-08 |  | 0.5
1105 | 2025-07-04 | B224 | Megha(Pkg09) |  | SV | MMS | [9 empty] | 2025-07-04 | 2025-07-08 |  | 0.5
1106 | 2025-07-03 | B378 |  | YIL | NV | DCS | [6 empty] | 2025-07-03 | 2025-07-03 |  |  |  | Cyber sec doc rev/IRN | 0.5
1107 | 2025-07-04 | 4994 |  | Nidec | SV | Emergency Generator | [11 empty] | Enlistment Survey | 2
1108 | 2025-07-04 | B302 | Ruhrpumpen | Tmeic | SV | Drives | 2 | 2 | 2025-07-07 |  | 2025-07-07 | [6 empty] | PO6873-reinsp of failed drives | 1
1109 | 2025-06-02 | B224 | Megha(Pkg09) |  | NV | Level Transmitters | [9 empty] | 2025-06-02 | 2025-07-07 |  | 0.5
1110 | 2025-07-08 | B269 |  | BDK Valves | AG/BT | Valves | [11 empty] | VC on 8,15/7 | 1
1111 | 2025-07-08 | B440 |  | Weir Minerals | BT | Hydrocyclone | [6 empty] | 2025-07-08 |  |  |  |  | Insp clarifications | 0.5
1112 | 2025-07-08 | B224 |  | YIL | NV | DCS |  |  | 2025-07-10 |  | 2025-07-11 | 2025-07-27 |  | 2025-07-22 |  |  |  | Aux Consoles | 2
1113 | 2025-07-08 | B224 | Megha(SRU) | Godrej | SV | Busducts |  |  | 2025-07-15 | 2025-07-17 | 2025-07-21 | 2025-07-23 | 2025-07-27 | 2025-07-27 | 2025-07-31 |  |  |  | 4
1114 | 2025-07-08 | B448 | ABB | Emerson | NV | Mass Flow Meters | [9 empty] | 2025-07-08 | 2025-07-08 | Rev. of Various QAPs of MFM,Control Vlv & Pr. Rel. Vlv | 2
1115 | 2025-07-10 | B224 | Megha(SRU) | Endress & Hauser | NV | Guided Wave Radar Transmitter | [9 empty] | 2025-06-06 | 2025-06-10 |  | 0.5
1116 | 2025-07-08 | B378 |  | YIL | NV | DCS |  |  | 2025-07-08 |  | 2025-07-08 | [6 empty] | PDH Raw matl id & certification | 1
1117 | 2025-06-25 | B224 | L&T(DFCU) | YIL | NV | DCS | [6 empty] | 2025-07-09 | 2025-07-09 |  |  |  | Tablets | 0.5
1118 | 2025-07-09 | B224 | Megha(Pkg09) |  | NV | Control Valves | [9 empty] | 2025-06-10 | 2025-07-09 |  | 0.5
1119 | 2025-07-10 | B224 | Megha(SRU) | Endress & Hauser | NV | Servo Level Inst | [9 empty] | 2025-07-10 | 2025-07-31 | Rev1
1120 | 2025-07-13 | B302 |  | Shirdi Sai | US | Transformer | 2 | 2 | 2025-07-21 | 2025-07-22 | 2025-07-21 | 2025-07-22 | [5 empty] | 6.6/3.3kV;10/12.5 MVA & 33/6.9kV,10/12.5MVA- Vac & Pr test | 2
1121 | 2025-07-11 | B302 | Ruhrpumpen | Tmeic | SV | Drives | 2 | 2 | 2025-07-29 |  | 2025-07-29 |  | 2025-07-17 |  |  |  |  | PO6873-light load test | 2
1122 | 2025-07-09 | B448 | ABB | Continental | US | Control Valves | [9 empty] | 2025-07-09 | 2025-07-10 |  | 0.5
1123 | 2025-07-11 | B224 | Megha(Pkg09) | Sterlite | SV | EHV Cables | [9 empty] | 2025-07-11 | 2025-07-14 |  | 0.5
1124 | 2025-07-11 | B448 | ABB | Microfinish | US | ON-OFF valves | [9 empty] | 2025-07-11
1125 | 2025-07-10 | B448 | ABB |  | AG | Metering Skid | [9 empty] | 2025-07-10 | 2025-07-11 | WPS/PQR appl.,review of Pipe ITP, | 1
1126 | 2025-07-11 | B414 | Pace Process Controls | Universal Cables | SV | Capacitor Package | [9 empty] | 2025-07-11 |  | Capacitor,RVT,Series Reactor,Capacitor panel-4QAPs
1127 | 2025-07-03 | 8518 | HPCL GRDC |  | VR | [12 empty] | BEL team visit | 1
1128 | 2025-07-12 | B224 |  | YIL | NV | DCS |  |  | 2025-07-17 | 2025-07-19 | 2025-07-17 | 2025-07-19 | [5 empty] | SRU ESD H/w FAT | 3
1129 | 2025-07-14 | 158 | [6 empty] | 2025-07-17 | 2025-07-18 | 2025-07-17 | 2025-07-18 | [5 empty] | Intl Audit | 18
1130 | 2025-07-12 | B302 | Fluidyne | Auma | BT | Actuators | 12 | 12 | 2025-07-15 |  | 2025-07-16 |  |  | 2025-07-16 |  |  |  |  | 1
1131 | 2025-07-11 | B224 | Megha(Pkg09) | Vertiv | SV | UPS | [9 empty] | 2025-07-11 | 2025-07-17 |  | 0.5
1132 | 2025-07-14 | B269 |  | BDK Valves | AG | Valves | [6 empty] | 2025-07-11 |  |  |  |  | Rev.& acc. Of prop.for bypass welding | 0.5
1133 | 2025-07-14 | B224 | Megha(Pkg09) | MK Engineers | SV | Panels | [6 empty] | 2025-07-14 |  |  |  |  | Rev1
1134 | 2025-07-14 | B519 |  | YIL | NV | Analysers |  |  | 2025-07-25 |  | 2025-07-25 |  | 2025-08-11 |  |  |  |  | PO 6827- FAT with BPCL participation | 1
1135 | 2025-07-14 | B378 |  | YIL | NV | Analyser Shelter |  |  | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-07-25 | [5 empty] | PO620
1136 | 2025-07-15 | B224 | Megha(Pkg09) |  | SV | MMS | [9 empty] | 2025-07-15 | 2025-07-15 | Rev1 | 0.5
1137 | 2025-07-15 | B224 | Megha(Pkg09) | Siemens Energy | SV | GRP | [9 empty] | 2025-07-15 | 2025-07-15 | Gen. Relay Panel Rev1 | 0.5
1138 | 2025-07-15 | B224 | Megha(Pkg10) | Suyog Electricals | SV | MV Cables | [9 empty] | 2025-07-15 | 2025-07-16 |  | 0.5
1139 | 2025-07-14 | B297 |  | YIL | NV | Analysers |  |  | 2025-07-23 |  | 2025-07-23 | [6 empty] | PO 160 | 1
1140 | 2025-07-18 | B224 | Megha(Pkg09) | Siemens Energy/TDPS | SV | Alternators | 1 | 1 | 2025-07-30 | 2025-07-31 | 2025-07-30 | 2025-07-31 | [5 empty] | 48MW Alternator
1141 | 2025-07-21 | B269 |  | ABB | SV | ECS | [11 empty] | Rev.Mtg with client - VR&SV | 0.5
1142 | 2025-07-21 | 8518 |  | IIMB | VR | [12 empty] | Tech.Presentation | 1
1143 | 2025-07-22 | B224 | Megha(PPU) | Sterlite | SV | EHV Cables | [9 empty] | 2025-07-22 | 2025-07-22 | HV & EHV-2QAPs | 0.5
1144 | 2025-07-22 | B224 | Megha(SRU) | Sterlite | SV | EHV Cables | [9 empty] | 2025-07-22 | 2025-07-22 |  | 0.5
1145 | 2025-07-22 | B224 | Megha(LLDPE) | Shreem | SV | Capacitor | [9 empty] | 2025-07-22 | 2025-07-22 |  | 0.5
1146 | 2025-07-22 | B224 | Megha(LLDPE) | Sterlite | SV | EHV Cables | [9 empty] | 2025-07-22 | 2025-07-23 |  | 0.5
1147 | 2025-07-22 | B224 | Megha(Pkg09) | Sterlite | SV | MV Cables | [9 empty] | 2025-07-22 | 2025-07-22 | MV XLPE cable | 0.5
1148 | 2025-07-22 | B224 | Megha(Pkg09) | Polycab | SV | EHV Cables | [9 empty] | 2025-07-22 | 2025-07-23 | 6.6 & 11kVcables | 0.5
1149 | 2025-07-22 | B224 | Afcons | Microfinish | US | Valves | 2 | 2 | 2025-07-25 | 2025-07-26 | 2025-07-29 | 2025-07-30 | [5 empty] | 2nos 48" vlvs | 2
1150 | 2025-07-22 | B224 | Megha(SRU) | Emerson | NV | Magnetic Flowmeters | 2 | 2 | 2025-08-01 |  | 2025-08-01 | [6 empty] | FCRI wet cal.reinsp.
1151 | 2025-07-22 | 4994 |  | Jindalsaw | AG |  |  |  | 2025-07-25 |  | 2025-07-25 | [6 empty] | Reval. | 1
1152 | 2025-07-21 | B378 |  | ABB | NV | Analyser Shelter | 1 | 1 | 2025-07-28 | 2025-07-29 | 2025-07-28 | 2025-07-29 | [5 empty] | B378/618 | 2
1153 | 2025-07-21 | B378 |  | ABB | NV | Analyser Shelter | 1 | 1 | 2025-07-28 |  | 2025-07-28 | [6 empty] | B378/569-bal. items | 1
1154 | 2025-07-14 | B440 | Tecnicas Reunidas | Neo Structo Construction | BT | Spools | [6 empty] | 2025-07-23 | 2025-07-23 |  |  |  | TC rev&IRN end of loose spools & pr parts | 1
1155 | 2025-07-18 | B269 |  | YIL | NV | DCS |  |  | 2025-07-28 | 2025-08-07 | 2025-07-28 | 2025-08-07 | 2025-08-30 | 2025-08-30 |  |  |  | CT1& other Util sec. FAT | 4
1156 | 2025-07-25 | C007 |  | Welspun | BT | Pipe Mill |  |  | 2025-07-29 | 2025-08-13 | 2025-07-29 | 2025-08-13
1157 | 2025-07-25 | B448 |  | Weinberg | SV | Consoles |  |  | 2025-07-28 |  | 2025-07-28 | [6 empty] | Plant Automation Sys- Console Insp. | 1
1158 | 2025-07-24 | B414 | Pace Process Controls | Thermal Instrument | NV | [10 empty] | 2024-07-24 | 2025-07-28 | RTD/T/w QAP | 0.5
1159 | 2025-07-26 | B224 | Megha(SRU) | Adage | NV | Analysers | [9 empty] | 2025-07-26 | 2025-07-31 | 4QAPs-Rev3 | 0.5
1160 | 2025-07-26 | B224 | Megha(Pkg10) | ABB | NV | Analysers | 12 | 12 | 2025-08-05 |  | 2025-08-05 | [6 empty] | O2 Anal
1161 | 2025-07-28 | 4994 |  | Uniabex | US | Forgings |  |  |  |  | 2025-07-30 | [6 empty] | Revalidation | 1
1162 | 2025-07-28 | B269 |  | BDK Valves | US | [5 empty] | 2025-07-30 | [6 empty] | Rev. of site issues | 1
1163 | 2025-07-28 | B224 | Megha(LLDPE) | Meher | SV | Series Reactors | 60 | 60 | 2025-08-04 |  | 2025-08-04 |  | 2025-11-03 | 2025-11-03
1164 | 2025-07-28 | B224 | Megha(Pkg09)/Siemens | Southern Lubrication | AG | LOS | 1 | 1 | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-14 | [6 empty] | 2
1165 | 2025-07-28 | 8590 | PROSTARM INFO SYSTEMS LIMITED | HBL | SV | Batteries | 384 | 384 |  |  |  |  | 2025-08-13 | 2025-08-13 |  |  |  | VRLA-120AH-2 sets of 192 cells for EIB | 2
1165 | 2025-07-29 | B224 | Megha(LLDPE) | ABB | SV | Drives | 1 | 1 | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-08 | [5 empty] | NOV ord.on ABB | 2
1166 | 2025-07-30 | B224 | Megha(Pkg09) |  | SV | SCAP | [9 empty] | 2025-07-30 | 2025-08-09 |  | 0.5
1167 | 2025-07-30 | B398 | CCIPL | SAFT | SV | Batteries | [6 empty] | 2025-08-14 | 2025-08-14 |  |  |  | Rev. as per ITP | 0.5
1168 | 2025-07-25 | B224 | L&T(DFCU) | KSBMIL | NV | Control Valves | 1 | 1 | [6 empty] | 2025-07-31 |  |  | Rev/IRN end. | 0.5
1169 | 2025-07-31 | B224 | Megha(SRU) | Hitachi | SV | Capacitor Package | 2 | 2 | 2025-08-11 | 2025-08-12 | 2025-08-11 | 2025-08-12 | [6 empty] | 2
1170 | 2025-08-01 | B302 | KEPL | Tmeic | SV | Drives | 3 | 3 | 2025-08-18 | 2025-08-21 | 2025-08-18 | 2025-08-21 | [5 empty] | PO8731-400KVA VFDs
1171 | 2025-08-02 | B224 | Megha(Pkg09) | Vertiv | SV | UPS | [9 empty] | 2025-08-02 | 2025-08-08 | Rev1 | 0.5
1172 | 2025-08-04 | B224 | Megha(Pkg10) | Emerson | NV | Mass Flow Meters | [9 empty] | 2025-08-04 | 2025-08-08 | Rev0 | 0.5
1173 | 2025-08-05 | B224 | Megha(Pkg09) | Siemens/KSBMIL | US | Control Valves | [9 empty] | 2025-08-05 | 2025-08-05 | CV+DSH | 0.5
1174 | 2025-08-05 | B414 | Pace Process Controls | FCG | SV | Panels | [9 empty] | 2025-08-05 | 2025-08-05 | 2 QAPs | 1
1175 | 2025-08-04 | B448 | ABB | Werner | SV | Consoles | [9 empty] | 2025-08-04 | 2025-08-06 | QAP rev. | 0.5
1169 | 2025-07-31 | B224 | L&T(DFCU) | YIL | NV | HHC | [7 empty] | 2025-08-05 |  |  |  | Doc rev/TPI IRN endorsement | 0.5
1170 | 2025-08-07 | B224 | Megha(Pkg10) |  | NV | CO Analyser | [9 empty] | 2025-08-07 | 2025-08-08 | Rev2 | 0.5
1171 | 2025-08-07 | B224 | Megha(Pkg10) |  | NV | SOX Analyser | [9 empty] | 2025-08-07 | 2025-08-08 | Rev1 | 0.5
1172 | 2025-08-18 | B414 | Pace Process Controls | Narkhade Engg. | SV | NGR | [9 empty] | 2025-08-18 | 2025-08-18 |  | 0.5
1173 | 2025-08-14 | B448 | ABB |  | US | Metering Skid | [9 empty] | 2025-08-14 | 2025-08-16 |  | 0.5
1174 | 2025-08-14 | B378 | YIL |  | NV | Analysers | [6 empty] | 2025-08-14 | 2025-08-14 |  |  |  | Compl. Rev+IRN issue | 0.5
1175 | 2025-08-13 | B378 | ABB |  | SV | ECS | 1 | 1 | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-26
1176 | 2025-08-14 | B302 | Fluidyne | Auma | BT | Actuators | 10 | 10 | 2025-08-26 |  | 2025-08-26 | [6 empty] | Last Lot | 1
1177 | 2025-08-06 | B378 |  | KSBMIL | US | Control Valves | 11 | 11 | 2025-08-11 | 2025-08-12 | 2025-08-11 | 2025-08-12 | 2025-08-25 | 2025-08-25 |  |  |  | B378/816 | 3
1178 | 2025-08-06 | B224 | Megha(SRU) | KSBMIL | US | Control Valves |  |  | 2025-08-11 | 2025-08-12 | 2025-08-11 | 2025-08-12 | [6 empty] | 2
1179 | 2025-08-14 | B224 | Megha(Pkg09) |  | NV | Level Transmitters | [9 empty] | 2025-08-14 | 2025-08-30 | Rev1 | 0.5
1180 | 2025-08-13 | B224 | Megha(Pkg09) |  | NV | Flow Nozzle & Venturi | [9 empty] | 2025-08-13 | 2025-09-02 | 2 QAPs
1181 | 2025-08-13 | B224 | Megha(Pkg09) |  | US | Control Valves | [9 empty] | 2025-08-13 | 2025-08-18 | 3 QAPs-2 reviewed;1 cat C | 0.5
1182 | 2025-08-08 | B224 | Megha(SRU) | YIL | NV | DCS |  |  | 2025-08-11 | 2025-08-13 | 2025-08-11 | 2025-08-13 | [5 empty] | SRU-118,119 & 120 | 3
1183 | 2025-08-08 | B224 | Megha(Pkg09) | TDPS | SV | Alternators | 1 | 1 | 2025-08-22 | 2025-08-23 | 2025-08-22 | 2025-08-23 | [5 empty] | Last Lot | 2
1184 | 2025-08-08 | B378 | Paramount | Control & Schematics | NV | Sw Bds | [6 empty] | 2025-08-11 | 2025-08-11 |  |  |  | Spares | 0.5
1185 | 2025-08-08 | B224 | Megha(Pkg09) | Vee Vee Controls | NV | Panels | 10 | 10 | 2025-08-21 | 2025-08-23
1186 | 2025-08-07 | B224 | Megha(Pkg09) |  | SV | Power Cables | [9 empty] | 2025-08-07 | 2025-08-22 | 1.1kV Power Cable | 0.5
1187 | 2025-08-11 | B411 | Bluegrass Tech. | West Coastoptilinks | NV | OFC | [6 empty] | 2025-09-07 | 2025-09-07 |  |  |  | Rev& Endors. Of TPI repts | 1
1188 | 2025-08-18 | B448 |  | ABB | US | Plant Automation system | [6 empty] | 2025-08-19 |  |  |  |  | Rev.mtg.with Client | 1
1189 | 2025-08-18 | B224 | Megha(Pkg10A) | Emerson | NV | Mass Flow Meters | 8 | 8 | 2025-08-25 | 2025-09-01 | [7 empty] | Cal of MFMs @ FCRI - Rescheduled to 9-12/9 vide mail dt.23/8
1190 | 2025-08-19 | B414 | Pace Process Controls | Sri Jaishanth | NV | Gas Detectors | [9 empty] | 2025-08-19 | 2025-09-01 |  | 0.5
1191 | 2025-08-12 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 40 | 40 | 2025-08-18 | 2025-08-21 | 2025-08-18 | 2025-08-21 | [6 empty] | 4
1192 | 2025-08-13 | B378 |  | ABB | SV | ECS |  |  | 2025-08-25 | 2025-08-26 | 2025-08-25 | 2025-08-26 | 2025-08-29 | [5 empty] | 3
1193 | 2025-08-20 | B224 | Megha(Pkg10A) | Flexpro | SV | Flame Proof JBs | [9 empty] | 2025-08-20 | 2025-08-20 |  | 0.5
1194 | 2025-08-22 | B224 | Megha(Pkg09) | Chabi Electricals | SV | Battery Charger & Batteries | [9 empty] | 2025-08-22 | 2025-08-22 |  | 0.5
1195 | 2025-08-22 | B224 | Megha(LLDPE) | Atlas Copco/BHEL | SV | Motors | [9 empty] | 2025-08-22
1196 | 2025-08-25 | B302 | KEPL | Tmeic | SV | Drives | 2 | 2 | 2025-08-28 | 2025-09-05 | 2025-08-28 |  | 2025-09-12 |  |  |  |  | Light load of 2 nos VFD | 2
1197 | 2025-08-25 | B224 | Afcons | Emerson | VR | Ultrasonic FM | 1 | 1 | 2025-08-26 |  | 2025-08-26 | [7 empty] | 1
1198 | 2025-08-25 | B224 | Megha(Pkg09) | Siemens/KSBMIL | US | Control Valves | [9 empty] | 2025-08-25 | 2025-08-25 | CV+DSH- Rev2 | 0.5
1199 | 2025-08-25 | B302 | YIL | YIL | NV | Field Insts | 244 | 244 | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-09 | [6 empty] | 2
1200 | 2025-08-18 | B302 | YIL | YIL | NV | PLC | [9 empty] | 2025-08-18 | 2025-08-26 | PO 103- QAPs of PLC & Field Insts | 0.5
1201 | 2025-08-28 | B448 | ABB | Emerson | NV | Mass Flow Meters | 8 | 8 | 2025-09-08 | 2025-09-12 | 2025-09-10 | 2025-09-12 | [5 empty] | 1no. Passed on 10/9; cust t/f meter testing 4" planned today
1202 | 2025-08-21 | B224 | Megha(LLDPE) | Tmeic | SV | Motors | 4 | 4 | 2025-07-07 | 2025-07-08 | 2025-07-07 | 2025-07-08 | 2025-08-21 | 2025-08-21 |  |  |  | 6.6kV,180KW | 0.5
1203 | 2025-08-29 | B269 |  | BDK Valves | BT | Valves |  |  | 2025-09-03 |  | 2025-09-03 | [6 empty] | mtg. with IOCL/Pjts | 1
1204 | 2025-08-29 | B297 |  | Belgaum Aqua | BT | Valves | 20 | 20 | 2025-09-04 |  | 2025-09-04 | [6 empty] | PO 315 | 1
1205 | 2025-08-29 | B224 | Megha(Pkg09) | Suyog Electricals | NV | Cables | [9 empty] | 2025-08-29 | 2025-09-05 | T/c & signal cable
1206 | 2025-08-29 | B224 | Technip | YIL | NV | Analyser | 2 | 2 | [9 empty] | Moisture Analyser
1207 | 2025-08-09 | B933 |  | Flowserve | BT | Pumps | [9 empty] | 2025-08-09 | 2025-08-29 | Pump ITP | 0.5
1208 | 2025-08-25 | B302 | KEPL | Tmeic | SV | Drives | 2 | 2 | 2025-09-05 | [8 empty] | Light load of 2x400KVA
1209 | 2025-09-01 | B933 |  |  | BT | Fittings | [11 empty] | Meet on Fittings MR reqt | 0.5
1210 | 2025-09-02 | B861 |  | Enginemates | BT | Air Finned Cooler | [11 empty] | Mtg. on 2/9 for ITP(PAUG) disc.
1211 | 2025-07-11 | B448 | ABB | Microfinish | US | ON-OFF valves | [9 empty] | 2025-07-11 | 2025-08-29 | QAP Rev1 | 0.5
1212 | 2025-09-01 | B224 | Megha(Pkg09) | ABB | SV | AVR | 5 | 5 | 2025-09-08 | 2025-09-09 | 2025-09-09 | 2025-09-10
1213 | 2025-09-01 | B378 | Paramount | KSBMIL | BT | Control Valves | 1 | 1
1214 | 2025-09-01 | B302 |  | YIL | NV | HHC | [9 empty] | 2025-09-01 | 2025-09-06 | PO 103 - 3 QAPs - TT, HC Det & HHC | 1
1215 | 2025-09-01 | B224 | Megha(SRU) | ICE(Asia) | NV | Optical Pyrometer | [9 empty] | 2025-09-01 | 2025-09-05 | Rev1 | 0.5
1216 | 2025-09-01 | B224 | Megha(SRU) | Sherman | NV | Thermal Mass Flowmeters | [9 empty] | 2025-09-01 | 2025-09-05 | Rev1 | 0.5
1217 | 2025-09-01 | B653 |  | Universal Insts | VR | Battery Charger & Batteries | [11 empty] | Attended Term.Comm.mtg | 0.5
1218 | 2025-09-06 | B224 | YIL | Pyrotech Workspace | NV | Aux Cons.
1219 | 2025-08-29 | B440 |  | YIL | NV | DCS | [9 empty] | 2025-08-29 | 2025-09-06 |  | 0.5
1220 | 2025-09-04 | B302 |  | YIL | NV | PLC | 1 | 1 | 2025-09-15 | 2025-09-19 | 2025-09-18 | 2025-09-19 | [6 empty] | 2
1221 | 2025-09-06 | B224 | Megha(SRU) |  | NV | USM | [9 empty] | 2025-09-04 | 2025-09-06 |  | 0.5
1222 | 2025-08-23 | B224 | Megha(Pkg10A) | TKIL/Emerson | NV | Mass Flow Meters | 8 | 8 | 2025-09-09 | 2025-09-12 | 2025-09-10 | 2025-09-11 | [5 empty] | Cal of MFMs @ FCRI - Rescheduled to 9-12/9 vide mail dt.23/8 - Gas serv.- prob.4" failed on 10/9
1223 | 2025-09-05 | B378 | Paramount | KSBMIL | BT | Control Valves | 1 | 1 | 2025-09-17 |  | 2025-09-17 | [6 empty] | PO643 on Para.
1224 | 2025-08-25 | B224 | Megha(Pkg09) | Advance Valves | US | Control Valves | [9 empty] | 2025-09-04 | 2025-09-04 |  | 0.5
1225 | 2025-09-08 | B224 | Megha(PPU) | Triparulex | SV | Fire Protection System | [9 empty] | 2025-09-08 | 2025-09-13 |  | 0.5
1226 | 2025-09-09 | B224 | Megha(Pkg09) | KSBMIL | BT | Control Valves | 12 | 9 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-17 | [6 empty] | 2
1227 | 2025-09-09 | B224 | Megha(Pkg09)/Siemens | Southern Lubrication | AG | LOS | 1 | 1 | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-14 | 2025-09-09 | 2025-09-15 |  |  |  |  | 0.5
1228 | 2025-09-09 | B224 | Megha(PPU) | DMW/Tmeic | SV | Motors | [9 empty] | 2025-09-09 | 2025-09-13 | Rev2-2 QAPs | 0.5
1229 | 2025-09-10 | B302 | YIL |  | NV | Turnkey Instn | [9 empty] | 2025-09-10 |  | Cables
1230 | 2025-09-10 | B378 |  | IL | BT | Control Valves | 26 | 26 | 2025-09-18 |  | 2025-09-18 | [6 empty] | B378/797
1231 | 2025-09-10 | B448 | ABB | Microfinish | AG | Plant Automation system | [9 empty] | 2025-09-10 | 2025-09-10 | Rev. of Metering/Blend skid QAPs +Mtg.to resolve issues & expedite; Expediting of Vlvs s/ordered by Sharp Tanks on request of Client & Pjts | 1
1232 | 2025-09-11 | B224 | Megha(pkg09) | Rotex | SV | Actuators | [9 empty] | 2025-09-11
1233 | 2025-09-12 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2025-09-18 | 2025-09-19 | 2025-09-18 | 2025-09-19 | [5 empty] | Raw mtl id+PAUT demo | 2
1234 | 2025-09-16 | B224 | Megha(PPU) | DMW/Tmeic | SV | Motors | 4 | 4 | 2025-09-22 | 2025-09-24 | 2025-09-22 | 2025-09-24 | 2025-10-15 | 2025-10-15 |  |  |  | 190kW,6.6kV(2)+225kW,6,6kV(2) | 3
1235 | 2025-09-16 | B224 | Megha(Pkg09) | KSBMIL | BT | Control Valves | 31 | 9 | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-23 | [5 empty] | insptd. On 17/9 | 1
1236 | 2025-09-16 | C007 |  | Welspun | BT | Pipe Mill |  |  | 2025-09-25 | 2025-10-07
1237 | 2025-09-15 | B224 | Megha(Pkg09) | Cords Cables | SV | Cables | [9 empty] | 2025-09-15 | 2025-09-15 |  | 0.5
1238 | 2025-09-15 | B224 | Megha(SRU) | Endress & Hauser | NV | USM | [9 empty] | 2025-09-15 | 2025-10-08 |  | 0.5
1239 | 2025-09-15 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 230 | 4 | 2025-09-17 |  | 2025-09-17 | [7 empty] | 1
1240 | 2025-09-12 | B224 | Megha(Pkg09) | Triveni Turbine | AG | Steam Turbine | 2 | 2 |  |  |  |  | 2025-09-15 |  |  |  |  | Triveni exp. Upon HO request | 0.5
1241 | 2025-09-12 | B224 | Megha(Pkg09)/Siemens | Southern Lubrication | AG | LOS | 1 | 1 | 2025-09-29 |  | 2025-09-29 |  | 2025-11-05 | 2025-11-05 |  |  |  | 2nd LOS
1242 | 2025-09-11 | B224 | Megha(Pkg09) | WiloMather/ABB | SV | Motors | [9 empty] | 2025-09-11 | 2025-09-13 |  | 0.5
1243 | 2025-09-12 | B224 | Megha(Pkg10) | ABB | NV | Analysers | 12 | 12 |  |  |  |  | 2025-09-13 | 2025-09-13 |  |  |  | O2 Anal | 0.5
1244 | 2025-09-13 | B378 | ABB |  | SV | ECS | 1 | 1 |  |  |  |  | 2025-09-15 |  |  |  |  | B378/833 | 0.5
1245 | 2025-09-02 | B224 | Megha(SRU) | Hitachi | SV | Capacitor Package | 2 | 2 |  |  |  |  | 2025-09-17 |  |  |  |  | rev. of (non)compliance to MOM obs. | 0.5
1246 | 2025-09-19 | B224 | Megha(SRU) | C&S | SV | Sw Bds | [9 empty] | 2025-09-19
1247 |  | B224 | Megha(Pkg09)
1248 | 2025-09-02 | B224 | Megha(Pkg09) | Siemens/KSBMIL | BT | Control Valves | 47 | 47 | 2025-09-09 | 2025-09-10 | 2025-09-16 | 2025-09-17 | [6 empty] | 2
1249 | 2025-09-19 | B224 | Megha(SRU) | C&S | SV | Sw Bds | 1 | 1 | 2025-09-25 | 2025-09-27 | 2025-09-25 | 2025-09-27 | [6 empty] | 3
1250 | 2025-09-19 | B378 |  | ABB | NV | Analyser Shelter | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-23 | 2025-09-24 | [5 empty] | PO618 | 2
1251 | 2025-09-19 | C007 |  | Welspun | BT | Pipe Mill |  |  | 2025-09-25 | 2025-10-07
1252 | 2025-09-22 | B269 |  | BDK Valves | AG | Valves | [6 empty] | 2025-09-26 |  |  |  |  | Rev.of prog. Of rect. Of vlvs | 1
1253 | 2025-09-22 |  | KEPL | Tmeic | SV | Drives | 2 | 2 | 2025-10-10 | [8 empty] | Light load test-400kVA VFD
1254 | 2025-09-22 | B224 | Megha(PPU) | DMW/GE/CGL | SV | Motors | [9 empty] | 2025-09-22 | 2025-09-23 | ITP Rev1-2900kW
1255 | 2025-09-22 | B933 | Flowserve | Laxmi Hydraulics | SV | Motors | [9 empty] | 2025-09-22 |  |  | 0.5
1256 | 2025-09-22 | B862 |  | Flowserve | BT | Pumps | [9 empty] | 2025-09-22 | 2025-09-22 | PO61 ITP, impeller balancing & Hyd. Test proc. appl | 0.5
1257 | 2025-09-22 | B224 | Megha(Pkg09) |  | SV | Cables | [9 empty] | 2025-09-22 | 2025-09-23 |  | 0.5
1258 | 2025-09-23 | B269 |  | YIL | NV | DCS | [6 empty] | 2025-09-23 | 2025-09-23 |  |  |  | Rev/IRN end.-MCR system+short items of U&O/DHDT/VGO | 0.5
1259 | 2025-09-25 | B795 |  | Shirdi Sai | SV | Transformer | 4 | 4 | 2025-10-06 | 2025-10-10 | 2025-10-06 | 2025-10-10 | 2025-11-21 | 2025-11-21 |  |  |  | PO no.15: 2nos 33kV/11kV 6.3/8MVA t/f;33kV/6.9kV 10/12.5MVA-2nos
1260 | 2025-09-27 | B224 | Megha(PPU) | Sundyne/ABB | SV | Motors | [9 empty] | 2025-09-27 | 2025-09-29 | ITP Rev1 | 0.5
1261 | 2025-09-26 | B224 | Megha(Pkg09) | Siemens/KSBMIL | BT | Control Valves | 13 | 13 | 2025-10-06 | 2025-10-07 | 2025-10-09
1262 | 2025-09-29 | B957 |  | Vihawk | VR | CCTV based Perimeter Surveillance System | [11 empty] | Mtgs. for ICP review | 1
1263 | 2025-09-29 | B440 | YIL | Delseal | NV | Video Wall | [9 empty] | 2025-09-11 | 2025-09-29 | QAP for Video Wall & Panel | 0.5
1264 | 2025-09-29 | B440 |  | YIL | NV | Field Insts | [6 empty] | 2025-09-29 | 2025-09-29 |  |  |  | PO103 | 0.5
1265 | 2025-09-29 | B440 |  | YIL | NV | PLC | [6 empty] | 2025-09-29 | 2025-09-29 |  |  |  | PO103 - PLC for 3 sections | 0.5
1266 | 2025-09-29 | B224 | Megha(Pkg09) | TDPS | SV | Alternators | 1 | 1 | 2025-08-22 | 2025-08-23 | 2025-08-22 | 2025-08-23 | 2025-09-29 | 2025-09-29 |  |  |  | Last Lot | 0.5
1267 | 2025-09-29 | B224 | Megha(Pkg09) | Vee Vee Controls | NV | Panels | 10 | 10 | 2025-08-21 | 2025-08-23 |  |  | 2025-09-29 | 2025-09-29 |  |  |  | NGT & LAPT | 0.5
1268 | 2025-09-29 | B224 | L&T(PFCCU) | YIL | NV | DCS | [6 empty] | 2025-09-29 | 2025-09-29 |  |  |  | Spares rev/endors. | 0.5
1269 | 2025-09-29 | B224 | Megha(SRU) | Emerson | NV | Magnetic Flowmeters | 2 | 2 | 2025-08-01 |  | 2025-08-01 |  | 2025-09-29 | 2025-09-29 |  |  |  | FCRI wet cal.reinsp. | 0.5
1270 | 2025-10-06 | B302 | Kalpataru | Powerica | NV | AMF Panel | 8 | 8 | 2025-10-10 | [8 empty] | Insp on 14/10 not confirmed by KPCL
1271 | 2025-10-07 | B302 |  | YIL | NV | Turnkey Instn | 3 | 3 | 2025-10-23 | 2025-10-25 | 2025-10-23 | 2025-10-25 | 2025-10-31 |  |  |  |  | PLCs for IPPS 1,2 & 3 | 4
1272 | 2025-10-06 | B302 | KEPL | Tmeic | NV | VFD | 2 | 2 | 2025-10-10 |  | 2025-10-13 | [6 empty] | Light load-2x400KVA
1273 | 2025-10-08 | B224 | Megha(SRU) | Rohrback Cosasco | NV | Corrosion Txers | [9 empty] | 2025-10-08 | 2025-10-21 |  | 0.5
1274 | 2025-10-08 | B861 |  | Enginemates | AG | Air Finned Cooler | [6 empty] | 2025-10-08 |  |  |  |  | Rev. of weld plan | 0.5
1275 | 2025-10-08 | B224 | Megha(SRU) | Endress & Hauser | NV | Ultrasonic FM | [9 empty] | 2025-10-08 | 2025-10-21 | Rev2 - 2 QAPs - E&H & Krohne | 0.5
1276 | 2025-10-07 | B269 |  | YIL | NV | DCS |  |  | 2025-10-13 | 2025-10-17 | 2025-10-13 | 2025-10-17 | [5 empty] | Indmax/Flare FAT | 5
1277 | 2025-10-07 | B224 | Megha(SRU) | C&S | SV | Sw Bds | [6 empty] | 2025-10-07 | 2025-10-23 |  |  |  | Expediting | 1
1278 | 2025-10-09 | B861 |  | Enginemates | AG | Air Finned Cooler | [9 empty] | 2025-10-08 | 2025-10-09 | ICP appl. | 0.5
1279 | 2025-10-13 | B224 | Megha(Pkg09) | Metaval | NV | Venturi | [9 empty] | 2025-10-13 | 2025-10-21 |  | 0.5
1280 | 2025-10-14 | B302 |  | YIL | NV | Turnkey Instn | [9 empty] | 2025-10-14 | 2025-10-15 | Mass FM QAP | 0.5
1281 | 2025-10-16 | B378 |  | KSBMIL | BT | Control Valves | 7 | 7 | 2025-10-27 | 2025-10-28 | 2025-10-27 | 2025-10-28 | 2025-10-29 |  |  |  |  | PO816 & 854 | 3
1282 | 2025-10-17 | B224 | Megha(SRU) | Nirmal Controls | BT | Pressure Regulating Valves | [9 empty] | 2025-10-17 | 2025-10-23 |  | 0.5
1283 | 2025-10-17 | B224 | Megha(SRU) | Chemtrols | NV | Variable Area Flowmeter | [9 empty] | 2025-10-17 | 2025-10-21 |  | 0.5
1284 | 2025-10-16 | B224 | Megha(SRU) | Koso | BT | Control Valves | [9 empty] | 2025-10-16 | 2025-10-23 |  | 0.5
1285 | 2025-10-16 | B224 | Megha(Pkg09) | Metaval | NV | Orifice Plates | [9 empty] | 2025-10-16 | 2025-10-21 |  | 0.5
1286 | 2025-10-17 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 230 | 14 | 2025-10-27 | 2025-10-30 | 2025-10-27 | [7 empty] | 1
1287 | 2025-10-17 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 31 | 8 | 2025-10-27 | 2025-10-30 | 2025-10-27 |  | 2025-11-04 | 2025-11-04 |  |  |  |  | 1
1288 | 2025-10-18 | B224 | Megha(SRU) | Belgaum Aqua | BT | Valves | 22 | 22 | 2025-10-22 |  | 2025-10-22 | [7 empty] | 1
1289 | 2025-10-18 | B224 | Megha(SRU) | Chemtrols | NV | Vortex Flowmeter | [9 empty] | 2025-10-18 | 2025-10-21 |  | 0.5
1290 | 2025-10-25 | B224 | Megha(PPU) | JSW/CGL | SV | Motors | [9 empty] | 2025-10-24 | 2025-10-28 | R2 | 0.5
1291 | 2025-10-27 | B957 | Vihawk | Infinova | NV | CCTV | [9 empty] | 2025-10-24 | 2025-10-27 |  | 0.5
1292 | 2025-10-30 | B224 | Megha(SRU) | Rohrback Cosasco | NV | Corrosion Txers | [9 empty] | 2025-10-30 | 2025-11-03 | R3 | 0.5
1293 | 2025-10-31 | B224 | Megha(SRU) | Emerson | BT | Control Valves | [9 empty] | 2025-10-31 |  | R0-Cat C- no rev.
1294 | 2025-10-31 | B903 |  | KSBMIL | BT | Control Valves | 1 | 1 |  |  |  |  | 2025-10-31 |  |  |  |  | TC rev+IRN end | 1
1295 | 2025-10-31 | B224 | Megha(SRU) |  | NV | Temp Elements | [9 empty] | 2025-10-31 | 2025-11-03 | CatC-No appl reqd | 0.5
1296 | 2025-11-01 | B224 | Megha(SRU) | Belgaum Aqua | AG | Valves | 200 | 200 | 2025-11-04 | 2025-11-06 | 2025-11-04 | 2025-11-06 | [6 empty] | 3
1297 | 2025-10-29 | B933 |  | Phils | AG | Vessels |  |  | 2025-11-03 |  | 2025-11-03 | [6 empty] | Plate Id. | 1
1298 | 2025-10-31 | B302 | Kalpataru | Powerica | SV | DG Sets | 8 | 8 | 2025-11-06 | 2025-11-14 | 2025-11-06 | 2025-11-14 | [6 empty] | 7
1299 | 2025-11-03 | B224 | Mahati Infra | FCG | SV | PDB | [6 empty] | 2025-11-13 | 2025-11-13 |  | 2025-11-03 | 2025-11-07 |  | 1
1300 | 2025-11-03 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2025-11-20 | 2025-11-21 | 2025-11-20 | 2025-11-21 | [5 empty] | PO26:Plate & Tube Id+Header Box Final Weld PAUTcalib.+2 finning vendors visit + Online mtg.with all stake holders on 19/11 | 2.5
1301 | 2025-11-19 | B269 |  | Microfinish | AG | Valves | [11 empty] | Visit to Expedite 1695 being f/up by IOC
1302 | 2025-11-04 | B224 | Megha(SRU) | Control & Schematics | SV | Sw Bds | [6 empty] | 2025-11-04 |  |  |  |  | TR Test Proc. | 0.5
1303 | 2025-11-05 | B862 |  |  | AG | [12 empty] | Job Spec for CS Vessels-ODC-rev. | 0.5
1304 | 2025-11-06 | B448 | ABB | Microfinish | BT | Valves | 2 | 2 | 2025-11-10 |  | 2025-11-18
1305 | 2024-11-07 | 4994 |  | Frenzelit | BT | [12 empty] | Enlistment survey | 1
1306 | 2025-11-06 | B302 |  | YIL | NV | Turnkey Instn |  |  | 2025-11-06 |  | 2025-11-06 | [6 empty] | Field Insts. | 0.5
1307 | 2025-11-06 | C028 | Tata Steel |  | NV | Pipes |  |  | 2025-11-12 | 2025-11-25 | 2025-11-12 | 2025-11-25 | [5 empty] | Coating | 12
1308 | 2025-11-10 | B359 | Corrtech | Ramtek | SV | Solar Charge Controller | 7 | 7 | 2025-11-18 |  | 2025-11-19
1309 | 2025-11-10 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 15 | 15 | 2025-11-24 | 2025-11-25
1310 | 2025-11-11 | B224 | Megha(SRU) | Koso | BT | Control Valves | [9 empty] | 2025-11-11 | 2026-01-10 | ITPR3-clarification on scope & enlistment recd. on 10/1 | 0.25
1311 | 2025-11-11 | B224 | Megha(LLDPE) | Chabi Electricals | SV | Battery Charger & Batteries | [9 empty] | 2025-11-11 | 2025-11-13 | Rev1 | 0.5
1312 | 2025-11-12 | B224 | Megha(Pkg09)/Siemens | Southern Lubrication | AG | LOS | 1 | 1 | 2025-09-29 |  | 2025-09-29 |  | 2025-11-12 | 2025-11-12 |  |  |  | 2nd LOS | 0.5
1313 | 2025-11-12 | B957 |  | Vihawk | VR | [12 empty] | Vir.Mtg.with client | 0.25
1314 | 2025-11-13 | B224 | Megha(SRU) | C&S | SV | Sw Bds | 2 | 2 | 2025-11-17 | 2025-11-18 | 2025-11-17 | 2025-11-18 | Exp. C&S |  |  |  |  | 4000A TR+PMCC2433 | 2.5
1315 | 2025-11-13 | B224 | Megha(Pkg09) | ABB | SV | AVR | 5 | 5 | 2025-09-08 | 2025-09-09 | 2025-09-09 | 2025-09-10 | 2025-11-13 | 2025-11-13 |  |  |  | compl. Rev+IRN endors. | 0.5
1316 | 2025-11-14 | B269 |  | YIL | VR | DCS |  |  | 2025-11-17 | 2025-11-21 | 2025-11-17 | 2025-11-21 | [5 empty] | SRU DCS/ESD/F&G FAT
1317 | 2025-11-14 | 4994 |  | Micon | AG | Valves |  |  |  |  | 2025-11-18 | [6 empty] | Reval. | 1
1318 | 2025-11-14 | 4994 |  | 2L | AG | Valves | [11 empty] | Enh. | 2
1319 | 2025-11-14 | B440 |  | BDK Valves | BT | Valves | [11 empty] | Excl. exp.visit -B269 & B440 | 1
1320 | 2025-11-14 | B269 |  | Microfinish | BT | Valves | [11 empty] | Excl. exp.visit -B269 & B440 | 1
1321 | 2025-11-11 | 4994 |  | Tmeic | SV | Motors | [11 empty] | Intl. Mtg on Prototype route - 11 & 17 | 0.5
1322 | 2025-11-17 | B653 |  | Ultrafilter | BT | Filters | [11 empty] | Excl. exp.mtg. | 0.5
1323 | 2025-11-14 | 4994 |  | TDPS | SV | Generators | [11 empty] | Reval. | 1
1324 | 2025-11-14 | B224 | Megha(Pkg09) | KSBMIL | BT | Control Valves | 7 | 7 |  |  |  |  | 2025-11-14 | 2025-11-14 |  |  |  | Rev/End. Of TPI repts/IRN | 0.5
1325 | 2025-11-15 | B378 | Kequip | Fogtech Fireprotection | NV | Water Mist System | [9 empty] | 2025-11-15
1326 | 2025-11-07 | B378 | Kequip | Chetan Corp | NV | Clean Agent System | [9 empty] | 2025-11-07 | 2025-11-15 |  | 0.5
1327 | 2025-11-17 | B224 | Megha(SRU) | Belgaum Aqua | AG | Valves | 54 | 54 | 2025-11-21 |  | 2025-11-21 |  | 2025-11-24 |  |  |  |  | Insp/Rev & Clearance of 214 nos vlvs on Belgaum Aqua | 2
1328 | 2025-11-17 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 230 | 15 | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26 | 2025-11-28 | 2025-11-28 |  |  |  |  | 0.5
1329 | 2025-11-17 | B224 | Megha(Pkg09) | KSBMIL | BT | Control Valves | 31 | 4 | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26
1330 | 2025-11-17 | B224 | Siemens | KSBMIL | BT | Control Valves | 75 | 25 | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26
1331 | 2025-11-17 | B224 | Siemens | KSBMIL | BT | Control Valves | 24 | 15 | 2025-11-25 | 2025-11-26 | 2025-11-25 | 2025-11-26
1332 | 2025-11-17 | B224 | Megha(Pkg09) | CGPower | SV | Power Transformers | [9 empty] | 2025-11-17 | 2025-11-18 | R0
1333 | 2025-11-17 | B302 | Ace Pipeline | HBL | SV | Batteries | [6 empty] | 2025-11-17 | 2025-11-17 |  |  |  | 360AH-16sets & 550AH-4sets doc rev+TPI IRN endors | 0.5
1334 | 2025-11-19 | B795 |  | Schneider | SV | Sw Bds |  |  | 2025-11-24 | 2025-11-26 | 2025-11-24 | 2025-11-26 | [6 empty] | 3
1335 | 2025-11-20 | B302 | YIL | Gauges Bourden | NV | Pressure Gauges | 142 | 142 |  |  |  |  | 2025-11-23 | 2025-11-23 |  |  |  | Turnkey Instn-Doc rev.&TPI IRN endors | 0.5
1336 | 2025-11-23 | B378 |  | YIL | NV | Spares | 1 | 1 |  |  |  |  | 2025-11-23 | 2025-11-23 |  |  |  | PO620-Spares-last lot | 0.5
1337 | 2025-11-24 | B224 | Megha(Pkg 09) | Thermax | NV | Instruments | [9 empty] | 2025-11-24 | 2025-12-03 |  | 0.5
1338 | 2015-11-26 | B224 | Megha(Pkg09) | Triveni Turbine | AG | Steam Turbine | 2 | 2 | [9 empty] | Rev.with Triveni & expediting based on pjts request | 0.5
1339 | 2025-11-24 | B224 | Megha(SRU) | C&S | SV | Sw Bds | 2 | 2 | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-29 | [6 empty] | 2
1340 | 2025-11-27 | B440 |  | Belgaum Aqua | AG | Valves | 1 | 1 |  |  |  |  | 2025-11-27 | 2025-11-27 |  |  |  | PO 267:Rev+End. Of TPI TCs | 0.5
1341 | 2025-11-27 | B302 | Kalpataru | Powerica | SV | DG Sets | 8 | 8 | 2025-12-03 |  | 2025-12-03 |  | 2025-12-08 | 2025-12-08 |  |  |  | Reinsp. Of failed DG | 1.5
1342 | 2025-11-27 | B224 | Megha(SRU) | Microsys Automation | SV | SAS | [9 empty] | 2025-11-27 | 2025-12-11 | SAS
1343 | 2025-11-28 | B224 | Megha(Pkg 09) |  | SV | Power Transformers | [9 empty] | 2025-11-28 | 2025-12-11 | 13.5/16MVA,66/6.9kV PT
1344 | 2025-11-29 | B224 | Vijay Tanks | Microfinish | BT | Valves | 7 | 7 | 2025-12-01 | 2025-12-02
1345 | 2025-12-01 | B224 | Megha(Pkg 09) | Triveni Turbine | AG | Steam Turbine | 2 | 2 | 2025-12-11 | 2025-12-16 | [8 empty] | 6
1346 | 2025-12-01 | B861 |  | Enginemates | BT | Air Finned Cooler | [9 empty] | 2025-12-01 | 2025-12-01 | PAUT proc. Appl. | 0.5
1347 | 2025-12-03 | B224 | Megha(SRU) | C&S | SV | Sw Bds | 2 | 2 | 2025-12-04 | 2025-12-05 | [7 empty] | PMCC2433-2500A,415V,AL,65kA/sec + PMCC 2432-4000A,415V,65kA/sec - final insp.
1348 | 2025-12-03 | 4994 |  | RSA Turbotech | AG | Piping Spools |  |  | 2025-12-04 |  | 2025-12-04 | [6 empty] | Reval. Survey | 1
1349 | 2025-12-03 | B653 |  | Ultrafilter | BT | Vessels | 4 | 4 | [9 empty] | B653/114-Exp. Mtg.10/12 | 0.5
1350 | 2025-12-04 | B224 | Megha(LLDPE) | PCTL/Emerson | BT | Control Valves | [9 empty] | 2025-12-04 |  | Level CVs -queried to Megha on Emerson appl.
| 2025-12-05 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 230 | 12 | 2025-12-15 | 2025-12-16 | 2025-12-15 | 2025-12-16 | [5 empty] | online
| 2025-12-05 | B440 |  | Belgaum Aqua | BT | Valves | 1 | 1 |  |  |  |  | 2025-12-05 | 2025-12-05 |  |  |  | PO-TP16I TC rev/IRN end. | 0.5
| 2025-12-08 | B302 | Kalpataru | Powerica | SV | DG Sets | 9 | 9 | 2025-12-15 | 2025-12-20 | 2025-12-17 | 2025-12-19 | 2026-01-06 | 2026-01-06 |  |  |  | 30KVA-4 & 40 KVA-5 nos | 3.5
| 2025-12-09 | B571 | ACIL | Universal Insts | SV | Battery Charger & Batteries | 1 | 1 | 2025-12-12 | 2025-12-13 | 2025-12-15 | 2025-12-17 | [5 empty] | 220V,165AH batt.ch | 3
| 2025-12-08 | B302 |  | Shirdi Sai | SV | Transformer | 2 | 2 | 2025-07-21 | 2025-07-22 | 2025-07-21 | 2025-07-22 | 2025-11-21 | 2025-11-21 |  |  |  | 6.6/3.3kV;10/12.5 MVA & 33/6.9kV,10/12.5MVA- Comp rev & IRN issue | 0.5
| 2025-12-09 | B795 |  | ABB | NV | Telecom System |  |  | 2025-12-12 |  | 2025-12-12 | [6 empty] | POC | 1
| 2025-12-10 | B378 |  | YIL | NV | DCS |  |  | 2025-12-15 | 2025-12-20 | 2025-12-15 | 2025-12-20 | [5 empty] | PDH ESD FAT | 5
| 2025-12-10 | B224 | Megha(Pkg09) |  | NV | Rotameter | [9 empty] | 2025-12-10 | 2025-12-23
| 2025-12-12 | B398 | Likitha | Kristron Controls & Systems | SV | CP TRU & CPPSM | [9 empty] | 2025-12-12 | 2025-12-15 |  | 0.5
| 2025-12-13 | B861 |  | Enginemates | BT | Air Finned Cooler |  |  | 2025-12-17 | 2025-12-18 | 2025-12-17 | 2025-12-18 | [5 empty] | Header boxes assembly Before PWHT-PT of Final weld, Visual & Dimension 2. Flange to Nozzle Pipe welding RT Film Interpretation;3.Finned tubes-visual & dimension 4. Material Identification (Bare Tubes and Flanges – MTC & Material Identification chart Review) - EM to go ahead - to be reviewed in next visit | 2
| 2025-12-15 | B448 | ABB | Hydrotherm | AG | Plant Automation system |  |  | 2025-12-18 | 2025-12-19 | 2025-12-19 | 2025-12-19 | [5 empty] | Metering & Blending Skid Hyd.test - spool piece hydro
| 2025-12-15 | B224 | Megha(SRU) | Microsys Automation | NV | Ethernet Panels |  |  | 2025-12-17
| 2025-12-13 | B302 | Bridge & Roof | Plantech | BT | Hot Tapping |  |  | 2025-12-15 |  | 2025-12-16 |  | 2025-12-30 | 2025-12-30 |  |  |  | Although CatB, Rev. of TPI repts done
| 2025-12-09 | B224 | Megha(Pkg09) | KSBMIL | BT | Control Valves | 14 | 14 | 2025-12-16 | 2025-12-17 | 2025-12-16 | 2025-12-17 | 2025-12-30 | 2025-12-30 |  |  |  | DSH+CV(3nos+1no) - BFV-24" (no DSH) - online
| 2025-12-15 | B224 | Megha(SRU) | C&S | SV | Sw Bds | 3 | 3 | 2025-12-18 | 2025-12-19 | [7 empty] | ASB,MLDB,EMLDB | 2
| 2025-12-16 | B378 |  | Belloseal | BT | Valves | 67 | 67 | 2025-12-16 |  | 2025-12-16 | [6 empty] | PO864 | 1
| 2025-12-17 | B224 | Megha(Pkg09) |  | SV | Power Cables | [9 empty] | 2025-12-17 | 2026-01-01 |  | 0.5
| 2025-12-18 | B933 |  | Phils Engg. | AG | Pressure Vessel | [11 empty] | Mtg. for AI scope,QAP revision & expediting
| 2025-12-19 | B224 | Vijay Tanks | Swims Technologies | AG | Valves | 7 | 7 | 2025-12-25 | 2025-12-26 | 2026-01-08 | 2026-01-09 | [5 empty] | not ready-vol.tank-29-30
| 2025-12-20 | B448 | ABB | Hydrotherm | AG | Plant Automation system |  |  | 2025-12-23 |  | 2025-12-23 | [6 empty] | Metering & Blending Skig Hyd test | 1
| 2025-12-22 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2025-12-29 | 2025-12-30 | 2025-12-29 | 2025-12-30 | [5 empty] | 28 plates +PWHT - 1d | 2
| 2025-12-22 | B448 |  | Hydrotherm | AG | Plant Automation system |  |  | 2025-12-30 | 2025-12-31 | [7 empty] | Met.+Blend Skid Fin.Insp. | 2
| 2025-12-22 |  |  | FS - bina | AG | [12 empty] | QAP-appl
|  |  |  | QLAR | AG | [12 empty] | Cat.Plan appl
|  | B795 |  | ECIL | NV | SCADA |  |  | 2026-01-06 |  | 2026-01-06 | [6 empty] | RTU PoC
| 2025-12-20 | B224 | Megha(pkg09) |  | NV | Signal Cables | [9 empty] | 2025-12-20 | 2026-01-01 |  | 0.25
| 2025-12-29 | B224 | Megha(Pkg09) | Triveni Turbine | BT | Steam Turbine |  |  | 2025-12-29 |  | 2025-12-29 | [6 empty] | re-insp. After rectification of unacceptable vibration | 0.5
| 2025-12-29 | B957 |  | Vihawk | NV | CCTV based Perimeter Surveillance System | [11 empty] | online mtg. | 0.25
| 2025-12-30 | B378 |  | ABB | SV | ECS | [7 empty] | 2025-12-30 |  |  |  | Rev. & end. Of Accessories & Spares | 0.25
| 2025-12-31 | B653 |  | Ultrafilter | AG | Filters | [11 empty] | Rev. mtg.
| 2025-12-30 | B224 | Megha(SRU) | C&S | SV | Sw Bds | 2 | 2 | 2025-12-04 | 2025-12-05 |  |  | 30d-ec-25 | 2025-12-30 |  |  |  | PMCC 2432-4000A,415V,65kA/sec - compl.rev+IRN endo. | 0.25
| 2025-12-30 | B224 | Megha(SRU) | Endress & Hauser | NV | [10 empty] | 2025-12-30
| 2025-12-30 | B861 |  | Enginemates | BT | Air Finned Cooler | [6 empty] | 2025-12-30 | 2025-12-30 |  |  |  | Rev+endors.of Anchor Bolts | 0.25
| 2026-01-01 | B224 | Vijay Tanks | Microfinish | BT | Valves | 7 | 7 | 2026-01-13 |  | 2026-01-14 |  |  | 2026-04-01 |  |  |  | Rev/IRN end. | 8
| 2026-01-01 | B224 | Megha(SRU) | Endress & Hauser | NV | Ultrasonic FM |  |  | 2026-01-19 | 2026-01-21 | 2026-01-20 | 2026-01-21 |  |  |  | 2026-01-01 | 2026-01-01 |  | 0.25
| 2026-01-01 | B224 | Megha(SRU) | Microsys Automation | NV | Ethernet Panels | 7 | 7 | 2026-01-05 |  | 2026-01-05 | [6 empty] | Internet Panels
| 2026-01-02 | B224 | Megha(Pkg10) | TKIL/Emerson | NV | Mass Flow Meters | 8 | 8 | 2026-01-20 | 2026-01-23 | 2026-01-20 | 2026-01-21 | [5 empty] | FCRI cal. | 2
| 2026-01-03 | B224 | Megha(SRU) | Endress & Hauser | NV | GWR Level Inst | [9 empty] | 2025-12-30 | 2026-01-03 | Rev0
| 2026-01-06 | B224 | Megha(Pkg09) | JSW/Hitachi Hirel | SV | VFD | [9 empty] | 2026-01-06 | 2026-01-06 | Rev3
| 2026-01-06 | B224 | Megha(Pkg09) | JSW/Raychem | SV | Transformer | [9 empty] | 2026-01-06 | 2026-01-06 | Rev3
| 2026-01-06 | B378 |  | Microfinish | AG | Valves |  |  | 2026-01-08 |  | 2026-01-08 | [6 empty] | PO990
| 2026-01-06 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-01-08 | 2026-01-09 | 2026-01-08 | 2026-01-09
| 2026-01-06 | B224 | Megha(Pkg08) | Atlas Copco/RSA Turbotech | AG | Seal Panel | 1 | 1 | 2026-01-12 | 2026-01-13 | 2026-01-12 | 2026-01-13
| 2026-01-07 | B224 | Megha(Pkg09) | Siemens/Southern Lub | AG | LOS | 1 | 1 | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | [6 empty] | 2
| 2026-01-07 | B224 | Megha(Pkg09) | CGPower | SV | Generator Transformer | [9 empty] | 2026-01-07 | 2026-01-09 | INSPECTION AND TEST PLAN FOR 60 MVA & 47 MVA STG TRANSFORMER R0 | 0.25
| 2026-01-07 | B519 |  | YIL | NV | Analyser | [6 empty] | 2026-01-07 | 2026-01-07 |  |  |  | Final Lot insp. Doc rev/IRN issue | 0.5
| 2026-01-08 | B224 | Megha(Pkg09) | Shreem Electricals | SV | Capacitors | [9 empty] | 2026-01-08 | 2026-01-09
| 2026-01-08 | B224 | Megha(Pkg09) | JSW/Hitachi Hirel | SV | VFD | [9 empty] | 2026-01-08 | 2026-01-09 | Rev2 | 0.25
| 2025-12-25 | B224 | Megha(pkg09) |  | NV | Signal Cables | [9 empty] | 2025-12-25 | 2026-01-08
| 2026-01-09 | B224 | L&T(PFCCU) | Endress & Hauser | NV | Vortex Flowmeter | 2 | 2 | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-05 | [5 empty] | wet cal @ FCRI 2"&6" - remote/review
| 2026-01-09 | B224 | Megha(Pkg09) | Shreem/Meher Mangoldt | SV | Series Reactor |  |  | 2026-01-19 | 2026-01-20 | 2026-01-19 | 2026-01-20 | [6 empty] | 2
| 2026-01-09 | B224 | Megha(SRU) | Endress & Hauser | NV | [10 empty] | 2026-01-09 | 2026-01-21 | Rev2
| 2026-01-12 | 7716 |  | Godrej Busducts | SV | Busduct |  |  | 2026-01-23 |  | 2026-01-23 | [7 empty] | 1
| 2026-01-13 | B224 |  | ABB | SV | SCADA | [6 empty] | 2026-01-13 | 2026-01-13 |  |  |  | Pkg 18 - Rev+Irn End. For SCADA spares | 0.5
| 2026-01-14 | B378 |  | Belgaum Aqua | AG | Valves | 5 | 5 | 2026-01-23 |  | 2026-01-22 | [6 empty] | PO1004
| 2026-01-19 | B448 |  | ABB | AG | Plant Automation system | 2 | 2 | 2026-01-20 |  | 2026-01-21 | [6 empty] | Metering & Blending Skid Fin. Insp
| 2026-01-17 | B224 | Megha(SRU) |  | SV | Cables | [9 empty] | 2026-01-17 |  | FA & PA cables
| 2026-01-17 | B224 | Megha(SRU) | KSBMIL | AG | Control Valves | 1 | 1 | 2026-01-23 | [8 empty] | Doc rev.
| 2026-01-17 | B378 |  | Microfinish | AG | Valves |  |  | 2026-01-23 |  | 2026-01-23 | [6 empty] | PO990
| 2026-01-19 | B957 |  | Vihawk | VR | [12 empty] | Rev. Mtg. | 0.25
| 2026-01-19 | B860 |  | YIL | VR | Loading Automation System | [11 empty] | Rev. Mtg. | 0.25
| 2026-01-19 | B224 | Megha(Pkg10) |  | SV | Cables | [9 empty] | 2026-01-19 |  | EHV & HV cables
| 2026-01-19 | B224 | Megha(Pkg09) | CGPower | SV | Generator Transformer | [9 empty] | 2026-01-19 | 2026-01-21 | Rev1 | 0.25
| 2026-01-21 | B224 | Megha(PPU) | Cords Cables | SV | Cables | [9 empty] | 2026-01-21 | 2026-01-21 | Rev0 | 0.25
| 2026-01-21 | B957 |  | Vihawk | VR | [12 empty] | Rev. Mtg. | 0.25
| 2026-01-22 | B224 | Megha(SRU) | Endress & Hauser | NV | USM | [9 empty] | 2026-01-22 | 2026-01-29 | Rev2 - comments on CRS not incorporated
| 2026-01-22 | B224 | Megha(SRU) | Sherman | NV | Thermal Mass Flowmeters | [9 empty] | 2026-01-22 |  | Rev2 - not reqd. to be reviewed
| 2026-01-23 | B224 | Megha(SRU) | Delton | SV | Cables | [9 empty] | 2026-01-23
| 2026-01-23 | B224 | Megha(LLDPE) | Cords Cables | SV | Cables | [9 empty] | 2026-01-23 | 2026-02-03
| 2026-01-25 | B440 |  | YIL | NV | DCS |  |  | 2026-01-27 | 2026-01-31 | [7 empty] | PO256-EIL insp involved - NRL shifted to 16/2
| 2026-01-28 | B224 | Megha(SRU) | Endress & Hauser | NV | Ultrasonic FM | [9 empty] | 2026-01-28 | 2026-02-03 | Rev1
| 2026-01-29 | B378 |  | Belgaum Aqua | BT | Valves | 5 | 5 | 2026-01-29 |  | 2026-01-29 | [6 empty] | PO1004 - doc rev & IRN issue
| 2026-01-28 | B957 |  | Flowserve | BT | Pumps | 16 | 16 | [7 empty] | 2026-01-28 | 2026-01-28 | PO33 - ITP appl | 0.5
| 2026-01-28 | B795 |  | Essenar | SV | Transformer | 2 | 2 | 2026-01-29 | 2026-01-30 | 2026-01-29 | 2026-01-30 | [5 empty] | PO15 | 2
| 2026-01-30 | B448 |  | ABB | BT | Plant Automation system | 2 | 2 | 2026-02-03 |  | 2026-02-03 | [6 empty] | Metering Skid -final+pneumatic | 1
| 2026-02-02 | B224 | Megha | YIL | NV | DCS | [6 empty] | 2026-02-02 | 2026-02-02 |  |  |  | Rev+End of PDBs+IT H/w | 0.5
| 2026-02-02 | 4994 |  | Fasteners & Allied Products | BT | [12 empty] | Reval. | 1
| 2026-02-03 | B302 |  | Hitachi | SV | Capacitors | 2 | 2 | 2026-02-04 | 2026-02-05 | 2026-02-04 | 2026-02-05 | [5 empty] | PO116 | 2
| 2026-02-03 | B862 |  | Belgaum Aqua | BT | Valves | 662 | 330 | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-27 | [5 empty] | PO163 | 2
| 2026-02-04 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 1 | 1 | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 | 2026-02-04 |  |  |  | Doc rev.&IRN endors.
| 2026-02-04 | B895 |  | Fasteners & Allied Products | BT | Fasteners | 4024 | 4024 | 2026-02-09 |  | 2026-02-09 | [6 empty] | PO2805
| 2026-02-04 | B411 |  | Belgaum Aqua | BT | Valves | 3 | 3 | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-10 | [5 empty] | PO22
| 2026-02-04 | B862 |  | TS Flow Controls | BT | Valves | 5 | 5 | 2026-02-09 |  | 2026-02-09 |  |  | 2026-02-20 |  |  |  | PO139 | 1
| 2026-02-04 | B378 |  | Sivananda Pipe Fittings | BT | Fasteners | 49 | 49 | 2026-02-06 |  | 2026-02-06 | [6 empty] | PO 983
| 2026-02-03 | B302 | YIL | Metaval | NV | Restriction Orifice | [6 empty] | 2026-02-03 | 2026-02-03 |  |  |  | PO103
| 2026-01-29 | B224 | Megha(Pkg08) | Atlas Copco/BHEL | SV | [10 empty] | 2026-01-29 | 2026-02-03 | 6.6kV,550KW Rev2
| 2026-01-31 | B224 | Megha(SRU) | Delton | SV | FA& PA cables | [9 empty] | 2026-01-31 | 2026-02-03 | Rev1-2QAPs
| 2026-02-03 | B795 |  | ABB | NV | Telecom System | [11 empty] | Rev.mtg. with client as well
| 2026-02-04 | B795 |  | YIL | NV | DCS | [11 empty] | Rev.mtg.
| 2026-02-04 | B957 |  | Vihawk | NV | CCTV based Perimeter Surveillance System | [11 empty] | Mtg. on 4th & 5th to rev.QA reqts of JB,LED lights
| 2026-02-05 | B933 |  | YIL | NV | DCS | [11 empty] | Rev.mtg. with YIL
| 2026-02-05 | B224 | Megha(SRU) | Control & Schematics | SV | Sw Bds |  |  | 2026-02-10 | 2026-02-12 | [7 empty] | MCC-2443 & 2444 POSTPONED
| 2026-02-05 | B378 |  | Kequip | NV | Lab Instruments | [9 empty] | 2026-02-05 |  | UPS &Batteries
| 2026-02-06 | 4994 |  | Weir Mineral | BT | Hydro Cyclone |  |  | 2026-02-13 | [8 empty] | Enl. Surv. | 2
| 2026-02-06 | B224 | Megha(LLDPE) | Vertiv | SV | UPS | [9 empty] | 2026-02-06 | 2026-02-09
| 2026-02-06 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-02-18 | 2026-02-19 | 2026-02-18 | 2026-02-20 | [5 empty] | 1. Flange to Nozzle Pipe welding RT Film Interpretation2. Header boxes assembly After PWHT- Hardness(Weld & HAZ) & Visual & Dimensional & PAUT/UT/MPT 3. Tube to Tube sheet joint Root run air test 1. Finned tubes-visual & dimension POSTPONED from 12/13; Rev. Mtg with KLL CEO on 20/2 | 3
| 2026-02-02 | C068 |  | Flowserve | BT | Pumps | [11 empty] | KOM -with client/ho | 0.25
| 2026-02-07 | B224 | Megha(Pkg09) | CGPower | SV | Power Transformers | [9 empty] | 2026-02-07
| 2026-02-06 | B378 |  | YIL | VR | DCS | [11 empty] | Mtg. with GAIL followed by YIL & Eaton,for resolving FF diagnostics issue | 0.25
| 2026-02-06 | B957 |  | Vihawk | NV | CCTV based Perimeter Surveillance System | [11 empty] | Mtg. for LED lights & LVS QA reqts | 0.25
| 2026-02-04 | B224 | Megha(LLDPE) | JSW | SV | Motors | [9 empty] | 2026-02-04 | 2026-02-10
| 2026-02-09 | B957 |  | Vihawk | VR | CCTV based Perimeter Surveillance System | [11 empty] | Wkly rev.mtg | 0.25
| 2026-02-10 | B224 | Megha(SRU) | Emerson | NV | Vortex Flowmeter | 2 | 2 | 2026-02-11 | 2026-02-12 | [7 empty] | TPI repts to be provided for review
| 2026-02-10 | B302 | Shreem Electricals | Kalpa | SV | RVT |  |  | 2026-02-11 |  | 2026-02-11
| 2026-01-31 | B224 | Megha(Pkg09) | Meher Magoldt | SV | Series Reactor | [6 empty] | 2026-02-10 | 2026-02-10 |  |  |  | Rev+IRN end. | 0.5
| 2026-02-06 | B862 |  | QLAR | BT | Additive Loading Package | [6 empty] | 2026-02-12 | 2026-02-12 |  |  |  | ITP appl. | 0.5
| 2026-02-13 | B889 |  | Dubas | VR/SV | UPS | [11 empty] | Rev.mtg. with Dubas
| 2026-02-13 | B440 |  | YIL | NV | DCS |  |  | 2026-02-16 | 2026-02-20 | [7 empty] | FAT-PO256
| 2026-02-13 | B378 |  | K-Equip | NV | Lab Instruments | [9 empty] | 2026-02-13 | 2026-02-13 | UPS,Batteries & Elec Panels QAPs | 1
| 2026-02-16 | B302 |  | ABB | NV | Magnetic Flowmeters | [11 empty] | Job Survey-B302/103 | 1
| 2026-02-18 | B224 | Megha(SRU) | Control & Schematics | SV | Sw Bds | 4 | 4 | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-02-27 | [6 empty] | 4
| 2026-02-18 | B378 | ABB | Pyrotech | SV | Consoles | [6 empty] | 2026-02-18 | 2026-02-18 |  |  |  | Doc rev. & IRN end. | 0.5
| 2026-02-19 | B269 |  | YIL | NV | DCS | [9 empty] | 2026-02-17 | 2026-02-19 | FO Cable QAP appl. | 0.5
| 2026-02-21 | B224 | Megha(SRU) | Microsys Automation | NV | SAS | [6 empty] | 2026-02-21 | 2026-02-21 |  |  |  | Rev+IRN end | 0.5
| 2026-02-19 | B957 |  | Vihawk | VR | CCTV based Perimeter Surveillance System | [11 empty] | Rev Mtg.with Client | 0.25
| 2026-02-19 | B957 |  | Vihawk | VR | CCTV based Perimeter Surveillance System |  |  | 2026-02-23 | 2026-02-24 | 2026-02-23 | 2026-02-24 | [5 empty] | FAT | 2
| 2026-02-24 | 4994 |  | Belgaum Aqua | AG/BT | Valves | [11 empty] | Enhancement Survey | 2
| 2026-02-20 | B957 | Flowserve | Wolong & CGL | SV | Motors | [9 empty] | 2026-02-20 |  | PO133 -FS S/o-CGL
| 2026-02-23 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-02-26 | 2026-02-27 | 2026-02-26 | 2026-02-27 | [6 empty] | 2
| 2026-02-25 | B224 | Megha(PPU) | Delton | SV | Cables | [9 empty] | 2026-02-25
| 2026-02-25 | B224 | Megha(PPU) | JSW/Raychem | SV | Transformer | [9 empty] | 2026-02-25 | 2026-02-26
| 2026-02-25 | B224 | Megha(Pkg09) |  | SV | FA& PA cables | [9 empty] | 2026-02-25
| 2026-02-26 | B302 | Shreem Electricals | Meher Magoldt | SV | Series Reactor | 96 | 96 | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-10 | [5 empty] | S/o of B302/118 on Shreem(4 s/os) | 2
| 2026-02-26 | B411 | Bluegrass | SRMTL | BT | Weld Joints |  |  | 2026-03-03 |  | 2026-03-03 | [6 empty] | Stamp t/f @ Lab
| 2026-03-02 | B224 | YIL | BARCO | NV | [10 empty] | 2026-02-27 | 2026-03-02
| 2026-03-02 | B957 | Flowserve | CGL | SV | Motors | [9 empty] | 2026-02-27 | 2026-03-02 | B957/33-2QAPs appl | 0.5
| 2026-02-27 | B224 | Megha(LLDPE) | CGIPL | SV | Transformer | [9 empty] | 2026-02-27 | 2026-03-02
| 2026-02-27 | B224 | Megha(LLDPE) | Microsys Automation | NV | SAS | [9 empty] | 2026-02-27 | 2026-03-10 |  | 0.25
| 2026-02-27 | B224 | Megha(Pkg10) | Sterlite | SV | Cables | [9 empty] | 2026-01-27 | 2026-03-02 | EHV & HV cables | 0.5
| 2026-02-25 | B224 | Megha(PP0 | United Electric | SV | Busduct | [9 empty] | 2026-02-25 | 2026-03-03 |  | 0.25
| 2026-03-03 | B861 |  | Enginemates | BT | Air Finned Cooler |  |  | 2026-03-06 |  | 2026-03-06 | [6 empty] | Tube bundle header box paint DFT • PWHT hardness (Weld & HAZ), visual & dimensional checks • Header box final drilling • Tube to tube sheet root run air test • 6" & 2" pipe, plug and gasket identification • PAUT data interpretation | 1
| 2026-03-03 | B957 |  | Flowserve | SV&AG | Pumps | [9 empty] | 2026-03-03 | 2026-03-03 | Appl. Of ITPs,Test Procedures & QAPs of Pumps/Motors/Turbines | 1
| 2026-03-05 | B964 |  | Ratnamani | BT | Pipes |  |  | 2026-03-11 | 2026-03-23 | [7 empty] | Coating
| 2026-03-05 | B224 | Megha(pkg09) |  | SV | Capacitor Bank | [9 empty] | 2026-03-05 | 2026-03-13
| 2026-03-03 | B653 |  | Ultrafilter | BT | Filters | [11 empty] | Visit to wks for exp. PO114 on 3/3 | 0.5
| 2026-03-04 | B378 |  | Flowserve | BT | Pumps | [6 empty] | 2026-03-04 | 2026-03-04 |  |  |  | IRN against PO282 | 0.5
| 2026-03-04 | B862 |  | QLAR | BT | Additive Loading Package | [6 empty] | 2026-03-04 |  |  |  |  | Mtg. & ITP appls - Screw conveyer, Hopper agitator,Elec, Mech,Bulk Bag discharger,additive talc surge bin,Jumbo bag,Multicor Mass FM
| 2026-03-07 | B224 | Megha(pkg10) |  | SV | PA& FA Cables | [9 empty] | 2026-03-07
| 2026-03-07 | B224 | Megha(pkg09) | Delton | SV | Cables | [9 empty] | 2026-03-07 | 2026-03-09
| 2026-03-07 | B224 | Megha(pkg09) | JSW/Raychem | SV | Transformer | [9 empty] | 2026-03-07 | 2026-03-09
| 2026-03-09 | B861 |  | Enginemates | AG | Air Finned Cooler | [11 empty] | VC - Rev. of NDT reqts. & usage of PAUT in place of RT | 0.5
| 2026-03-09 | B933 |  | Flowserve | BT | Pumps | [9 empty] | 2026-03-08 | 2026-03-09 | PO154 ITP,Hyd.test & NDT proc. rev. | 0.25
| 2026-03-09 | B861 |  | Enginemates | BT | Air Finned Cooler |  |  | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | [5 empty] | PWHT hardness (Weld & HAZ), visual & dimensional checks � Header box final drilling. � Tube to tube sheet joint final Weld DP test. � Tube to tube sheet joint expansion. � Tube to tube sheet Joint Final weld air test. � Final Tube Bundle HYDRO & Dimension. � PAUT data interpretation. | 2
| 2026-03-10 | B378 |  | IL | BT | Control Valves | [6 empty] | 2026-03-10 | 2026-03-10 |  |  |  | PO797-Spares | 0.25
| 2026-03-10 | B411 | Bluegrass | SRMTL | AG | Weld Joints |  |  | 2026-03-12 |  | 2026-03-12 | [6 empty] | Lab testing | 1
| 2026-03-02 | B224 | Megha(PPU) | Microsys Automation | NV | SAS | [9 empty] | 2026-02-27 | 2026-03-10 |  | 0.25
| 2026-03-11 | B957 |  | Vihawk | VR | CCTV based Perimeter Surveillance System | [11 empty] | Rev.mtg. | 0.25
| 2026-03-12 | B269 |  | YIL | NV | DCS |  |  | 2026-03-23 | 2026-03-27 | [7 empty] | LPG/SR,ISOM,MSBlock,CDW/LOBS FAT
| 2026-03-13 | B862 |  | Belgaum Aqua | BT | Valves | 223 | 223 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-26 | [5 empty] | PO163
| 2026-03-13 | B224 | Megha(LLDPE) | CGIPL | SV | Transformer | [9 empty] | 2026-03-13 | 2026-03-17
| 2026-03-13 | B224 | Megha(LLDPE) | C&I | NV | C&I | [9 empty] | 2026-03-13
| 2026-03-13 | B224 | Megha(LLDPE) | Meher Magoldt | SV | Series Reactor | 48 | 48 | 2026-03-24 |  | 2026-03-24 | [6 empty] | Shreem S/o | 1
| 2026-03-13 | B448 |  | ABB | BT | Plant Automation system |  |  | 2026-03-23 |  | 2026-03-24 | [6 empty] | Blending Skid Fin. Insp | 1
| 2026-02-27 | B224 | Megha(LLDPE) | Raychem | SV | Transformer | [9 empty] | 2026-02-27 | 2026-03-13
| 2026-02-27 | B224 | Megha(LLDPE) | Delton | SV | Cables | [9 empty] | 2026-02-27 | 2026-03-13
| 2026-03-16 | B860 | YIL | Woodfield | BT | Loading Arm | [9 empty] | 2026-03-16 | 2026-04-01 |  | 0.25
| 2026-03-16 | B224 | Megha(PPU) | Vertiv | SV | UPS | [9 empty] | 2026-03-16 | 2026-03-17
| 2026-03-16 | B224 | Megha(PPU) | Microsys Automation | NV | SAS | [9 empty] | 2026-03-16 | 2026-03-20 | Rev1
| 2026-02-27 | B224 | Megha(LLDPE) | Delton | SV | FA & PA Cables | [9 empty] | 2026-03-14 | 2026-03-17
| 2026-03-07 | B224 | Megha(Pkg 09) | Delton | SV | FA&PACables | [9 empty] | 2026-03-12 | 2026-03-17
| 2026-03-30 | B302 | YIL | Exprotecta | NV | PB | [6 empty] | 2026-03-20 | 2026-03-20 |  |  |  | Rev/End. of TPI reports | 0.5
| 2026-03-18 | B224 | Megha(LLDPE) | Microsys Automation | NV | SAS | [9 empty] | 2026-03-18 | 2026-03-20
| 2026-03-18 |  |  | BEL | VR | [12 empty] | Visit to BEL with MBD -
| 2026-03-17 |  |  | HAL | VR | [12 empty] | Visit to HAL with MBD
| 2026-03-21 | B224 | Megha(SRU) | C&S | SV | Sw Bds |  |  | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02
| 2026-03-24 | B767 |  | OLA | VR | ACC | [11 empty] | Qtrly Visit on 24/3
| 2026-03-23 | B224 | VTV | Flowserve | BT | Control Valves | 5 | 5 | 2026-04-07
| 2026-03-17 | B224 | Megha(SRU) | KEC Asian Cables | SV | MV Power Cables | [9 empty] | 2026-03-17 | 2026-03-23 |  | 0.5
| 2026-03-20 | B224 | Megha(PPU) | Escorts Kubota | SV | Heater Control Panel | [9 empty] | 2026-03-20 | 2026-03-23 |  | 0.5
| 2026-03-23 | B224 | Megha | Endress & Hauser | NV | Ultrasonic FM | [9 empty] | 2026-03-23 | 2026-03-30 | Rev1-Rejected.
| 2026-03-23 | B224 | Megha(LLDPE) | CGIPL | SV | Transformer | [9 empty] | 2026-03-23 | 2026-03-25 | Rev1 | 0.25
| 2026-03-26 | 4994 |  | Polyvalvetech | AG | Valves |  |  | 2026-04-15 | [8 empty] | Enl.Surv. | 2
| 2026-03-27 | B224 | Megha(Pkg10A) | CGIPL | SV | Transformer | [9 empty] | 2026-03-27 | 2026-03-27 |  | 0.25
| 2026-03-27 | B224 | Megha(Pkg10A) | CGIPL | SV | Transformer | [9 empty] | 2026-03-27 |  | Emergency Dist. T/f-ref. docs sought
| 2026-03-30 | B519 |  | Flowserve | BT | Pumps | [11 empty] | Insp | 1
| 2026-04-01 | B862 |  | Flowserve | BT | Pumps | 2 | 2 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | [5 empty] | Hydro,Impeller Bal. | 2
| 2026-04-01 | B860 | YIL | Severn Glocon | NV | Control Valves | [10 empty] | 2026-04-01 |  | 0.25
| 2026-04-01 | B895 | Flowserve | CGL | SV | Motors | [9 empty] | 2026-04-01 |  | B895/3-S/o-315kW,6.6KV
| 2026-03-30 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01
| 2026-03-31 | B224 | Megha(PPU) | Microsys Automation | NV | SAS |  |  | 2026-04-06
| 2026-04-28 | B224 | Megha(Pkg09) | Microsys Automation | NV | SAS | [6 empty] | 2026-04-28 | 2026-04-28 |  |  |  | rev+end. Of TPI reports | 0.5
| 2026-04-27 | B224 | Megha(LLDPE) | Tri-Parulex | SV | NIFPS | [9 empty] | 2026-04-27 | 2026-04-28 |  | 0.25
| 2026-04-28 | B302 | Ecotanks | Yaskawa | SV | Drives |  |  | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-05 | [5 empty] | S/o | 3
| 2026-04-27 | B224 | Megha(PPU) | Sundyne | NV | [10 empty] | 2026-04-13 | 2026-04-28 | E&I items | 0.25
| 2026-04-21 | B795 |  | Microfinish | BT | Valves | 2 | 2 | 2026-04-27 |  | 2026-04-27 | [6 empty] | PO 60
| 2026-04-15 | B224 | Megha(LLDPE) | Endress & Hauser | NV | UFM | [9 empty] | 2026-04-15 | 2026-04-24 |  | 0.25
| 2026-04-21 | B933 |  | TS Flow Controls | BT | Valves | [6 empty] | 2026-04-21 |  |  |  |  | PO16-rev. of docs
| 2026-04-28 | B378 |  | K-Equip | NV | HBL | [9 empty] | 2026-04-27 | 2026-04-28
| 2026-04-28 | B269 |  | YIL | NV | [7 empty] | 2026-04-28 | 2026-04-28 |  |  |  | PO1415-FO Cable doc rev/irn end. | 0.5
| 2026-04-29 | B933 |  | Flowserve | BT | HPRT Pumps | [11 empty] | PO118-Rev. mtg. with FS/SL & HO
| 2026-04-06 | B861 |  | Enginemates | BT | Air Finned Cooler |  |  | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | [5 empty] | ube to Tube sheet joint DPT Test TTSJ final Welding • Tube to Tube sheet joint Tube Expansion • Tube to tube sheet final air test • Final Inspection for Tube bundle - Dimensional/Visual & Hydro Test • PWHT hardness (Weld & HAZ), visual & dimensional checks • Header box final drilling • Re-hydro nozzle stiffener change (8 mm → 16 mm)- Dimensional/Visual & Hydro Test | 2
| 2026-04-20 | B861 |  | Enginemates | BT | Air Finned Cooler |  |  | 2026-04-27 | 2026-04-28 | 2026-04-27 | 2026-04-28 | [5 empty] | Tube to tube sheet final air test • Final Inspection for Tube bundle - Dimensional/Visual & Hydro Test | 2
| 2026-04-20 | B224 | Megha | [12 empty] | 2026-04-20 | 2026-04-22 | 2HT Cable QAPs | 0.5
| 2026-04-15 | B224 | Megha | Control & Schematics | SV | Sw Bds | 1 | 1 | 2026-04-16 | 2026-04-17 | 2026-04-16 | 2026-04-17 | [6 empty] | 2
| 2026-04-13 | B224 | Megha | CGIPL | SV | Transformer | [9 empty] | 2026-04-13 | 2026-04-15 | Pwr & Dist T/f QAPs+HT/LT Power Cables, DC-DC Batt Chargers,+Sundyne E&I ITP(10/4)+66kV Link Box+9/4-FPS;7/4-EHV Cables,Power Link Box-9 QAPs | 2
| 2026-04-10 | B269 |  | YIL | NV | [7 empty] | 2026-04-10 | 2026-04-10 |  |  |  | CDW LOBS doc rev+ IRN
| 2026-04-16 | B269 |  | YIL | NV | [7 empty] | 2026-04-16 | 2026-04-16 |  |  |  | ISOM Doc rev+IRN end
| 2026-04-16 | B378 |  | YIL | NV | [12 empty] | Console qap rev. - 16 & 17th
| 2026-04-29 | B378 |  | YIL | NV | [8 empty] | 2026-04-30 |  |  |  | Insp on 24,29 & IRN iss on 30 for man sp,PDBs & misc. items | 3
| 2026-04-28 | B860 | YIL | Emerson | NV | Mass Flow Meters | 3 | 3 | 2026-04-28 | 2026-04-30 | 2026-04-29 | 2026-04-30 | [5 empty] | Loading Arm QAP appl on 1/4;MFM QAP appl on 10/4 | 2.5
| 2026-04-10 | B795 |  | YIL | [12 empty] | 2026-04-10 | DCS QAP | 0.5
| 2026-05-01 | B795 |  | ABB | NV | Telecom System |  |  | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-06 | [5 empty] | PO57 | 3
| 2026-05-05 | B895 | Atlas Copco | Elliot Ebara Turbomachinery | AG | Turbine |  |  | 2026-05-11 | 2026-05-20 | 2026-05-20 | 2026-05-21 | [5 empty] | POB895/33-so -11,13,14,15,18&20 - Residual Unbalance Test, Low Speed Balance & Mechanical / Electrical Runout - 18-21/5(4d) | 4
| 2026-05-05 | B895 | Atlas Copco | Southern Lubrication |  | LOS |  |  | 2026-05-11 | 2026-05-12 | [7 empty] | POB895/33-s/o-PMI & Hydro | 2
| 2026-04-30 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-05-06 | 2026-05-08 | 2026-05-06 | 2026-05-08 | [6 empty] | 3
| 2026-04-30 | B933 |  | Flowserve | AG | Pumps | 4 | 4 | 2026-05-11 | 2026-05-12 | 2026-05-11 | 2026-05-12 | [5 empty] | PO 8- Hydro | 2
| 2026-05-06 | 4994 |  | ABB | SV | Motors | [11 empty] | Reval. Survey
| 2026-05-07 | B224 | Megha(Pkg09) |  | NV | Tank Level Inst | [9 empty] | 2026-05-07 | 2026-05-27
| 2026-05-07 | 8518 |  |  | NV |  |  |  | 2026-05-13 | 2026-05-14 | [7 empty] | Trg. At HO-cancelled | 0
| 2026-05-08 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-05-14 | 2026-05-15 | 2026-05-14 | 2026-05-15 | [5 empty] | Rev.mtg.with all stakeholders+ Tube to tube sheet final air test • Final Inspection for Tube bundle - Dimensional/Visual & Hydro Test | 2
| 2026-05-11 | C068 |  | Flowserve | AG | Pumps | [11 empty] | Rev. mtg. with all stake holders | 0.5
| 2026-05-12 | B224 | VTV | Microfinish | BT | Valves | 8 | 8 | 2026-05-15 |  | 2026-05-22 | [7 empty] | 1
| 2026-05-13 | B795 |  | ABB | NV | Telecom System |  |  | 2026-05-14 |  | 2026-05-14 | [6 empty] | Compl.witness | 1
| 2026-05-15 | B378 |  | Belloseal | BT | Valves | 5 | 5 | 2026-05-20 | [8 empty] | PO1085
| 2026-05-15 | B933 |  | Phils Engg. | BT | Pressure Vessels | 1 | 1 | 2026-05-25 | 2026-05-27 | 2026-05-25 | 2026-05-27 | 2026-06-01 | 2026-06-01 |  |  |  | PO13 | 4
| 2026-05-16 | B378 |  | Belgaum Aqua | BT | Valves | 46 | 46 | 2026-05-21 |  | 2026-05-21 | [6 empty] | PO1072 | 1
| 2026-05-18 | B795 |  | ABB | NV | Telecom System |  |  | 2026-05-18 |  | 2026-05-18 | [6 empty] | Punch pt. compliance visit | 1
| 2026-05-18 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-05-26 | 2026-05-27 | 2026-05-26 | 2026-05-27 | [5 empty] | Tube to tube sheet final air test • Final Inspection for Tube bundle - Dimensional/Visual & Hydro Test | 2
| 2026-05-09 | B224 | VTV | Flowserve | BT | Valves | [6 empty] | 2026-05-18 | 2026-05-18 |  |  |  | B795/58 | 0.5
| 2026-05-19 | B795 |  | Endress & Hauser | NV | Mass Flow Meters | 1 | 1 | 2026-05-20 | [8 empty] | No witness scope | 0
| 2026-05-20 | B224 | Megha(Pkg10A) |  | NV | HV VFD | [9 empty] | 2026-05-20 | 2026-05-26
| 2026-05-20 | B957 |  | Vihawk | NV | CCTV based Perimeter Surveillance System | [6 empty] | 2026-05-20 |  |  |  |  | Rev. of Vihawk IRN | 0.5
| 2026-05-20 | B224 | Megha(PPU) | CGL | NV | LT Motor | [9 empty] | 2026-05-20 | 2026-05-26
| 2026-05-20 | B224 | Megha(LLDPE) |  | NV | Lighting Fixture & Sw.gear equipment | [9 empty] | 2026-05-20 |  | Cat C- Rev. n.a
| 2026-05-22 | B224 | Megha(LLDPE) |  | NV | FLP Lighting & Power DB | [9 empty] | 2026-05-22
| 2026-05-21 | B440 |  | YIL | NV | Field Insts | 266 | 266 | [9 empty] | Rev+end. Of TPI IRN (YIL & ABB) | 1
| 2026-05-22 | B224 | Megha (SRU) | E&H | NV | [10 empty] | 2026-05-22 |  | ITP
| 2026-05-22 | B767 |  |  | VR | [12 empty] | Rev. of Insp. Methodology | 1
| 2026-05-30 | 7716 |  | Godrej Busducts | NV | Busduct | 2 | 2 | 2026-06-05 |  | 2026-06-05 | [6 empty] | Notice too short - to be taken up on 4 or 5/6 | 0
| 2026-05-26 | B378 |  | West Coast Optilinks | NV | FO Cable | [9 empty] | 2026-05-24 | 2026-05-26 | PO1090
| 2026-05-30 | B224 | Megha(PPU) |  | NV | MOV | [9 empty] | 2026-05-30 | 2026-06-08
| 2026-05-30 | B224 | Megha(Pkg09) |  | NV | ECS | [9 empty] | 2026-05-29 | 2026-06-15 | replied on 4/6 -after clarification,appd on 15/6
| 2026-05-27 | B224 | Megha | KEPL | SV | Motors | [9 empty] | 2026-05-27
| 2026-05-27 | B795 |  | YIL | NV | DCS | 1 | 1 | 2026-06-01 | 2026-06-03 | 2026-06-01 | 2026-06-03 | [6 empty] | 3
| 2026-06-01 | B224 | Megha(SRU) | Koso | BT | Control Valves | [9 empty] | 2026-06-01 | 2026-06-05
| 2026-06-02 | B861 |  | Enginemates | AG | Air Finned Cooler | [11 empty] | Rev.mtg. for expediting tubes & other items | 0.5
| 2026-06-02 | B862 |  | Flowserve | BT | Pumps |  |  | 2026-06-08 | 2026-06-09 | 2026-06-08 | 2026-06-09 | [5 empty] | Insp. Of Pumps-PO163 & appl. Of ITPs | 2
| 2026-06-02 | B862 |  | YIL | VR | DCS | [11 empty] | Rev. of Pjt.Sch | 0.5
| 2026-06-02 | B933 |  | Flowserve | BT | Pumps | 2 | 2 | 2026-06-08 | 2026-06-09 | 2026-06-08 | 2026-06-09 | [5 empty] | Aappl. Of ITPs | 2
| 2026-06-02 | B224 | Megha(SRU) |  | NV | Analysers | [9 empty] | 2026-06-02 | 2026-06-09
| 2026-06-02 | B861 |  | Enginemates | AG | Air Finned Cooler | 4 | 4 | 2026-06-10 | 2026-06-11 | 2026-06-10 | 2026-06-11 | [5 empty] | TTSJ FINAL WELD DPT / TTSJ EXPANISON/ TTSJ FINAL WELD AIR TEST / NOZZLE RT FILM • Final Inspection for Tube Bundle – Dimensional / Visual & Hydro Test -4 bundles | 2
| 2026-06-02 | B378 |  | Belgaum Aqua | AG | Valves | 74 | 51 | 2026-06-08 |  | 2026-06-09 | [6 empty] | PO1084 | 1
| 2026-06-03 | B378 |  | Micon | BT | Valves | 20 | 20 |  |  |  |  | 2026-06-03 | 2026-06-03 |  |  |  | PO1089 | 1
| 2026-06-03 | B378 |  | K-Equip | NV | Lab Instruments | [6 empty] | 2026-06-03 | 2026-06-03 |  |  |  | Sw Bds
| 2026-06-03 | B957 |  | Vihawk | NV | Cables | [9 empty] | 2026-06-02 | 2026-06-03 |  | 0.5
| 2026-06-03 | B933 |  | Flowserve | AG | Pumps | [10 empty] | 2026-06-03 | Appl. Of ITPs | 0.5
| 2026-06-04 | B411 | Likita | Synergy | NV | RTU | [9 empty] | 2026-06-04 |  | Scope/Tender doc. Sought
| 2026-06-04 | B933 |  | Flowserve | BT | Pumps | [11 empty] | HPRT Test proc. Rev. & mtg. on Y-type CV proc. | 0.5
| 2026-06-05 | B957 |  | Flowserve | AG | Pumps | [11 empty] | Mtg. on Turbine clarifications
| 2026-06-08 | B224 |  | Microsys Automation | VR | [12 empty] | VFD&PLC Job Survey | 2
| 2026-06-08 | B378 |  | Vihawk | NV | Cables | [9 empty] | 2026-06-02 | 2026-06-08 | Cables QAP
| 2026-06-08 | B378 |  | YIL | NV | Cables | [9 empty] | 2026-06-02 | 2026-06-08 | Cables QAP
| 2026-06-09 | B933 | Atlas Copco | Triveni Turbine | BT | Turbine | 1 | 1 | 2026-06-22 | 2026-06-23 | [7 empty] | Assembled Rotor At speed Bal. | 2
| 2026-06-09 | B269 |  | YIL | NV | DCS |  |  | 2026-06-16 | 2026-06-17 | [7 empty] | PDBs FAT | 3
| 2026-06-09 | B269 |  | YIL | NV |  |  |  | 2026-06-22 | 2026-06-25 | [7 empty] | MUG FAT | 3
| 2026-06-09 | B269 |  | YIL | NV |  |  |  | 2026-06-24 | 2026-07-02 | [7 empty] | MS Blk FAT | 1
| 2026-06-11 | B378 |  | 2L Engineers |  |  |  |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | PO1057 | 1
| 2026-06-11 | 4994 |  | Microfinish Pumps |  |  |  |  | 2026-06-19 |  | 2026-06-19 | [6 empty] | Shifting of wks | 1
| 2026-06-11 | B795 |  | Microfinish | Valves | [7 empty] | 2026-06-11 | 2026-06-11 |  |  |  | PO60
| 2026-06-12 | B860 |  | YIL | NV | [12 empty] | Mtg. with Woofield & all stake holders mtg. | 0.5
| 2026-06-12 | B224 | Megha | Cords Cables | SV | [10 empty] | 2026-06-12 | 2026-06-18
| 2026-06-14 | B224 | Megha(Pkg09) |  | NV | Ultrasonic FM | [9 empty] | 2026-06-22 | 2026-07-01 | Rev1
| 2026-06-12 | B224 | Megha(LLDPE) | JSW/GE | SV | Motors | [9 empty] | 2026-06-12 | 2026-06-18 | Rev3; also expediting of Pkg 9B -C&S for Swbds & site issues | 0.5
| 2026-06-13 | B795 |  | ECIL | VR | [12 empty] | Rev.mtg.with all stake holders & expediting+ Corr. On 16/6 | 0.5
| 2026-06-15 | B378 |  | K-Equip | NV | Sw Bds | [7 empty] | 2026-06-15 |  |  |  | Rev/end of Sw Bd IRN | 0.5
| 2026-06-15 | B895 |  | IL | BT | Control Valves | [11 empty] | PO5412:Mtg. for urgent dely. Advancement | 0.5
| 2026-06-15 | B795 | ABB |  | NV | Poles | [9 empty] | 2026-06-15 | 2026-06-15 | QAP of poles,VHF,Acoustic Booth
| 2026-06-16 | B860 | YIL | Cryogenic | AG | Metering Skid | [10 empty] | 2026-06-16 | Mtg. & QAP rev. of Met. Skid | 0.5
| 2026-06-16 | B224 | Megha(Pkg10) |  | SV | HV VFD | [9 empty] | 2026-06-16 | 2026-07-01
| 2026-06-16 | B285 | Megha(Pkg02) | KEPL/LHP | SV | Motors | [9 empty] | 2026-06-16 | 2026-07-07 | Mongol ref.
| 2026-06-16 | B895 | Atlas Copco | Southern Lubrication | BT | LOS |  |  |  | 2026-06-23 | 2026-06-24 | 2026-06-23 | 2026-06-24 |  |  |  |  | PO33
| 2026-06-17 | B861 | Enginemates |  | AG | Air Finned Cooler | [6 empty] | 2026-06-17 | 2026-06-17 |  |  |  | Doc.rev &IRN issue
| 2026-06-17 | 7716 | EIB | Godrej Busducts | NV | Busduct | [6 empty] | 2026-06-17 | [5 empty] | 0.5
| 2026-06-17 | B795 | ECIL |  | NV | [10 empty] | 2026-06-17 | 2026-06-17 | Consoles/Server Rack QAP appl | 0.5
| 2026-06-17 | B224 | Megha(SRU) | KSBMIL | BT | Control Valves | 8 | 8 | 2026-06-22 | 2026-06-23 | 2026-06-22 | 2026-06-23 | [6 empty] | 2
| 2026-06-17 | B224 | Megha(LLDPE) | Endress & Hauser | NV | Level Transmitter | [9 empty] | 2026-06-17 | 2026-07-01
| 2026-06-17 | B224 | Megha(LLDPE) | ABB | NV | Level Transmitter | [9 empty] | 2026-06-17 | 2026-07-01
| 2026-06-17 | B767 |  | Rajesh Exports | [13 empty] | Qtrly visit to Dhward | 2
| 2026-06-17 | B795 | Emerson | KSBMIL | BT | Control Valves | [11 empty] | S/o exp. Against PO69
| 2026-06-22 | B224 | Megha(Pkg10) |  | BT | Control Valves | [9 empty] | 2026-06-20
| 2026-06-20 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-06-29 | 2026-06-30 | 2026-06-30 | 2026-07-01 | [5 empty] | MRT | 2
| 2026-06-22 | B224 | Megha(Pkg10) | Emerson | NV | Mass Flow Meters | 4 | 4 | 2026-07-06 | 2026-07-10 | 2026-07-06 | 2026-07-10 | [5 empty] | Wet cal @ FCRI | 4
| 2026-06-24 | B285 | Megha |  | AG | [12 empty] | Expediting of MEIL orders on UF,Alleima & KSBMIL | 2
| 2026-06-24 | B933 |  | Flowserve | [13 empty] | Rev mtg. with client | 0.5
| 2026-06-25 | B957 |  | Flowserve | [13 empty] | Rev. mtg for all orders of B957,B943,C028,B862,B895,C247, | 0.5
| 2026-06-25 | B895 | Atlas Copco | RSA Turbotech | AG | Seal Gas Panel |  |  | 2026-06-26 | 2026-06-27 | [7 empty] | PO133 | 2
| 2026-06-25 | 4994 |  | Kalpa Electrikal | NV | [12 empty] | Reval
| 2026-06-25 | 4994 |  |  | AG | Air Finned Cooler | [11 empty] | Feedback on ACHE Enlistment Guidelines
| 2026-06-29 | B795 | ECIL | Udey Pyrotech | NV | Consoles | [7 empty] | 2026-06-29
| 2026-06-26 | 4994 |  | Cathodic Control | SV | [12 empty] | Revalidation visit
| 2026-06-29 | B224 | Megha(LLDPE) | Tri parulex | SV | NIFPS | [9 empty] | 2026-06-29 | 2026-07-01 | Elec. Comments already shared-rest appl by EILHyd
| 2026-06-29 | B795 | ABB | Baliga | NV | Consoles | [7 empty] | 2026-06-29 |  |  |  | Acoustic booth
| 2026-06-25 | B795 |  | YIL | NV | DCS | [7 empty] | 2026-06-25
| 2026-06-29 | B378 | YIL | Delton | NV | Cables | [7 empty] | 2026-06-29
| 2026-07-01 | B795 | ABB |  | NV | RF/VHF | [7 empty] | 2026-07-01 |  |  |  | PO 59
| 2026-07-01 | B957 |  | Flowserve | BT | Pumps | [9 empty] | 2026-07-01 |  | Rotor balancing proc - PO33
| 2026-07-01 | B933 |  | KSBMIL | BT | Valves | [11 empty] | KOM
| 2026-07-01 | B224 | Megha/Tata Pjts | Flowserve | BT | Pumps | [6 empty] | 2026-07-01 |  |  |  |  | Review of MRB
| 2026-06-30 | B269 |  | YIL | NV | DCS | [7 empty] | 2026-06-30 |  |  |  | MUG-1lot IRN
| 2026-07-02 | B224 | Megha(Pkg10) | ABB | SV | Drives | 4 | 4 | 2026-07-08 | 2026-07-10 | 2026-07-13 | 2026-07-15 | [5 empty] | Lot-1 Insp called off owing to T/f sourcing & TPI issue | 0
| 2026-07-03 | B224 | Megha(PPU) | Endress & Hauser | NV | Ultrasonic FM | [9 empty] | 2026-07-03 |  | R1
| 2026-07-03 | B224 | Megha(Pkg10) | Schneider | SV | Sw Bds | [9 empty] | 2026-07-03
| 2026-07-03 | B795 | ECIL | Udey Pyrotech | NV | Consoles | [7 empty] | 2026-07-03 |  |  |  | Consoles+Server rack - doc rev&IRN endo.
| 2026-07-03 | B224 | Megha(Pkg10) | Microsys Automation | NV | SAS | [9 empty] | 2026-07-03 | 2026-07-08 | Rev0
| 2026-06-27 | B224 | Megha(Pkg10) | ABB | SV | Drives | 4 | 4 | 2026-07-27 | 2026-07-29 | [7 empty] | Lot-2 Insp called off owing to T/f sourcing & TPI issue | 0
| 2026-07-07 | B285 | Megha(Pkg02) | KEPL/Tmeic | SV | HV Motors | [9 empty] | 2026-07-07 | 2026-07-07 | Mongol ref.
| 2026-07-08 | B224 | Megha(Pkg06) | Interactive Datasystems | NV | FO Cable | [9 empty] | 2026-07-08 | 2026-07-18
| 2026-07-06 | B224 | Megha(Pkg09) | Microsys Automation | NV | ECS | [9 empty] | 2026-07-06 | 2026-07-09 | Rev1
| 2026-07-07 | B224 | Megha(Pkg09) |  | SV | ACDB | [9 empty] | 2026-07-06
| 2026-07-09 | B895 | Coperion | Tmeic | SV | Motors | 3 | 3 | 2026-07-13 | 2026-07-14 | 2026-07-13 | 2026-07-14 | 2026-07-30 | 2026-07-30 |  |  |  | B895/34-2x400 & 1x355kW | 2
| 2026-07-09 | B861 |  | Enginemates | BT | Air Finned Cooler |  |  | 2026-07-16 | 2026-07-17 | 2026-07-16 | 2026-07-17 | [5 empty] | Fin insp of 4 tube bundles | 2
| 2026-07-09 | B224 | Megha(LLDPE) | Endress & Hauser | NV | Ultrasonic FM | [9 empty] | 2026-07-09 |  | R1
| 2026-07-09 | B964 |  | Shirdi Sai | SV | Transformer | 1 | 1 | 2026-07-27 | [8 empty] | Pr & Vac test | 1
| 2026-07-20 | 4994 |  | Steel Strong | AG | Valves | [11 empty] | Shifting of wks | 2
| 2026-07-10 | B862 |  | YIL | NV | DCS | [9 empty] | 2026-07-10 |  | QAP rev
| 2026-07-08 | B862 |  | YIL | VR | DCS | [11 empty] | SDM-VR+NV | 2
| 2026-07-10 | B895 |  | Tyco | NV | FA System | [9 empty] | 2026-07-10 | 2026-07-10 | QAP appl
| 2026-07-10 | B269 |  | Minebea | AG | Weigh Bridge | [11 empty] | Rev.mtg
| 2026-07-10 | B224 |  | ABB | NV | HV VFD | [9 empty] | 2026-06-16 | 2026-07-10 | R1
| 2026-07-10 | B795 |  | YIL | NV | DCS | [10 empty] | 2026-07-10
| 2026-07-11 | B224 | Megha(LLDPE) | Vijay Elec | SV | Lighting Fixture & Sw.gear equipment | [9 empty] | 2026-07-11
| 2026-07-11 | B224 | Megha(Pkg09) | United Electric | SV | Busduct | [9 empty] | 2026-07-11 | 2026-07-22
| 2026-07-13 | B861 |  |  | AG | [12 empty] | Rev.mtg with GAIL Dir
| 2026-07-10 | B224 | Megha(LLDPE) | KSBMIL | BT | [10 empty] | 2026-07-11
| 2026-07-13 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-07-23 | 2026-07-24 | 2026-07-23 | 2026-07-24
| 2026-07-13 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-07-30 | 2026-07-31
| 2026-07-13 | B224 | Megha(LLDPE) | Endress & Hauser | NV | Ultrasonic FM | [9 empty] | 2026-07-13 | 2026-07-13 | Rev2
| 2026-07-13 | B862 |  | Flowserve | AG | Pumps | 2 | 2 | 2026-07-16 | 2026-07-17 | 2026-07-16 | 2026-07-17 | 2026-07-23 | 2026-07-23 |  |  |  | Fin Insp | 3
| 2026-07-13 | B933 | Atlas Copco | RSA Turbotech | BT | Seal Gas Panel |  |  | 2026-07-20 | 2026-07-21 | [7 empty] | PO133-Hyd & PMI - to be witnessed as part of Fin. Insp-stage insp waived-TPI to be done | 2
| 2026-07-14 | B933 | Atlas Copco | Elliot Ebara Turbomachinery | AG | Turbine | 2 | 2 | 2026-07-22 | 2026-07-27 | 2026-07-21 | 2026-07-28 | [5 empty] | NLMRT -21/22 & 27,28/7 | 4
| 2026-07-14 | B224 | Megha(LLDPE) | Vega | NV | Nucleonic Level Instrument | [9 empty] | 2026-07-14 | 2026-07-17
| 2026-07-15 | B224 | Megha(Pkg10) | CGIPL | SV | Transformer | [9 empty] | 2026-07-15 | 2026-08-04
| 2026-07-15 | B224 | Megha(PPU) | Sundyne | BT | Dry Gas Seal |  |  | 2026-07-21 | 2026-07-22 | [7 empty] | RSA Turbotech cancelled by MEIL
| 2026-07-18 | B957 |  | Vihawk | NV | Poles | [7 empty] | 2026-07-18 |  |  |  | Poles IRN rev/end.
| 2026-07-18 | B224 | Megha(LLDPE) | Godrej Busducts | SV | Busduct | [9 empty] | 2026-07-18 | 2026-07-22
| 2026-07-20 | B378 |  | ABB | NV | Analysers | [11 empty] | Mtg. with GAIL/EILHO on spares
| 2026-07-21 | B224 | Megha(Pkg09) | Godrej Busducts | SV | Busduct | [9 empty] | 2026-07-21 | 2026-07-22
| 2026-07-24 | B895 |  | IL | BT | Control Valves | 12 | 12 | 2026-07-29 |  | 2026-07-29 | [7 empty] | 1
| 2026-07-24 | B224 | Megha(PKG09) |  | SV | Control Cables | [9 empty] | 2026-07-24
| 2026-07-24 | B224 | Megha(PKG09) | United Electric | SV | Busduct | [9 empty] | 2026-07-24 | 2026-08-21 | R1 | 0.5
| 2026-07-24 | B224 | Megha(PKG10A) |  | SV | Busduct | [9 empty] | 2026-07-24 | 2026-07-30
| 2026-07-22 | B224 | Megha(PPU) | Nov/BBL | SV | Motors | [9 empty] | 2026-07-22 | 2026-07-30
| 2026-07-24 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | [6 empty] | 1
| 2026-07-24 | B957 |  | 2L Engineers | BT | Valves | [11 empty] | RM identification-visit on 24/7 | 1
| 2026-07-25 | B964 |  | Shirdi Sai | SV | Transformer | [9 empty] | 2026-07-22 | 2026-07-25 | QAP appl
2026-07-27
| 2026-07-21 | B224 | Megha |  | SV | Control Cables | [9 empty] | 2026-07-21 | 2026-07-22
| 2026-07-27 | B378 |  | West Coast Optilinks | NV | FO Cable |  |  | 2026-07-28 |  | 2026-07-28 | [6 empty] | PO1090 | 2
| 2026-07-28 | B964 |  | Shirdi Sai | SV | Transformer | 2 | 2 | 2026-08-03 |  | 2026-08-03 | [6 empty] | PO29-Stg.Insp | 1
| 2026-07-28 | B895 | Atlas Copco | Elliot Ebara Turbomachinery | AG | Gas Turbine | 1 | 1 | 2026-08-10 |  | 2026-08-10 |  |  | 2026-08-24 |  |  |  | PO33-fin.insp | 2
| 2026-07-28 | B895 |  | Micon | AG | Valves | 97 | 97 | 2026-07-29 |  | 2026-07-29 | 2026-08-02 | [5 empty] | PO1224 | 2
| 2026-07-30 | B795 |  | YIL | NV | MCT | [7 empty] | 2026-07-29 |  |  |  | MCT ,Consoles,FO C -rev/IRN end. | 1
| 2026-07-29 | B224 | Megha(LLDPE) | Godrej Busducts | SV | Busduct |  |  | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | [5 empty] | 4000A&2000A | 3
| 2026-07-29 | B895 | Atlas Copco | RSA Turbotech | BT | Seal Gas Panel |  |  | 2026-08-11 | 2026-08-12 | 2026-08-11 | 2026-08-12 | [6 empty] | 2
| 2026-07-15 | B224 | Megha(PPU) | Sundyne/Process Equipments | BT | Dry Gas Seal |  |  | 2026-08-11 | 2026-08-12 | [7 empty] | RSA Turbotech -dev.acc. for ITP reqd | 2
| 2026-07-29 | B269 |  | YIL | NV | DCS | [6 empty] | 2026-07-29 |  |  |  |  | IRN- MSB NHT/ CCR/FGS
| 2026-07-28 | B957 |  | Flowserve | BT | Pumps | [11 empty] | PO201 ITP rev
| 2026-07-30 | B933 |  | Flowserve | BT | Pumps | 4 | 4 | 2026-08-05 | 2026-08-06 | 2026-08-05 | 2026-08-06 | [5 empty] | PO8;Hyd test | 2
| 2026-07-30 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-08-03 | 2026-08-04 | [7 empty] | Fin. Insp. | 1
| 2026-07-24 | C028 |  | Shirdi Sai | NV | Transformer | [11 empty] | KOM | 0.5
| 2026-07-30 | B302 |  | YIL | NV | Turnkey Instrumentation | [9 empty] | 2026-07-30 | 2026-07-30 | Heat Det.QAP appl
| 2026-07-31 | B224 | Megha(Pkg 9B) | Godrej Busducts | SV | Busduct | [9 empty] | 2026-07-31 | 2026-08-21 | R1 | 0.5
| 2026-07-31 | B933 | Flowserve | CGL | SV | Motors | [9 empty] | 2026-07-31 |  | PO151-850kW
| 2026-07-31 | B224 | Megha(Pkg09) | Anderson Greenwood | BT | Pressure Relief Valves | [9 empty] | 2026-07-31 | 2026-08-02
| 2026-08-03 | B933 | Sensia Global(SLB) | Flowserve | BT | Control Valves | 4 | 4 | 2026-08-05 |  | 2026-08-10 | [6 empty] | PO37 | 1
| 2026-08-03 | B224 | Megha(Pkg03) | Siemens/ | NV | AVR | [9 empty] | 2026-08-03 | 2026-08-18 | ref.docs N.A | 0.5
| 2026-08-03 | B224 | Megha(SRU) | Koso | BT | Control Valves | [9 empty] | 2026-08-03 | 2026-08-12 |  | 0.5
| 2026-08-03 | B285 | Megha(EPC02) | Sparkle Cleantech | NV | Control Valves | [9 empty] | 2026-08-03 | 2026-08-10 | CV,On-Off vlv,JB & Analyser | 0.5
| 2026-08-03 | B224 | Megha(Pkg09) |  | NV | Mag Flow Meter | [9 empty] | 2026-08-03 | 2026-08-10 |  | 0.5
| 2026-08-03 | B964 |  | Shirdi Sai | SV | Transformer | 4 | 4 | 2026-08-03 |  | 2026-08-03 | [6 empty] | Stage Insp (Vac & Pr test of Tanks) | 1
| 2026-08-04 | B933 |  | YIL | NV | DCS | [9 empty] | 2026-08-04 | 2026-08-12 | QAP R1 on portal
| 2026-08-04 | B795 |  | YIL | NV | OFC | [7 empty] | 2026-08-04 |  |  |  | Doc rev+IRN-OFC | 0.5
| 2026-08-01 | B224 | Megha(Pkg09) | C&S | SV | Sw Bds | [9 empty] | 2026-07-31 | 2026-08-01 | with stg.insp.
| 2026-08-04 | 4994 |  | Yaskawa | SV | Drives | [11 empty] | Reval.
| 2026-08-04 | B414 | Pace Process Controls | FCG | NV | Flame Proof Panel | [9 empty] | 2026-08-04 | 2026-08-18 | no ref.docs - QAP for some other client- should be returned by NV | 0.5
| 2026-08-05 | B378 |  | Schneider | SV | Sw Bds | [7 empty] | 2026-08-05 | 2026-08-05 |  |  | Addl panels ord. against PO725 | 1
| 2026-08-06 | B957 |  | Flowserve | BT | Pumps | [11 empty] | PO212-KOM | 0.5
| 2026-08-06 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-08-11 | 2026-08-13 | 2026-08-12 | 2026-08-14 | [6 empty] | 3
| 2026-08-06 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-08-17 | 2026-08-18 | [7 empty] | combined in next visit | 2
| 2026-08-06 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-08-20 | 2026-08-21 | 2026-08-19 | 2026-08-21 | [6 empty] | 3
| 2026-08-06 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-08-24 | 2026-08-25 | [8 empty] | 2
| 2026-08-06 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-08-31 | 2026-09-01 | [8 empty] | 2
| 2026-08-07 | B269 |  | YIL | NV | DCS |  |  | 2026-08-12 | [9 empty] | 1
| 2026-08-07 | B269 |  | YIL | NV | DCS |  |  | 2026-08-13 | 2026-08-18 | [8 empty] | 4
| 2026-08-07 | B269 |  | YIL | NV | DCS |  |  | 2026-08-24 | 2026-08-28 | [8 empty] | 0
| 2026-08-07 | B861 |  | ABB | VR | PLC | [11 empty] | KOM | 0.5
| 2026-08-06 | B224 | Megha(Pkg09) | Microsys Automation | NV | ECS | [9 empty] | 2026-08-06 | 2026-08-10 | Rev1 FAT proc+QAP | 0.5
| 2026-08-10 | B398 | Likitha | Jaisanth Automation | NV | Gas Detectors | [6 empty] | 2026-08-10 | 2026-08-10 |  |  |  |  | 0.5
| 2026-08-08 | B285 | Megha | TLT Engg./LHP | SV | Motors | [9 empty] | 2026-08-08 | 2026-08-14 |  | 0.5
| 2026-08-10 | B957 | BHEL | Gemscab | NV | HV Cables | [9 empty] | 2026-08-10 |  | PO 1021
| 2026-08-11 | B895 |  | Tyco | NV | FA System |  |  | 2026-08-11 |  | 2026-08-11 |  | 2026-08-11 | 2026-08-11 |  |  |  | Po141 | 1
| 2026-08-12 | B795 |  | YIL | NV | DCS | [9 empty] | 2026-08-12 | 2026-08-17 | LVS QAP | 0.5
| 2026-08-13 | B224 | SRU | YIL | NV | DCS |  |  | 2026-08-13 |  | 2026-08-13 | [6 empty] | SRU-Addl. Cabinets | 1
| 2026-08-13 | B224 | Megha(PKG10A) |  | NV | Power T/f | [9 empty] | 2026-08-13 |  | Power t/f & 66kV link Box
| 2026-08-13 | B224 | Megha(PKG9B) |  | NV | 66kV Link Box | [9 empty] | 2026-08-13
| 2026-08-13 | B933 |  | Flowserve | BT | Pumps | [11 empty] | PO118 Milestone certification | 0.35
| 2026-08-17 | B895 | Toyo | Schneider | SV | Sw Bds | 6 | 6 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | [6 empty] | 4
| 2026-08-17 | B895 |  | YIL | NV | DCS | [9 empty] | 2026-08-17 |  | On portal
| 2026-08-17 | B895 |  | WIL | NV | Temp Gauges | [9 empty] | 2026-08-17 |  | On portal-PO9370
| 2026-08-17 | B224 | Megha(Pkg09) | Microsys Automation | NV | ECS | 57 | 57 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | [6 empty] | 2
| 2026-08-18 | B895 | Coperion | Tmeic | SV | Motors | 1 | 1 | 2026-08-28 |  | 2026-08-28 | [6 empty] | 600kW -not ready | 0
| 2026-08-18 | B895 | Coperion | ABB | NV | Drives | 7 | 7 | 2026-08-27 | 2026-08-28 | [8 empty] | 2
| 2026-08-19 | B224 | Megha(Pkg09) |  | NV | Tank Level Inst | [9 empty] | 2026-08-19 |  | Rev1
| 2026-08-19 | B224 | Megha(SRU) | YIL | NV | DCS |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | [5 empty] | SRU Train1 FAT | 2
| 2026-08-19 | B224 | Megha(SRU) | Endress & Hauser | NV | [10 empty] | 2026-08-20
| 2026-08-21 | B224 | Megha(PPU) | Godrej Busducts | SV | Busduct | [9 empty] | 2026-08-20 | 2026-08-21 | R0-Pkg09 | 0.5
| 2026-08-19 | B795 | ECIL |  | NV | MCT | [10 empty] | 2026-08-19 | MCT & Cables QAP rev | 0.5
| 2026-08-24 | B861 | ABB |  | VR | [12 empty] | Rev mtg with client & test proc. Appl. | 0.5
| 2026-08-20 | 4994 | TS Flow Controls |  | AG/BT | Valves | [11 empty] | Enhancement Survey | 2
| 2026-08-24 | B933 |  | Phils Engg. | BT | Vessel | [7 empty] | 2026-08-24 |  |  |  | Rev/IRN issue for spares | 0.5
| 2026-08-13 | 4994 |  | RSA Turbotech | [13 empty] | Reval. | 1
| 2026-08-24 | B861 |  | Enginemates | BT | Air Finned Cooler |  |  | 2026-08-27 | 2026-08-28 | 2026-08-27 | 2026-08-28 | [6 empty] | 2
| 2026-08-24 | B957 |  | 2L Engineers | BT | Valves | 84 | 84 | 2026-08-27 |  | 2026-08-27 | [6 empty] | PO58 | 1
| 2026-08-24 | B224 | Megha(Pkg09) | ABB | NV | HV VFD | 38 | 6 | 2026-09-07 | 2026-09-09 | [8 empty] | 3
| 2026-08-25 | B957 |  | Flowserve | BT | Pumps | [10 empty] | 2026-08-25 | Pump ITPs-2 nos | 0.5
| 2026-08-27 | B224 | Megha(SRU) | YIL | NV | DCS | [7 empty] | 2026-08-27 |  |  |  | Compl. Rev+TPI IRN end. For SRU DCS | 1
| 2026-08-27 | B224 | Megha(Pkg09B) | Godrej Busducts | SV | Busduct | 10 | 10 | 2026-09-07
| 2026-08-27 | B224 | Megha(PPU) | Godrej Busducts | SV | Busduct | 5 | 5 | 2026-09-22 | 2026-09-24
| 2026-08-27 | B957 |  | Belgaum Aqua | BT | Valves | 11 | 11 | 2026-08-28 |  | 2026-08-28 | [6 empty] | PO106 | 1
| 2026-08-27 | B861 |  | Enginemates | AG | Air Finned Cooler |  |  | 2026-09-02 | 2026-09-03 | 2026-09-02 | 2026-09-03